## ClinicPaperDeltas
CLINIC PAPER | OVERALL PROJECT |  |  | Deltas for LCie Processes
Variables | Current | Expected | Delta |  | Current | Expected | Delta
AvgNumberofPagesinFacilityCriteria | 14 | 14 | 0 | LCie 01 - Facility Criteria | 0 | 0 | 0
AvgNumberofPagesinDisciplineSpecification | 400 | 400 | 0 | LCie 02 - Design Specification | 100 | 0 | 100
AvgNumberofPagesinProjectDefinition | 14 | 14 | 0 | LCie 03 - Feasibility Study | 700 | 0 | 700
AvgNumberofPagesinFrontMatter | 50 | 50 | 0 | LCie 04 - Project Definition | 0 | 0 | 0
AvgNumberofEquipment(product)Types(Types/project) | 155 | 155 | 0 | LCie 05 - Space Program | 2800 | 250 | 2550
AvgCountTaggedComponents(components/project) | 3950 | 3950 | 0 | LCie 06 - Product Program | 1900 | 150 | 1750
AvgNumberofSpaceTypesperBuilding | 159 | 159 | 0 | LCie 07 - Request for Proposal | 900 | 150 | 750
AvgTimetoLog(hours/transmittal) | 0.25 | 0 | 0 | LCie 08 - Design Early | 22500 | 5600 | 16900
AvgNumberofOptions | 3 | 3 | 0 | LCie 09 - Design Schematic | 32100 | 5500 | 26600
AvgPre-DesignSubmittalSetsReqd(sets/submittal) | 4 | 0 | 0 | LCie 10 -Design Coordinated | 94300 | 9800 | 84500
AvgNumberofSheetsperOption | 6 | 6 | 0 | LCie 11 - Design Final | 30300 | 3600 | 26700
AvgNumberofLetter-SizedPagesinDesignNarrativeperOption | 10 | 10 | 0 | LCie 12 - Request for Proposal | 2000 | 60 | 1940
AvgNumberofPagesinSpaceProgram | 65 | 65 | 0 | LCie 13 - Inquiry Issue | 1200 | 30 | 1170
AvgNumberofPagesinProductProgram | 33 | 33 | 0 | LCie 14 - Pre-Construction Plan | 0 | 0 | 0
NumberofDesignSubmittalSetsReqd(sets/submittal) | 6 | 0 | 0 | LCie 15 - Inquiry Issue (RFI) | 14000 | 700 | 13300
AvgNumberofSheetsinDesignEarlyDrawings | 48 | 48 | 0 | LCie 16 - Product Type Selection | 0 | 0 | 0
AvgNumberofLetter-SizedPagesinDesignEarlyNarrative | 60 | 60 | 0 | LCie 17 - System Layout | 0 | 0 | 0
AvgNumberofSheetsinDesignSchematicDrawings | 167 | 167 | 0 | LCie 18 - Submittal Package | 60700 | 4900 | 55800
AvgNumberofLetterSizedPagesinDesignSchematicNarrative | 60 | 60 | 0 | LCie 19 - Submittal Issue | 213900 | 4500 | 209400
AvgNumberofLetterSizedPagesinaDesignSchematicSpecification | 10 | 10 | 0 | LCie 20 - Purchase Order | 0 | 0 | 0
AvgNumberofSheetsinDesignCoordinatedDrawings | 218 | 218 | 0 | LCie 21 - Product Installation | 46700 | 18600 | 28100
AvgNumberofLetterSizedPagesinaDesignCoordinatedNarrative | 60 | 60 | 0 | LCie 22 - Start-Up | 0 | 0 | 0
AvgNumberofLetterSizedPagesinaDesignCoordinatedSpecification | 2156 | 2156 | 0 | LCie 23 - Product Inspection | 29100 | 1200 | 27900
AvgNumberofSheetsinDesignFinalDrawings | 316 | 316 | 0 | LCie 24 - Punchlist Issue | 100 | 0 | 100
AvgNumberofLetterSized'PagesinDesignFinalNarrative | 60 | 60 | 0 | LCie 25 - Turnover Package | 16900 | 200 | 16700
AvgNumberofLetterSizedPagesinDesignFinalSpecification | 2156 | 2156 | 0
AvgQTOTimeforEquipmentComponents(hours/plandrawing) | 0.083333 | 0.033333 | -0.05
AvgQTOTimeforSpacesinbuilding(hours/plandrawing) | 0.16667 | 0.066667 | -0.1
NumberofSubmittalSetsReqd(sets/submittal) | 6 | 0 | 0
AvgNumberofSubmittalItemsinaSubmittalPackageforeachEquipment(product)Type(submittalitems/submittalpackage) | 3 | 3 | 0
AvgNumberofSubmittalPagesinaSubmittalItem(pages/submittalitem) | 18 | 18 | 0
AvgNumberofSubmittalSheetsinaSubmittalItem(sheets/submittalitem) | 1 | 1 | 0
OwnerAdministrativeRate($/hour) | 23.71 | 23.71 | 0
OwnersRepRate($/hour) | 62.2 | 62.2 | 0
OwnersRepAdministrativeRate($/hour) | 16.88 | 16.88 | 0
PlannerRate($/hour) | 37.84 | 37.84 | 0
PlannerAdministrativeRate($/hour) | 16.82 | 16.82 | 0
LicensedProfessionalArchitectRate($/hour) | 109.989 | 109.989 | 0
Specifier | 109.99 | 109.99 | 0
ArchitectDrafterRate($/hour) | 70.7033 | 70.7033 | 0
ArchitectAdministrativeRate($/hour) | 45.9558 | 45.9558 | 0
ConstructionProjectManagerRate($/hour) | 125.8125 | 125.8125 | 0
Assistant(Construction)ProjectManagerRate($/hour) | 70.526 | 70.526 | 0
ContractorAdministrativeRate($/hour) | 44.188 | 44.188 | 0
AvgPerPageCopyCost($/page) | 0.15 | 0 | 0
AvgPerSheetCopyCost($/sheet) | 3 | 0 | 0
AvgNumberofSetsRequired(sets/submittal) | 2 | 0 | 0
AvgIn-houseReproductionTimePerSet(hours/set) | 0.009 | 0 | 0
AvgNumberofSetsRequired(sets/submittal) | 2 | 0 | 0
AvgIn-houseReproductionTimePerSet(hours/set) | 0.27 | 0 | 0
AvgNumberofTransmittals | 2 | 2 | 0
AvgIn-houseReproductionTimePerSubmittalSet(hours/submittalset) | 0.02 | 0 | 0
AvgMailingCostperTransmittal($/Transmittal) | 21.6 | 0 | 0
AvgTimetoPrepareTransmittal(hours/transmittal) | 0.16667 | 0.16667 | 0
AvgNumberofSetsRequired(sets/submittal) | 2 | 0 | 0
AvgIn-houseReproductionTimePerSet(hours/set) | 0.009 | 0 | 0
AvgTimeSpentRecreatingSpaceProgramCriteria(hours/space) | 0.25 | 0.025 | -0.225
AvgTimeSpentReformattingRoomDataSheet(hours/space) | 0.08333 | 0.008333 | -0.074997
AvgTimetoCompareSpaceProgramwithOwnerStandards(hours) | 1 | 0.05 | -0.95
AvgPercentageoferrorsinSpaceProgram | 0.3 | 0.3 | 0
AvgTimeSpentRecreatingSpaceProgram(hours/space) | 0.25 | 0.0125 | -0.2375
AvgNumberofTransmittals | 2 | 2 | 0
AvgMailingCostperTransmittal($/Transmittal) | 16.5 | 0 | 0
AvgTimetoPrepareTransmittal(hours/transmittal) | 0.16667 | 0.16667 | 0
AvgTimeSpentRecreatingProductProgramCriteria(hours/product) | 0.25 | 0.025 | -0.225
AvgTimetoCompareProductProgramwithOwnerStandards(hours/product) | 0.05 | 0.005 | -0.045
AvgPercentageoferrorsinProductProgram | 0.3 | 0.3 | 0
AvgTimeSpentRecreatingProductProgram(hours/product) | 0.083333 | 0.0041667 | -0.079166
AvgNumberofTransmittals | 2 | 2 | 0
AvgMailingCostperTransmittal($/Transmittal) | 23.95 | 0 | 0
AvgTimetoPrepareTransmittal(hours/transmittal) | 0.16667 | 0.16667 | 0
AvgNumberofLetterSizedPagesinRFP(pages/proposal) | 50 | 50 | 0
AvgNumberofDrawingSheetsinProposal(sheets/proposal) | 2 | 2 | 0
NumberofRFPcopiesReqd(sets/submittal) | 5 | 0 | 0
AvgNumberofTransmittals-OwnersRepdocumentstoBidders | 5 | 5 | 0
AvgNumberofTransmittals-ArchitecttoOwner | 1 | 1 | 0
AvgIn-houseReproductionTimePerSubmittalSet(hours/submittalset) | 0.04 | 0 | 0
AvgMailingCostperTransmittal($/Transmittal)-OwnersRepdocumentstoBidders | 18.8 | 0 | 0
AvgMailingCostperTransmittal($/Transmittal)-ArchitecttoOwnersRep | 18.8 | 0 | 0
AvgTimetoPrepareTransmittal(hours/transmittal)-OwnersRep | 0.75 | 0.75 | 0
AvgTimetoPrepareTransmittal(hours/transmittal)-Architect | 1 | 1 | 0
AvgTimeSpentReformattingSpaceProgramRequirements(hours/spacetype) | 0.16666 | 0.049998 | -0.11666
AvgTimeSpentReformattingEquipmentType(hours/product) | 0.25 | 0.075 | -0.175
AvgTimeSpentEvaluatingDesignEarlyDrawingsagainstDesignRequirements-SpaceandEquipment | 12 | 6 | -6
AvgTimetoCompareDesignEarlyDocumentswithOwnerStandards | 24 | 12 | -12
AvgTimespentmakingcorrectionsduetonon-conformancewithSpaceorProductProgram | 7.8497 | 0.78497 | -7.0647
AvgNumberofReviewCycles | 3 | 3 | 0
PercentageofTimeSpentbyLicensedProfessionalArchitect | 0.9 | 0.9 | 0
PercentageofTimeSpentbyArchitectDrafter | 0.1 | 0.1 | 0
AvgNumberofTransmittals | 3 | 3 | 0
AvgIn-houseReproductionTimePerSubmittalSet(hours/submittalset) | 0.173 | 0 | 0
AvgMailingCostperTransmittal($/Transmittal)-OwnersReptoArchitect | 16.5 | 0 | 0
AvgMailingCostperTransmittal($/Transmittal)-ArchitecttoOwnersRep | 27.1 | 0 | 0
AvgTimetoPrepareTransmittal(hours/transmittal) | 0.5 | 0.2 | -0.3
AvgNumberofPlanDrawingsinDesignSchematicDrawings | 18.4 | 18.4 | 0
AvgTimeSpentDevelopingEquipment(product)TypeTemplate(hours/producttype) | 0.25 | 0.025 | -0.225
AvgTimeSpentEvaluatingDesignSchematicDrawingsagainstDesignRequirements-SpaceandEquipment | 41 | 20.5 | -20.5
AvgTimetoCompareDesignSchematicDocumentswithOwnerStandards | 16 | 8 | -8
AvgTimespentmakingcorrectionsduetonon-conformancewithSpaceorProductProgram | 11.7745 | 1.1775 | -10.5971
AvgNumberofReviewCycles | 3 | 3 | 0
PercentageofTimeSpentbyLicensedProfessionalArchitect | 0.8 | 0.8 | 0
PercentageofTimeSpentbyArchitectDrafter | 0.2 | 0.2 | 0
AvgNumberofTransmittals | 3 | 3 | 0
AvgIn-houseReproductionTimePerSubmittalSet(hours/submittalset) | 0.504 | 0 | 0
AvgMailingCostperTransmittal($/Transmittal)-OwnersReptoArchitect | 16.5 | 0 | 0
AvgMailingCostperTransmittal($/Transmittal)-ArchitecttoOwnersRep | 47.7 | 0 | 0
AvgTimetoPrepareTransmittal(hours/transmittal) | 0.5 | 0.2 | -0.3
AvgNumberofPlanDrawingsinDesignCoordinateDrawings | 36.8 | 36.8 | 0
AvgTimeSpentDevelopingDetailedEquipment(products)TypeTemplate(hours/product) | 2 | 0.2 | -1.8
AvgTimeSearchingforProductLiteratureforCandidates(Hours/product) | 1 | 0.1 | -0.9
AvgTimeSpentEvaluatingDesignCoordinatedDrawingsagainstDesignRequirements-SpaceandEquipment | 38 | 19 | -19
AvgPercentofErrorsinProductTypeCandidate | 0.15 | 0.15 | 0
AvgTimetoCompareDesignCoordinated&ProductTypeCandidateDocumentswithOwnerStandards | 16 | 8 | -8
AvgTimeSpentmakingCorrectionsduetoNon-ConformancewithSpaceorProductProgram | 6.5414 | 0.65414 | -5.8873
AvgNumberofReviewCycles | 3 | 3 | 0
PercentageofTimeSpentbyLicensedProfessionalArchitect | 0.8 | 0.8 | 0
PercentageofTimeSpentbyArchitectDrafter | 0.2 | 0.2 | 0
AvgNumberofTransmittals | 3 | 3 | 0
AvgIn-houseReproductionTimePerSubmittalSet(hours/submittalset) | 2 | 0 | 0
AvgMailingCostperTransmittal($/Transmittal)-OwnersReptoArchitect | 16.5 | 0 | 0
AvgMailingCostperTransmittal($/Transmittal)-ArchitecttoOwnersRep | 87.3 | 0 | 0
AvgTimetoPrepareTransmittal(hours/transmittal) | 0.5 | 0.2 | -0.3
AvgNumberofPlanDrawingsinDesignFinalDrawings | 115 | 115 | 0
AvgTimeSpentDevelopingDetailedEquipment(products)TypeCandidate(hours/product) | 1 | 0.1 | -0.9
AvgTimeSpentEvaluatingDesignFinalDrawingsagainstDesignRequirements-SpaceandEquipment | 12 | 6 | -6
PercentageofTimeSpentbyLicensedProfessionalArchitect | 0.9 | 0.9 | 0
PercentageofTimeSpentbyArchitectDrafter | 0.1 | 0.1 | 0
AvgNumberofTransmittals | 1 | 1 | 0
AvgIn-houseReproductionTimePerSubmittalSet(hours/submittalset) | 2.3 | 0 | 0
AvgMailingCostperTransmittal($/Transmittal)-OwnersReptoArchitect | 16.5 | 0 | 0
AvgMailingCostperTransmittal($/Transmittal)-ArchitecttoOwnersRep | 118 | 0 | 0
AvgTimetoPrepareTransmittal(hours/transmittal) | 1 | 0.4 | -0.6
AvgNumberofTransmittals | 5 | 5 | 0
AvgIn-houseReproductionTimePerSubmittalSet(hours/submittalset) | 2.36 | 0 | 0
AvgMailingCostperTransmittal($/Transmittal) | 119.7 | 0 | 0
AvgTimetoPrepareTransmittal(hours/transmittal) | 0.75 | 0.75 | 0
AvgNumberofRequestforProposalSubmittalSetsReqd | 1 | 0 | 0
AvgNumberofTransmittals | 3 | 3 | 0
AvgMailingCostperTransmittal($/Transmittal) | 16.5 | 0 | 0
AvgTimetoPrepareTransmittalsforInquiryIssues(hours/transmittal)-Contractor/Architect | 0.16667 | 0.066667 | -0.1
AvgTimetoPrepareTransmittalsforInquiryIssues(hours/transmittal)-OwnersRep | 0.083 | 0.0332 | -0.0498
AvgNumberofRFIs | 87 | 87 | 0
AvgMailingCostperTransmittal($/Transmittal) | 16.5 | 0 | 0
AvgTimetoPrepareTransmittalsforInquiryIssues(RFI)(hours/transmittal)-Contractor/Architect | 0.16667 | 0.066667 | -0.1
AvgTimetoPrepareTransmittalsforInquiryIssues(RFI)(hours/transmittal)-Owner | 0.033333 | 0.013333 | -0.02
TimeSpentValidatingEquipment(products)TypeagainstTemplate(hours/product) | 0.5 | 0.25 | -0.25
AvgTimeSpentOrganizingEquipment(product)Typeinformation(hours/submittalitem) | 0.16667 | 0.016667 | -0.15
AvgTimeSpentEvaluatingEquipment(product)TypeSubmittalItemsagainstContractDocuments(hours/submittalitem) | 0.5 | 0.25 | -0.25
AvgTimetoSigneachPage(hours/page) | 0.083333 | 0 | 0
AvgTimetoStampeachSheet(hours/sheet) | 0.083333 | 0 | 0
PercentageofSubmittalsItemsrejected | 0.2 | 0.2 | 0
PercentageofTimeSpentbyConstructionProjectManager | 0.1 | 0.1 | 0
PercentageofTimeSpentbyAssistant(Construction)ProjectManager | 0.9 | 0.9 | 0
AvgNumberofTransmittals | 342 | 342 | 0
AvgIn-houseReproductionTimePerSubmittalSet(hours/submittalset) | 0.015 | 0 | 0
AverageMailingCostsperTransmittal($) | 16.5 | 0 | 0
AvgTimetoPrepareTransmittal(hours/transmittal) | 0.5 | 0.2 | -0.3
AvgTimeSpentEvaluatingProductTypeSubmittalItemsagainstContractDocuments(hours/producttypesubmittalitem) | 1 | 0.5 | -0.5
AvgTimeSpentRevisingoneProductSubmittalItem(hours/product) | 0.5 | 0.05 | -0.45
PercentageofProductSubmittalsreviewedbyLicensedArchitect | 0.25 | 0.25 | 0
PercentageofProductSubmittalsrejectedonfirstreview | 0.425 | 0.425 | 0
PercentageofProductSubmittalsrejectedonsecondreview | 0.25 | 0.25 | 0
PercentageofProductSubmittalsrejectedonthirdreview | 0.08 | 0.08 | 0
AvgTimeSpentTransferringCommentsperPage | 0.033333 | 0 | 0
AvgTimeSpentTransferringCommentsperSheet | 0.083333 | 0 | 0
PercentageofTimeSpentbyConstructionProjectManager | 0.8 | 0.8 | 0
PercentageofTimeSpentbyAssistant(Construction)ProjectManager | 0.2 | 0.2 | 0
AvgNumberofTransmittals | 6 | 6 | 0
AvgTimetoPrepareTransmittal(hours/transmittal) | 0.083333 | 0.033333 | -0.05
AvgMailingCostperTransmittal | 16.5 | 0 | 0
AvgTimeSpentRecordingComponentsData | 0.16667 | 0.066667 | -0.1
AvgNumberofMonthsofConstruction(months) | 12 | 12 | 0
TotalTimeSpentinOffice(hours/day) | 8 | 8 | 0
AvgPercentageofOfficeTimeSpentformattingProductInstallationReport | 0.25 | 0.025 | -0.225
AvgNumberofTransmittals(Transmittals) | 2 | 2 | 0
AvgMailingCostperTransmittal($/Transmittal) | 16.5 | 0 | 0
AvgTimetoPrepareaTransmittal(hours/transmittal) | 0.083333 | 0.033333 | -0.05
AvgTimeSpentDocumentingReportperSiteVisit(hours/visit) | 2.75 | 1.1 | -1.65
AvgNumberofSiteVisitspermonth | 4 | 4 | 0
AvgNumberofMonthsofConstruction | 12 | 12 | 0
TotalTimeSpentinOffice(hours/day) | 8 | 8 | 0
AvgPercentageofOfficeTimeSpentQuantifyingproductsinplace | 0.25 | 0.025 | -0.225
AvgNumberofTransmittals | 2 | 2 | 0
AvgMailingCostperTransmittal($/Transmittal) | 16.5 | 0 | 0
AvgTimetoPrepareTransmittal(hours/transmittal) | 0.083333 | 0.033333 | -0.05
AvgTimeSpentDocumentingPunchlistReportperSiteVisit | 0.25 | 0.025 | -0.225
AvgNumberofSiteVisitsforPunchlistInspection | 0.9 | 0.9 | 0
TotalTimeSpentinOffice | 1 | 1 | 0
AvgPercentageofOfficeTimeSpentDocumentingSiteVisit | 0 | 0 | 0
AvgNumberofTransmittals | 2 | 2 | 0
AvgMailingCostperTransmittal($/Transmittal) | 16.5 | 0 | 0
AvgTimetoPrepareTransmittal(hours/transmittal) | 0.25 | 0.1 | -0.15
AvgTimeSpentSearchingandAssemblingOperations&MaintenanceManuals(hours/document) | 3 | 0.3 | -2.7
AvgTimeSpentSearchingandAssemblingCommissioningReport(hours/document) | 0 | 0 | 0
AvgTimeSpentSearchingandAssemblingRecordSpecifications(hours/document) | 1.5 | 0.15 | -1.35
AvgTimeSpentSearchingandAssemblingRecord(As-Built)Drawings(hours/sheet) | 0.0008 | 8e-05 | -0.00072
AvgTimeSpentSearchingandAssemblingFinalApprovedShopDrawings(hours/sheet) | 0.0083333 | 0.00083333 | -0.0075
AvgNumberofPagesinOperations&MaintenanceManuals | 5425 | 5425 | 0
AvgNumberofPagesinCommissioningReport | 0 | 0 | 0
AvgNumberofPagesinRecordSpecifications | 2156 | 2156 | 0
AvgNumberofSheetsinRecord(As-Built)Drawings | 364 | 364 | 0
AvgNumberofSheetsinFinalApprovedShopDrawings | 1 | 1 | 0
AvgTimeSpentReviewingOperations&MaintenanceManuals(hours/page) | 0.0016667 | 0.00066667 | -0.001
AvgTimeSpentReviewingCommissioningReport(hours/page) | 0 | 0 | 0
AvgTimeSpentReviewingRecordSpecifications(hours/page) | 0.0016667 | 0.00066667 | -0.001
AvgTimeSpentReviewingRecord(As-Built)Drawings(hours/sheet) | 0.0083333 | 0.0033333 | -0.005
AvgTimeSpentReviewingFinalApprovedShopDrawings(hours/sheet) | 0.0083333 | 0.0033333 | -0.005
AvgTimeSpentFilingOperations&MaintenanceManuals(hours/document) | 0.08333 | 0 | 0
AvgTimeSpentFilingCommissioningReport(hours/document) | 0 | 0 | 0
AvgTimeSpentFilingRecordSpecifications(hours/document) | 0.08333 | 0 | 0
AvgTimeSpentFilingRecord(As-Built)Drawings(hours/sheet) | 0.0016667 | 0 | 0
AvgTimeSpentFilingFinalApprovedShopDrawings(hours/sheet) | 0.0016667 | 0 | 0
PercentageofTimeSpentbyConstructionProjectManager | 0.1 | 0.1 | 0
PercentageofTimeSpentbyAssistant(Construction)ProjectManager | 0.9 | 0.9 | 0
AvgIn-houseReproductionTimePerSubmittalSet(hours/submittalset) | 9 | 0 | 0
AvgMailingCostperTransmittal($/Transmittal) | 350.32 | 0 | 0
AvgTimetoPrepareTransmittal(hours/transmittal) | 0.5 | 0.2 | -0.3
217

## Intro
COBie Calculator
Purpose: | This research will identify the potential savings/cost for a project team if information is exchanged using a COBie-based approach over the traditional “Paper-Based” approach.
Project Phase Color Coding:
Criteria
Project Definition
Requirement
Bidding
Design
Construction
Assumptions Tab | Assumptions were made when developing the COBie Calculator. These assumptions should be modified based on your project variables in order to calculate the potential savings.
Information Attributes | L E G E N D
| Color | Description | Allowed User Actions
|  | user defined information unique to this worksheet | change on inputs worksheet in project phase variables section
|  | common user information, listed on assumptions worksheet | change on inputs worksheet
|  | calculated information | do not change this cell

## Summary
Cost Summary
OmniClass Project Phase (Table31) | Current Process | Expected Process | Savings | % Savings
LCie 01 - Facility Criteria | 0 | 0 | 0 | 0%
LCie 02 - Design Specification | 100 | 0 | 100 | 100%
LCie 03 - Feasibility Study | 700 | 0 | 700 | 100%
LCie 04 - Project Definition | 0 | 0 | 0 | 0%
LCie 05 - Space Program | 2800 | 250 | 2550 | 91.07%
LCie 06 - Product Program | 1900 | 150 | 1750 | 92.11%
LCie 07 - Request for Proposal | 900 | 150 | 750 | 83.33%
LCie 08 - Design Early | 22500 | 5600 | 16900 | 75.11%
LCie 09 - Design Schematic | 32100 | 5500 | 26600 | 82.87%
LCie 10 -Design Coordinated | 94300 | 9800 | 84500 | 89.61%
LCie 11 - Design Final | 30300 | 3600 | 26700 | 88.12%
LCie 12 - Request for Proposal | 2000 | 60 | 1940 | 97%
LCie 13 - Inquiry Issue | 1200 | 30 | 1170 | 97.5%
LCie 14 - Pre-Construction Plan | 0 | 0 | 0 | 0%
LCie 15 - Inquiry Issue (RFI) | 14000 | 700 | 13300 | 95%
LCie 16 - Product Type Selection | 0 | 0 | 0 | 0%
LCie 17 - System Layout | 0 | 0 | 0 | 0%
LCie 18 - Submittal Package | 60700 | 4900 | 55800 | 91.93%
LCie 19 - Submittal Issue | 213900 | 4500 | 209400 | 97.9%
LCie 20 - Purchase Order | 0 | 0 | 0 | 0%
LCie 21 - Product Installation | 46700 | 18600 | 28100 | 60.17%
LCie 22 - Start-Up | 0 | 0 | 0 | 0%
LCie 23 - Product Inspection | 29100 | 1200 | 27900 | 95.88%
LCie 24 - Punchlist Issue | 100 | 0 | 100 | 100%
LCie 25 - Turnover Package | 16900 | 200 | 16700 | 98.82%
Total | 570000 | 55200 | 515000 | 90.35%
Breakdown by Role
Cost Summary - Owner / Owners Rep
OmniClass Project Phase | Current Process | Expected Process | Savings | % Savings
LCie 01 - Facility Criteria | 0 | 0 | 0 | 0%
LCie 02 - Design Specification | 100 | 0 | 100 | 100%
LCie 03 - Feasibility Study | 100 | 10 | 90 | 90%
LCie 04 - Project Definition | 0 | 0 | 0 | 0%
LCie 05 - Space Program | 120 | 10 | 110 | 91.67%
LCie 06 - Product Program | 100 | 10 | 90 | 90%
LCie 07 - Request for Proposal | 800 | 60 | 740 | 92.5%
LCie 08 - Design Early | 6800 | 3100 | 3700 | 54.41%
LCie 09 - Design Schematic | 4400 | 2000 | 2400 | 54.55%
LCie 10 -Design Coordinated | 4400 | 1500 | 2900 | 65.91%
LCie 11 - Design Final | 5 | 0 | 5 | 100%
LCie 12 - Request for Proposal | 2000 | 60 | 1940 | 97%
LCie 13 - Inquiry Issue | 150 | 5 | 145 | 96.67%
LCie 14 - Pre-Construction Plan | 0 | 0 | 0 | 0%
LCie 15 - Inquiry Issue (RFI) | 4400 | 0 | 4400 | 100%
LCie 16 - Product Type Selection | 0 | 0 | 0 | 0%
LCie 17 - System Layout | 0 | 0 | 0 | 0%
LCie 18 - Submittal Package | 11400 | 1200 | 10200 | 89.47%
LCie 19 - Submittal Issue | 0 | 0 | 0 | 0%
LCie 20 - Purchase Order | 0 | 0 | 0 | 0%
LCie 21 - Product Installation | 0 | 0 | 0 | 0%
LCie 22 - Start-Up | 0 | 0 | 0 | 0%
LCie 23 - Product Inspection | 0 | 0 | 0 | 0%
LCie 24 - Punchlist Issue | 0 | 0 | 0 | 0%
LCie 25 - Turnover Package | 400 | 100 | 300 | 75%
Total | 35000 | 8100 | 27100 | 77.43%
Cost Summary - Architect
OmniClass Project Phase | Current Process | Expected Process | Savings | % Savings
LCie 01 - Facility Criteria | 0 | 0 | 0 | 0%
LCie 02 - Design Specification | 0 | 0 | 0 | 0%
LCie 03 - Feasibility Study | 600 | 10 | 590 | 98.33%
LCie 04 - Project Definition | 0 | 0 | 0 | 0%
LCie 05 - Space Program | 2700 | 230 | 2470 | 91.48%
LCie 06 - Product Program | 1800 | 170 | 1630 | 90.56%
LCie 07 - Request for Proposal | 200 | 70 | 130 | 65%
LCie 08 - Design Early | 15700 | 2400 | 13300 | 84.71%
LCie 09 - Design Schematic | 27700 | 3400 | 24300 | 87.73%
LCie 10 -Design Coordinated | 89900 | 8200 | 81700 | 90.88%
LCie 11 - Design Final | 30300 | 3600 | 26700 | 88.12%
LCie 12 - Request for Proposal | 0 | 0 | 0 | 0%
LCie 13 - Inquiry Issue | 240 | 10 | 230 | 95.83%
LCie 14 - Pre-Construction Plan | 0 | 0 | 0 | 0%
LCie 15 - Inquiry Issue (RFI) | 5500 | 400 | 5100 | 92.73%
LCie 16 - Product Type Selection | 0 | 0 | 0 | 0%
LCie 17 - System Layout | 0 | 0 | 0 | 0%
LCie 18 - Submittal Package | 6000 | 0 | 6000 | 100%
LCie 19 - Submittal Issue | 207000 | 3900 | 203100 | 98.12%
LCie 20 - Purchase Order | 0 | 0 | 0 | 0%
LCie 21 - Product Installation | 40 | 0 | 40 | 100%
LCie 22 - Start-Up | 0 | 0 | 0 | 0%
LCie 23 - Product Inspection | 29100 | 1200 | 27900 | 95.88%
LCie 24 - Punchlist Issue | 100 | 0 | 100 | 100%
LCie 25 - Turnover Package | 0 | 0 | 0 | 0%
Total | 417000 | 23600 | 393300 | 94.32%
Cost Summary - Contractor
OmniClass Project Phase | Current Process | Expected Process | Savings | % Savings
LCie 01 - Facility Criteria | 0 |  | 0 | 0%
LCie 02 - Design Specification | 0 |  | 0 | 0%
LCie 03 - Feasibility Study | 0 |  | 0 | 0%
LCie 04 - Project Definition | 0 |  | 0 | 0%
LCie 05 - Space Program | 0 |  | 0 | 0%
LCie 06 - Product Program | 0 |  | 0 | 0%
LCie 07 - Request for Proposal | 0 |  | 0 | 0%
LCie 08 - Design Early | 0 |  | 0 | 0%
LCie 09 - Design Schematic | 0 |  | 0 | 0%
LCie 10 -Design Coordinated | 0 |  | 0 | 0%
LCie 11 - Design Final | 0 |  | 0 | 0%
LCie 12 - Request for Proposal | 0 |  | 0 | 0%
LCie 13 - Inquiry Issue | 800 | 10 | 790 | 98.75%
LCie 14 - Pre-Construction Plan | 0 |  | 0 | 0%
LCie 15 - Inquiry Issue (RFI) | 4000 | 300 | 3700 | 92.5%
LCie 16 - Product Type Selection | 0 |  | 0 | 0%
LCie 17 - System Layout | 0 |  | 0 | 0%
LCie 18 - Submittal Package | 43200 | 3800 | 39400 | 91.2%
LCie 19 - Submittal Issue | 15900 | 1600 | 14300 | 89.94%
LCie 20 - Purchase Order | 0 |  | 0 | 0%
LCie 21 - Product Installation | 46600 | 18600 | 28000 | 60.09%
LCie 22 - Start-Up | 0 |  | 0 | 0%
LCie 23 - Product Inspection | 20 | 0 | 20 | 100%
LCie 24 - Punchlist Issue | 20 | 0 | 20 | 100%
LCie 25 - Turnover Package | 16500 | 50 | 16450 | 99.7%
Total | 127000 | 24400 | 102700 | 80.87%

## Summary of Savings by Category
Cost Summary - Electronic Doc |  |  |  |  | Cost Summary - COBie
OmniClass Project Phase (Table31) | Current Process | Expected Process | Savings | % Savings | OmniClass Project Phase (Table31) | Current Process | Expected Process | Savings | % Savings
LCie 01 - Facility Criteria | 0 | 0 | 0 | 0% | LCie 01 - Facility Criteria | 0 | 0 | 0 | 0%
LCie 02 - Design Specification | 100 | 0 | 100 | 100% | LCie 02 - Design Specification | 0 | 0 | 0 | 0%
LCie 03 - Feasibility Study | 700 | 20 | 680 | 97.14% | LCie 03 - Feasibility Study | 0 | 0 | 0 | 0%
LCie 04 - Project Definition | 0 | 0 | 0 | 0% | LCie 04 - Project Definition | 0 | 0 | 0 | 0%
LCie 05 - Space Program | 300 | 20 | 280 | 93.33% | LCie 05 - Space Program | 2520 | 230 | 2290 | 90.87%
LCie 06 - Product Program | 300 | 20 | 280 | 93.33% | LCie 06 - Product Program | 1620 | 150 | 1470 | 90.74%
LCie 07 - Request for Proposal | 940 | 130 | 810 | 86.17% | LCie 07 - Request for Proposal | 0 | 0 | 0 | 0%
LCie 08 - Design Early | 5700 | 200 | 5500 | 96.49% | LCie 08 - Design Early | 16800 | 5380 | 11420 | 67.98%
LCie 09 - Design Schematic | 15000 | 210 | 14790 | 98.6% | LCie 09 - Design Schematic | 17100 | 5200 | 11900 | 69.59%
LCie 10 -Design Coordinated | 29400 | 210 | 29190 | 99.29% | LCie 10 -Design Coordinated | 65000 | 9500 | 55500 | 85.38%
LCie 11 - Design Final | 8900 | 30 | 8870 | 99.66% | LCie 11 - Design Final | 21400 | 3580 | 17820 | 83.27%
LCie 12 - Request for Proposal | 2000 | 60 | 1940 | 97% | LCie 12 - Request for Proposal | 0 | 0 | 0 | 0%
LCie 13 - Inquiry Issue | 1200 | 30 | 1170 | 97.5% | LCie 13 - Inquiry Issue | 0 | 0 | 0 | 0%
LCie 14 - Pre-Construction Plan | 0 | 0 | 0 | 0% | LCie 14 - Pre-Construction Plan | 0 | 0 | 0 | 0%
LCie 15 - Inquiry Issue (RFI) | 14000 | 700 | 13300 | 95% | LCie 15 - Inquiry Issue (RFI) | 0 | 0 | 0 | 0%
LCie 16 - Product Type Selection | 0 | 0 | 0 | 0% | LCie 16 - Product Type Selection | 0 | 0 | 0 | 0%
LCie 17 - System Layout | 0 | 0 | 0 | 0% | LCie 17 - System Layout | 0 | 0 | 0 | 0%
LCie 18 - Submittal Package | 57700 | 4200 | 53500 | 92.72% | LCie 18 - Submittal Package | 3000 | 770 | 2230 | 74.33%
LCie 19 - Submittal Issue | 113000 | 30 | 112970 | 99.97% | LCie 19 - Submittal Issue | 4300 | 2100 | 2200 | 51.16%
LCie 20 - Purchase Order | 0 | 0 | 0 | 0% | LCie 20 - Purchase Order | 0 | 0 | 0 | 0%
LCie 21 - Product Installation | 100 | 5 | 95 | 95% | LCie 21 - Product Installation | 46600 | 18600 | 28000 | 60.09%
LCie 22 - Start-Up | 0 | 0 | 0 | 0% | LCie 22 - Start-Up | 0 | 0 | 0 | 0%
LCie 23 - Product Inspection | 100 | 5 | 95 | 95% | LCie 23 - Product Inspection | 29000 | 1160 | 27840 | 96%
LCie 24 - Punchlist Issue | 100 | 10 | 90 | 90% | LCie 24 - Punchlist Issue | 0 | 0 | 0 | 0%
LCie 25 - Turnover Package | 16900 | 190 | 16710 | 98.88% | LCie 25 - Turnover Package | 0 | 0 | 0 | 0%
Total | 266000 | 6100 | 260400 | 97.89% | Total | 207000 | 46700 | 160700 | 77.63%
Breakdown by Role |  |  |  |  | Breakdown by Role
Cost Summary - Owner / Owners Rep |  |  |  |  | Cost Summary - Owner / Owners Rep
OmniClass Project Phase (Table31) | Current Process | Expected Process | Savings | % Savings | OmniClass Project Phase (Table31) | Current Process | Expected Process | Savings | % Savings
LCie 01 - Facility Criteria | 0 | 0 | 0 | 0% | LCie 01 - Facility Criteria | 0 | 0 | 0 | 0%
LCie 02 - Design Specification | 130 | 0 | 130 | 100% | LCie 02 - Design Specification | 0 | 0 | 0 | 0%
LCie 03 - Feasibility Study | 70 | 10 | 60 | 85.71% | LCie 03 - Feasibility Study | 0 | 0 | 0 | 0%
LCie 04 - Project Definition | 0 | 0 | 0 | 0% | LCie 04 - Project Definition | 0 | 0 | 0 | 0%
LCie 05 - Space Program | 60 | 10 | 50 | 83.33% | LCie 05 - Space Program | 60 | 3 | 57 | 95%
LCie 06 - Product Program | 70 | 10 | 60 | 85.71% | LCie 06 - Product Program | 3 | 0.5 | 2.5 | 83.33%
LCie 07 - Request for Proposal | 800 | 60 | 740 | 92.5% | LCie 07 - Request for Proposal | 0 | 0 | 0 | 0%
LCie 08 - Design Early | 900 | 130 | 770 | 85.56% | LCie 08 - Design Early | 6000 | 2990 | 3010 | 50.17%
LCie 09 - Design Schematic | 400 | 40 | 360 | 90% | LCie 09 - Design Schematic | 4000 | 1990 | 2010 | 50.25%
LCie 10 -Design Coordinated | 400 | 40 | 360 | 90% | LCie 10 -Design Coordinated | 4000 | 1490 | 2510 | 62.75%
LCie 11 - Design Final | 5 | 5 | 0 | 0% | LCie 11 - Design Final | 0 | 0 | 0 | 0%
LCie 12 - Request for Proposal | 2000 | 60 | 1940 | 97% | LCie 12 - Request for Proposal | 0 | 0 | 0 | 0%
LCie 13 - Inquiry Issue | 150 | 5 | 145 | 96.67% | LCie 13 - Inquiry Issue | 0 | 0 | 0 | 0%
LCie 14 - Pre-Construction Plan | 0 | 0 | 0 | 0% | LCie 14 - Pre-Construction Plan | 0 | 0 | 0 | 0%
LCie 15 - Inquiry Issue (RFI) | 4400 | 40 | 4360 | 99.09% | LCie 15 - Inquiry Issue (RFI) | 0 | 0 | 0 | 0%
LCie 16 - Product Type Selection | 0 | 0 | 0 | 0% | LCie 16 - Product Type Selection | 0 | 0 | 0 | 0%
LCie 17 - System Layout | 0 | 0 | 0 | 0% | LCie 17 - System Layout | 0 | 0 | 0 | 0%
LCie 18 - Submittal Package | 11400 | 1150 | 10250 | 89.91% | LCie 18 - Submittal Package | 0 | 0 | 0 | 0%
LCie 19 - Submittal Issue | 0 | 0 | 0 | 0% | LCie 19 - Submittal Issue | 0 | 0 | 0 | 0%
LCie 20 - Purchase Order | 0 | 0 | 0 | 0% | LCie 20 - Purchase Order | 0 | 0 | 0 | 0%
LCie 21 - Product Installation | 0 | 0 | 0 | 0% | LCie 21 - Product Installation | 0 | 0 | 0 | 0%
LCie 22 - Start-Up | 0 | 0 | 0 | 0% | LCie 22 - Start-Up | 0 | 0 | 0 | 0%
LCie 23 - Product Inspection | 0 | 0 | 0 | 0% | LCie 23 - Product Inspection | 0 | 0 | 0 | 0%
LCie 24 - Punchlist Issue | 0 | 0 | 0 | 0% | LCie 24 - Punchlist Issue | 0 | 0 | 0 | 0%
LCie 25 - Turnover Package | 400 | 150 | 250 | 62.5% | LCie 25 - Turnover Package | 0 | 0 | 0 | 0%
Total | 21000 | 1700 | 19500 | 92.86% | Total | 14000 | 6500 | 7600 | 54.29%
Cost Summary - Architect |  |  |  |  | Cost Summary - Architect
OmniClass Project Phase (Table31) | Current Process | Expected Process | Savings | % Savings | OmniClass Project Phase (Table31) | Current Process | Expected Process | Savings | % Savings
LCie 01 - Facility Criteria | 0 | 0 | 0 | 0% | LCie 01 - Facility Criteria | 0 | 0 | 0 | 0%
LCie 02 - Design Specification | 0 | 0 | 0 | 0% | LCie 02 - Design Specification | 0 | 0 | 0 | 0%
LCie 03 - Feasibility Study | 590 | 10 | 580 | 98.31% | LCie 03 - Feasibility Study | 0 | 0 | 0 | 0%
LCie 04 - Project Definition | 0 | 0 | 0 | 0% | LCie 04 - Project Definition | 0 | 0 | 0 | 0%
LCie 05 - Space Program | 260 | 10 | 250 | 96.15% | LCie 05 - Space Program | 2460 | 220 | 2240 | 91.06%
LCie 06 - Product Program | 210 | 10 | 200 | 95.24% | LCie 06 - Product Program | 1610 | 150 | 1460 | 90.68%
LCie 07 - Request for Proposal | 170 | 70 | 100 | 58.82% | LCie 07 - Request for Proposal | 0 | 0 | 0 | 0%
LCie 08 - Design Early | 4900 | 60 | 4840 | 98.78% | LCie 08 - Design Early | 10800 | 2390 | 8410 | 77.87%
LCie 09 - Design Schematic | 14600 | 170 | 14430 | 98.84% | LCie 09 - Design Schematic | 13100 | 3260 | 9840 | 75.11%
LCie 10 -Design Coordinated | 29000 | 170 | 28830 | 99.41% | LCie 10 -Design Coordinated | 61000 | 8100 | 52900 | 86.72%
LCie 11 - Design Final | 8900 | 30 | 8870 | 99.66% | LCie 11 - Design Final | 21400 | 3580 | 17820 | 83.27%
LCie 12 - Request for Proposal | 0 | 0 | 0 | 0% | LCie 12 - Request for Proposal | 0 | 0 | 0 | 0%
LCie 13 - Inquiry Issue | 240 | 10 | 230 | 95.83% | LCie 13 - Inquiry Issue | 0 | 0 | 0 | 0%
LCie 14 - Pre-Construction Plan | 0 | 0 | 0 | 0% | LCie 14 - Pre-Construction Plan | 0 | 0 | 0 | 0%
LCie 15 - Inquiry Issue (RFI) | 240 | 10 | 230 | 95.83% | LCie 15 - Inquiry Issue (RFI) | 0 | 0 | 0 | 0%
LCie 16 - Product Type Selection | 0 | 0 | 0 | 0% | LCie 16 - Product Type Selection | 0 | 0 | 0 | 0%
LCie 17 - System Layout | 0 | 0 | 0 | 0% | LCie 17 - System Layout | 0 | 0 | 0 | 0%
LCie 18 - Submittal Package | 6000 | 0 | 6000 | 100% | LCie 18 - Submittal Package | 0 | 0 | 0 | 0%
LCie 19 - Submittal Issue | 112900 | 30 | 112870 | 99.97% | LCie 19 - Submittal Issue | 4300 | 2100 | 2200 | 51.16%
LCie 20 - Purchase Order | 0 | 0 | 0 | 0% | LCie 20 - Purchase Order | 0 | 0 | 0 | 0%
LCie 21 - Product Installation | 40 | 0 | 40 | 100% | LCie 21 - Product Installation | 0 | 0 | 0 | 0%
LCie 22 - Start-Up | 0 | 0 | 0 | 0% | LCie 22 - Start-Up | 0 | 0 | 0 | 0%
LCie 23 - Product Inspection | 80 | 5 | 75 | 93.75% | LCie 23 - Product Inspection | 0 | 0 | 0 | 0%
LCie 24 - Punchlist Issue | 90 | 10 | 80 | 88.89% | LCie 24 - Punchlist Issue | 0 | 0 | 0 | 0%
LCie 25 - Turnover Package | 0 | 0 | 0 | 0% | LCie 25 - Turnover Package | 0 | 0 | 0 | 0%
Total | 178000 | 600 | 177600 | 99.78% | Total | 115000 | 19800 | 94900 | 82.52%
Cost Summary - Contractor |  |  |  |  | Cost Summary - Contractor
OmniClass Project Phase (Table31) | Current Process | Expected Process | Savings | % Savings | OmniClass Project Phase (Table31) | Current Process | Expected Process | Savings | % Savings
LCie 01 - Facility Criteria | 0 | 0 | 0 | 0% | LCie 01 - Facility Criteria | 0 | 0 | 0 | 0%
LCie 02 - Design Specification | 0 | 0 | 0 | 0% | LCie 02 - Design Specification | 0 | 0 | 0 | 0%
LCie 03 - Feasibility Study | 0 | 0 | 0 | 0% | LCie 03 - Feasibility Study | 0 | 0 | 0 | 0%
LCie 04 - Project Definition | 0 | 0 | 0 | 0% | LCie 04 - Project Definition | 0 | 0 | 0 | 0%
LCie 05 - Space Program | 0 | 0 | 0 | 0% | LCie 05 - Space Program | 0 | 0 | 0 | 0%
LCie 06 - Product Program | 0 | 0 | 0 | 0% | LCie 06 - Product Program | 0 | 0 | 0 | 0%
LCie 07 - Request for Proposal | 0 | 0 | 0 | 0% | LCie 07 - Request for Proposal | 0 | 0 | 0 | 0%
LCie 08 - Design Early | 0 | 0 | 0 | 0% | LCie 08 - Design Early | 0 | 0 | 0 | 0%
LCie 09 - Design Schematic | 0 | 0 | 0 | 0% | LCie 09 - Design Schematic | 0 | 0 | 0 | 0%
LCie 10 -Design Coordinated | 0 | 0 | 0 | 0% | LCie 10 -Design Coordinated | 0 | 0 | 0 | 0%
LCie 11 - Design Final | 0 | 0 | 0 | 0% | LCie 11 - Design Final | 0 | 0 | 0 | 0%
LCie 12 - Request for Proposal | 0 | 0 | 0 | 0% | LCie 12 - Request for Proposal | 0 | 0 | 0 | 0%
LCie 13 - Inquiry Issue | 820 | 10 | 810 | 98.78% | LCie 13 - Inquiry Issue | 0 | 0 | 0 | 0%
LCie 14 - Pre-Construction Plan | 0 | 0 | 0 | 0% | LCie 14 - Pre-Construction Plan | 0 | 0 | 0 | 0%
LCie 15 - Inquiry Issue (RFI) | 4000 | 300 | 3700 | 92.5% | LCie 15 - Inquiry Issue (RFI) | 0 | 0 | 0 | 0%
LCie 16 - Product Type Selection | 0 | 0 | 0 | 0% | LCie 16 - Product Type Selection | 0 | 0 | 0 | 0%
LCie 17 - System Layout | 0 | 0 | 0 | 0% | LCie 17 - System Layout | 0 | 0 | 0 | 0%
LCie 18 - Submittal Package | 40200 | 3000 | 37200 | 92.54% | LCie 18 - Submittal Package | 3000 | 770 | 2230 | 74.33%
LCie 19 - Submittal Issue | 70 | 0 | 70 | 100% | LCie 19 - Submittal Issue | 0 | 0 | 0 | 0%
LCie 20 - Purchase Order | 0 | 0 | 0 | 0% | LCie 20 - Purchase Order | 0 | 0 | 0 | 0%
LCie 21 - Product Installation | 60 | 5 | 55 | 91.67% | LCie 21 - Product Installation | 46600 | 18590 | 28010 | 60.11%
LCie 22 - Start-Up | 0 | 0 | 0 | 0% | LCie 22 - Start-Up | 0 | 0 | 0 | 0%
LCie 23 - Product Inspection | 20 | 0 | 20 | 100% | LCie 23 - Product Inspection | 29000 | 1160 | 27840 | 96%
LCie 24 - Punchlist Issue | 20 | 0 | 20 | 100% | LCie 24 - Punchlist Issue | 0 | 0 | 0 | 0%
LCie 25 - Turnover Package | 16500 | 50 | 16450 | 99.7% | LCie 25 - Turnover Package | 0 | 0 | 0 | 0%
Total | 62000 | 3400 | 58300 | 94.03% | Total | 79000 | 20500 | 58100 | 73.54%

## Current Assumptions
Inputs
| Value | Unit | Definitions | Process
Owner Project / Program Variables
Avg. Number of Pages in Facility Criteria | 14 | pages | Estimated number of pages in Owners initial analysis of Project need and Scope. | 10
Avg. Number of Pages in Discipline Specification | 400 | pages | Estimated number of pages in Equipment performance requirements during planning | 20
Avg. Number of Pages in Project Definition | 14 | pages | Estimated number of pages in Project Definition document. The Project Definition defines the project scope, budget requirements, site details, economic analysis and facility planning data | 40,70,80
Avg. Number of Pages in Front Matter | 50 | pages | Estimated number of pages that precede the technical content of the RFP for Design Services and Construction Services. | 70, 120
Project Variables
Avg. Number of Equipment (product) Types (Types / project) | 155 | types / project | Number of different equipment types that will be installed. | 60,80,90,100,110,180,190
Avg. Count Tagged Components (components / project) | 3950 | components / project | Total number of pieces of equipment that will have asset tags and will be managed by the owner | 230,240
Avg. Number of Space Types per Building | 159 | space types / building | Average number of space types found in building. | 50,80
Avg. Time to Log (hours / transmittal) | 0.25 | hours / transmittal | Average Time spent logging documents In and Out | 30,50,60,70,80,90,100,110,120,130,150,180,190,230,240,250
Avg. Number of Options | 3 | count | Average number of options created per project | 30
Avg. Pre-Design Submittal Sets Reqd. (sets / submittal) | 4 | sets / submittal | Average number of pre-design drawing sets required for each submittal. | 30,50,60,70
Avg. Number of Sheets per Option | 6 | pages | Average number of drawings per option. | 30
Avg. Number of Letter-Sized Pages in Design Narrative per Option | 10 | pages | Average number of pages in narrative for each option. | 30
Avg. Number of Pages in Space Program | 65 | pages | Typical number of pages in Space Program. | 50,70,80
Avg. Number of Pages in Product Program | 33 | pages | Typical number of pages in Product Program that documents Owners equipment specifications and performance | 60,70,80
Design Variables
Number of Design Submittal Sets Reqd. (sets / submittal) | 6 | sets / submittal | Number of Design Phase drawing sets required | 80,90,100,110
Avg. Number of Sheets in Design Early Drawings | 48 | drawings | Average number of Design Early or (Schematic Design) drawings for other disciplines | 80
Avg. Number of Letter-Sized Pages in Design Early Narrative | 60 | pages | Average number of Letter-Sized Pages | 80
Avg. Number of Sheets in Design Schematic Drawings | 167 | drawings | Average number of Design Schematic (Design Development) drawings | 90
Avg. Number of Letter Sized Pages in Design Schematic Narrative | 60 | pages | Average number of pages in Design Schematic narrative | 90
Avg. Number of Letter Sized Pages in a Design Schematic Specification | 10 | pages | Average number of pages in Design Schematic (Design Development) specifications. | 90
Avg. Number of Sheets in Design Coordinated Drawings | 218 | drawings | Average number of Design Coordinated drawings | 100
Avg. Number of Letter Sized Pages in a Design Coordinated Narrative | 60 | pages | Average number of pages in Design Coordinated narrative. | 100
Avg. Number of Letter Sized Pages in a Design Coordinated Specification | 2156 | pages | Average number of pages in Design Coordinated specifications. | 100
Avg. Number of Sheets in Design Final Drawings | 316 | drawings | Average number of Design Final drawings. | 110,120
Avg. Number of Letter Sized 'Pages in Design Final Narrative | 60 | pages | Average number of pages in Design Final narrative. | 110,120
Avg. Number of Letter Sized Pages in Design Final Specification | 2156 | pages | Average number of pages in Design Final specifications. | 110,120
Estimating Process Variables
Avg QTO Time for Equipment Components (hours / plan drawing) | 0.083333 | hours / plan drawing | Average time spent to take off all equipment pieces installed or specified in project. | 90,100,110
Avg QTO Time for Spaces in building (hours / plan drawing) | 0.16667 | hours / plan drawing | Average time spent to calculate areas. | 90,100,110
Submittal Process Variables
Number of Submittal Sets Reqd. (sets / submittal) | 6 | sets / submittal | Number of construction phase submittal sets required | 180,190
Avg. Number of Submittal Items in a Submittal Package for each Equipment (product) Type (submittal items/submittal package) | 3 | submittal items / submittal package | Average number of product Items per submittal package | 180,190
Avg. Number of Submittal Pages in a Submittal Item (pages/submittal item) | 18 | pages/submittal item | Average number of letter-sized pages per submittal item | 180,190
Avg. Number of Submittal Sheets in a Submittal Item (sheets/submittal item) | 1 | sheets/submittal item | Average number of drawings per submittal item | 180,190
Organizational Variables
Owner Administrative Rate ($ / hour) | 23.71 | $ / hour | Rate for activities that cover Handling of documents | 10,20,30,40,250
Owners Rep. Rate ($ / hour) | 62.2 | $ / hour | Rate for activities that include Validating of documents | 50,60,80,90,100
Owners Rep. Administrative Rate ($ / hour) | 16.88 | $ / hour | Rate for activities that cover Handling of documents | 50,60,70,80,90,100,110,120,130,150,180
Planner Rate ($ / hour) | 37.84 | $ / hour | Rate for professional assisting owner in Pre-design activities. | 50,60
Planner Administrative Rate ($ / hour) | 16.82 | $ / hour | Rate for activities that cover Handling of documents | 30,50,60
Licensed Professional Architect Rate ($ / hour) | 109.989 | $ / hour | Rate including Professional Services, Overhead and Profit | 80,90,100,110,190,230,240
Specifier | 109.99 | $ / hour
Architect Drafter Rate ($ / hour) | 70.7033 | $ / hour | Rate including Professional Services, Overhead and Profit | 80,90,100,110,190,230,240
Architect Administrative Rate ($ / hour) | 45.9558 | $ / hour | Rate for activities that cover Handling of documents | 70,80,90,100,110,130,150,180,190,210, 230,240
Construction Project Manager Rate ($ / hour) | 125.8125 | $ / hour | Rate including Professional Services, Overhead and Profit | 180190200210250
Assistant (Construction) Project Manager Rate ($ / hour) | 70.526 | $ / hour | Rate including Professional Services, Overhead and Profit | 180190250
Contractor Administrative Rate ($ / hour) | 44.188 | $ / hour | Rate for activities that cover Handling of documents | 130,150,180,190,230,240,250
General Repro/Postal Delivery Cost
Avg. Per Page Copy Cost ($ / page) | 0.15 | $ / sheet | - | 10,20,30,40,50,60,70,80,90,100,110,120,180,250
Avg. Per Sheet Copy Cost ($ / sheet) | 3 | $ / sheet | - | 30,70,80,90,100,110,120,180,250
Project Phase Variables
Facility Criteria
Avg. Number of Sets Required (sets / submittal) | 2 | sets / submittal | Average number of sets required
Avg. In-house Reproduction Time Per Set (hours/set) | 0.009 | hours/set | Average time spent in printing and making copies of Facility Criteria by Owner
Discipline Specification
Avg. Number of Sets Required (sets / submittal) | 2 | sets | Average number of sets required
Avg. In-house Reproduction Time Per Set (hours/set) | 0.27 | hours/set | Average time spent in printing and making copies of Discipline Specification by Owner
Feasibility Study
Avg. Number of Transmittals | 2 | Transmittals | Average number of times options / comments are exchanged between the Planner and Owner times the number of recipients for each exchange
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 0.02 | hours / submittal set | Average time spent in printing and making copies of feasibility study by Planner
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 21.6 | $ / Transmittal | Average cost for delivering documents/comments sent between Planner and Owner
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.16667 | hours / transmittal | Average time spent in compiling documents for transmittal
Project Definition
Avg. Number of Sets Required (sets / submittal) | 2 | sets | Average number of sets required
Avg. In-house Reproduction Time Per Set (hours/set) | 0.009 | hours/set | Average time spent in printing and making copies of Project Definition by Owner
Space Program
Avg. Time Spent Recreating Space Program Criteria (hours/space) | 0.25 | hours / space | Average time spent by Planner recreating Space Program Criteria
Avg. Time Spent Reformatting Room Data Sheet (hours/space) | 0.08333 | hours | Average time spent in evaluating information in Project Definition and identifying and creating a detailed spatial program
Avg. Time to Compare Space Program with Owner Standards (hours) | 1 | hours | Average time spent by Owners Rep in validating Space Program provided by planner
Avg. Percentage of errors in Space Program | 30% | % | Average percentage of errors found by Owners Rep in Space Program
Avg. Time Spent Recreating Space Program (hours/space) | 0.25 | hours / space | Average time spent by Planner recreating Space Program
Avg. Number of Transmittals | 2 | Transmittals | Average number of times Space Program / Comments are sent between the Planner and Owners Rep times the number of recipients for each exchange.
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 16.5 | $ / Transmittal | Average cost for delivering documents/comments sent between Planner and Owners Rep
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.16667 | hours / transmittal | Average time spent in compiling documents for transmittal
Product Program
Avg. Time Spent Recreating Product Program Criteria (hours / product) | 0.25 | hours / product | Average time spent by Planner recreating Product Program Criteria
Avg Time to Compare Product Program with Owner Standards (hours) | 0.05 | hour | Average time spent by Owners Rep in validating Product Program provided by Planner
Avg. Percentage of errors in Product Program | 30% | % | Average percentage of errors found by Owners Rep in Product Program
Avg. Time Spent Recreating Product Program (hours/space) | 0.083333 | hours / space | Average time spent by Planner recreating Product Program
Avg. Number of Transmittals | 2 | Transmittals | Average number of times Product Program / Comments are sent between the Planner and Owners Rep times the number of recipients for each exchange.
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 23.95 | $ / Transmittal | Average cost for mailing documents/comments sent between Planner and Owners Rep.
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.16667 | hours / transmittal | Average time spent in compiling documents for transmittal.
Request for Proposal
Avg. Number of Letter Sized Pages in RFP (pages / proposal) | 50 | pages / proposal | Average number of Letter-Sized Pages
Avg. Number of Drawing Sheets in Proposal (sheets / proposal) | 2 | sheets / proposal | Average number of Drawings
Number of RFP copies Reqd. (sets / submittal) | 5 | sets / submittal | Number of RFP copies required
Avg. Number of Transmittals - Owners Rep documents to Bidders | 5 | Transmittals | Average number of times Proposal is sent from the Owners Rep to the Bidders times the number of recipients for each exchange.
Avg. Number of Transmittals - Architect to Owner | 1 | Transmittals | Average number of times Proposal is sent from the Architect to the Owners Rep times the number of recipients for each exchange.
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 0.04 | hours / submittal set | Average time spent in printing and making copies of Proposal by Architect
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Owners Rep documents to Bidders | 18.8 | $ / Transmittal | Average cost for mailing documents/comments sent between Owners Rep and Architect
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Architect to Owners Rep | 18.8 | $ / Transmittal | Average cost for mailing proposal between Architect and Owners Rep.
Avg. Time to Prepare Transmittal (hours / transmittal) - Owners Rep | 0.75 | hours / transmittal | Average time spent in compiling documents for transmittal / submission
Avg. Time to Prepare Transmittal (hours / transmittal) - Architect | 1 | hours / transmittal | Average time spent in compiling documents for transmittal / submission
Design Early
Avg. Time Spent Reformatting Space Program Requirements(hours / space type) | 0.16666 | hours / space type | Average time spent by Architect in reformatting spatial requirements
Avg. Time Spent Reformatting Equipment Type (hours /product) | 0.25 | hours / product | Average Time spent by Architect reformatting equipment types
Avg. Time Spent Evaluating Design Early Drawings against Design Requirements - Space and Equipment | 12 | hours | Average time spent by Architect in validating Design Early drawings before submission to Owners Rep
Avg Time to Compare Design Early Documents with Owner Standards | 24 | hours | Average time spent by Owners Rep in validating Design Early documents
Avg. Time spent making corrections due to non-conformance with Space or Product Program | 7.8497 | hours | Average time spent by Architect making corrections based on feedback from Owners Rep.
Avg. Number of Review Cycles | 3 | Cycles | Average number of times submitted docmentation is examined.
Percentage of Time Spent by Licensed Professional Architect | 90% | % | Percentage of time spent by Licensed Architect reformatting Space Program, Equipment Type and Project Definition
Percentage of Time Spent by Architect Drafter | 10% | % | Percentage of time spent by Architect Drafter reformatting Space Program, Equipment Type and Project Definition
Avg. Number of Transmittals | 3 | Transmittals | Average number of times drawings, narratives and comments are sent and received between the Architect / Planner and Owner times the number of recipients for each exchange
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 0.173 | hours / submittal set | Average time spent in printing and making copies of drawings and narratives by Architect / Planner
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Owners Rep to Architect | 16.5 | $ / Transmittal | Average cost for mailing documents/comments sent between Owners Rep and Architect
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Architect to Owners Rep | 27.1 | $ / Transmittal | Average cost for mailing documents/comments between Architect and Owners Rep.
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.5 | hours / transmittal | Average time spent compiling copies of drawings, narratives and comments for transmittal by Architect and Owners Rep.
Design Schematic
Avg. Number of Plan Drawings in Design Schematic Drawings | 18.4 | plans / drawing set | Average number of Plan Drawings
Avg. Time Spent Developing Equipment (product) Type Template (hours / product type) | 0.25 | hours / product type | Time spent by Architect in developing specifications for equipment types required for the project
Avg. Time Spent Evaluating Design Schematic Drawings against Design Requirements - Space and Equipment | 41 | hours | Average time spent by Architect in validating Design Schematic drawings before submission to Owners Rep
Avg Time to Compare Design Schematic Documents with Owner Standards | 16 | hours | Average time spent by Owners Rep in validating Design Schematic documents
Avg. Time spent making corrections due to non-conformance with Space or Product Program | 11.7745 | hours | Average time spent by Architect making corrections based on feedback from Owners Rep.
Avg. Number of Review Cycles | 3 | Cycles | Average number of times submitted docmentation is examined.
Percentage of Time Spent by Licensed Professional Architect | 80% | % | Percentage of time spent by Licensed Architect to take off all equipment pieces and to calculate areas
Percentage of Time Spent by Architect Drafter | 20% | % | Percentage of time spent by Architect Drafter to take off all equipment pieces and to calculate areas
Avg. Number of Transmittals | 3 | Transmittals | Average number of times schematic drawings, narratives, specifications and comments are sent and received between the Architect / Planner and Owner times the number of recipients for each exchange
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 0.504 | hours/submittal set | Average time spent in printing and making copies of drawings, narratives and specifications by Architect / Planner
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Owners Rep to Architect | 16.5 | $ / Transmittal | Average cost for mailing documents/comments sent between Owners Rep and Architect
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Architect to Owners Rep | 47.7 | $ / Transmittal | Average cost for mailing documents/comments between Architect and Owners Rep.
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.5 | hours / transmittal | Average time spent compiling copies of schematic drawings, narratives, specifications and comments for transmittal by Architect and Owners Rep.
Design Coordinated
Avg. Number of Plan Drawings in Design Coordinate Drawings | 36.8 | plans / drawing set | Average number of Plan Drawings
Avg. Time Spent Developing Detailed Equipment (products) Type Template (hours / product) | 2 | hours / product | Time spent by Architect in preparing a detailed specifications list based on equipment types
Avg. Time Searching for Product Literature for Candidates (Hours/product) | 1 | hours / product | Average Time spent by Architect in searching for product data
Avg. Time Spent Evaluating Design Coordinated Drawings against Design Requirements - Space and Equipment | 38 | hours | Average time spent by Architect in validating Design Coordinated drawings before submission to Owners Rep
Avg. Percent of Errors in Product Type Candidate | 15% | % | Percentage of errors in Product Type List
Avg Time to Compare Design Coordinated & Product Type Candidate Documents with Owner Standards | 16 | hours | Average time spent by Owners Rep in validating Design Coordinated documents
Avg. Time Spent making Corrections due to Non-Conformance with Space or Product Program | 6.5414 | hours | Average time spent by Architect making corrections based on feedback from Owners Rep.
Avg. Number of Review Cycles | 3 | Cycles | Average number of times submitted docmentation is examined.
Percentage of Time Spent by Licensed Professional Architect | 80% | % | Percentage of time spent by Licensed Architect to take off all equipment pieces and to calculate areas
Percentage of Time Spent by Architect Drafter | 20% | % | Percentage of time spent by Architect Drafter to take off all equipment pieces and to calculate areas
Avg. Number of Transmittals | 3 | Transmittals | Average number of times coordinated drawings, narratives, specifications and comments are sent and received between the Architect and Owners Rep times the number of recipients for each exchange
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 2 | hours / submittal set | Average time spent in printing and making copies of drawings, narratives and specifications by Architect
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Owners Rep to Architect | 16.5 | $ / Transmittal | Average cost for mailing documents/comments sent between Owners Rep and Architect
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Architect to Owners Rep | 87.3 | $ / Transmittal | Average cost for mailing documents between Architect and Owners Rep.
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.5 | hours / transmittal | Average time spent compiling copies of coordinated drawings, narratives, specifications and comments for transmittal by Architect and Owners Rep
Design Final
Avg. Number of Plan Drawings in Design Final Drawings | 115 | plans / drawing set | Average number of Plan Drawings
Avg. Time Spent Developing Detailed Equipment (products) Type Candidate (hours / product) | 1 | hours / product | Time spent by Architect in preparing a detailed specifications list based on equipment types
Avg. Time Spent Evaluating Design Final Drawings against Design Requirements - Space and Equipment | 12 | hours | Average time spent by Architect in validating Design Final drawings before submission to Owners Rep
Percentage of Time Spent by Licensed Professional Architect | 90% | % | Percentage of time spent by Licensed Architect to take off all equipment pieces and to calculate areas
Percentage of Time Spent by Architect Drafter | 10% | % | Percentage of time spent by Architect Drafter to take off all equipment pieces and to calculate areas
Avg. Number of Transmittals | 1 | Transmittals | Average number of times final drawings, narratives, specifications and comments are sent and received between the Architect and Owners Rep times the number of recipients for each exchange.
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 2.3 | hours / submittal set | Average time spent in printing and making copies of drawings, narratives and specifications by Architect / Planner
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Owners Rep to Architect | 16.5 | $ / Transmittal | Average cost for mailing documents/comments sent between Owners Rep and Architect
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Architect to Owners Rep | 118 | $ / Transmittal | Average cost for mailing proposal between Architect and Owners Rep.
Avg. Time to Prepare Transmittal (hours / transmittal) | 1 | hours / transmittal | Average time spent compiling copies of final drawings, narratives, specifications for transmittal by Architect
Request for Proposal
Avg. Number of Transmittals | 5 | Transmittals | Average number of times RFP Package is sent from Owners Rep to Contractor times the number of recipients for purpose of bidding.
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 2.36 | hours / submittal set | Average time spent in printing and making copies of RFP Package by Owners Rep.
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 119.7 | $ / Transmittal | Average cost for mailing RFP by Owners Rep.
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.75 | hours / transmittal | Time spent compiling documents, drawings or specifications for transmittal by Owners Rep.
Avg. Number of Request for Proposal Submittal Sets Reqd. | 1 | submittal sets | Average number of RFP sets required for submission
Inquiry Issue
Avg. Number of Transmittals | 3 | Transmittals | Average number of times Inquiry Issues and responses are sent and received between Owners Rep, Architect and Contractor times the number of recipients for each exchange
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 16.5 | $ / Transmittal | Average cost for mailing documents/comments sent between Owners Rep, Architect, and Contractor
Avg. Time to Prepare Transmittals for Inquiry Issues (hours / transmittal) - Contractor / Architect | 0.16667 | hours / transmittal | Time spent compiling documents, drawings or specifications for transmittal by Architect and Contractor
Avg. Time to Prepare Transmittals for Inquiry Issues (hours / transmittal) - Owners Rep | 0.083 | hours / transmittal | Time spent compiling documents, drawings or specifications for transmittal by Owners Rep.
Pre-Construction Plan
Inquiry Issue (RFI)
Avg. Number of RFIs | 87 | Transmittals | Average number of times Inquiry Issues (RFI) and responses are sent and received between Owners Rep, Architect and Contractor times the number of recipients for each exchange
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 16.5 | $ / Transmittal | Average cost for mailing documents/comments sent between Owners Rep, Architect, and Contractor
Avg. Time to Prepare Transmittals for Inquiry Issues (RFI) (hours / transmittal) - Contractor / Architect | 0.16667 | hours / transmittal | Average Time spent compiling Inquiry Issues (RFI) for transmittal by Architect and Contractor
Avg. Time to Prepare Transmittals for Inquiry Issues (RFI) (hours / transmittal) - Owner | 0.033333 | hours / transmittal | Average Time spent compiling Inquiry Issues (RFI) for transmittal by Owners Rep
Product Type Selection
Time Spent Validating Equipment (products) Type against Template (hours / product) | 0.5 | hours / product | Time spent by Contractor in comparing equipment specifications against submittal information
System Layout
Submittal Package
Average Time Spent Organizing Equipment (product) Type information (hours / submittal item) | 0.16667 | hours / submittal item | Average Time spent by asst. project manager in producing submittal information by organizing equipment type information
Average Time Spent Evaluating Equipment (product) Type Submittal Items against Contract Documents (hours / submittal item) | 0.5 | hours / submittal item | Average Time spent evaluating submittal items
Avg. Time to Sign each Page (hours / page) | 0.083333 | hours/page | Average time required by Contractor to sign pages of Submittal Package
Avg. Time to Stamp each Sheet (hours / sheet) | 0.083333 | hours/sheet | Average time required by Contractor to stamp sheets of Submittal Package
Percentage of Submittals Items rejected | 20% | % | Percentage of items rejected
Percentage of Time Spent by Construction Project Manager | 10% | % | Percentage of time spent by Construction Project Manager in validating Submittal Information
Percentage of Time Spent by Assistant (Construction) Project Manager | 90% | % | Percentage of time spent by Assistant Construction Project Manager in validating Submittal Information
Avg. Number of Transmittals | 342 | Transmittals | Average number of times Submittal Packages are sent and received between Owners Rep, Architect and Contractor times the number of recipients for each exchange
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 0.015 | hours / submittal set | Average time spent in printing and making copies of Submittal Package by Contractor
Average Mailing Costs per Transmittal ($) | 16.5 | $ / Transmittal | Average cost for Mailing documents/transmittals sent between Owners Rep and Contractor
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.5 | hours / transmittal | Average time spent compiling Submittal Package for transmittal by Architect / Contractor
Submittal Issue
Avg. Time Spent Evaluating Product Type Submittal Items against Contract Documents (hours / product type submittal item) | 1 | hours / submittal item | Average Time spent by Architect in evaluating submittal package of equipment types
Avg. Time Spent Revising one Product Submittal Item (hours / product) | 0.5 | hours / product | Average Time spent by Contractor recreating Submittal Items
Percentage of Product Submittals reviewed by Licensed Architect | 25% | % | Percentage of submittals reviewed by Architect
Percentage of Product Submittals rejected on first review | 42.5% | % | Percentage of submittals rejected upon review
Percentage of Product Submittals rejected on second review | 25% | % | Percentage of submittals rejected upon review
Percentage of Product Submittals rejected on third review | 8% | % | Percentage of submittals rejected upon review
Avg. Time Spent Transferring Comments per Page | 0.033333 | hours / page | Time spent by Architect in marking up submittal with comments
Avg. Time Spent Transferring Comments per Sheet | 0.083333 | hours / sheet | Time spent by Architect in marking up submittal with comments
Percentage of Time Spent by Construction Project Manager | 80% | % | Percentage of time spent by Construction Project Manager in recreating Submittal Package
Percentage of Time Spent by Assistant (Construction) Project Manager | 20% | % | Percentage of time spent by Assistant Construction Project Manager in recreating Submittal Package
Avg. Number of Transmittals | 6 | Transmittals | Average number of times Submittal Packages (pages and sheets) are sent and received between Architect and Contractor times the number of recipients for each exchange
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.083333 | hours / transmittal | Average time spent compiling Submittal Package for transmittal by Architect
Avg. Mailing Cost per Transmittal | 16.5 | $ / Transmittal | Average cost for Mailing documents/transmittals between Architect / Planner and Contractor
Purchase Order
Product Installation
Avg. Time Spent Recording Components Data | 0.16667 | hours / component | Average time spent by Contractor recording data for installed components
Avg Number of Months of Construction (months) | 12 | months | Average duration of project
Total Time Spent in Office (hours / day) | 8 | hours / day | Total time spent in the office on a daily basis
Avg. Percentage of Office Time Spent formatting Product Installation Report | 25% | % | Average percentage of time spent by Contractor in the office formatting report
Avg. Number of Transmittals (Transmittals) | 2 | Transmittals | Average number of times Product Installation Reports are sent and received between Contractor and Architect / Owner times the number of recipients for each exchange
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 16.5 | $ / Transmittal | Average cost for mailing Product Installlation Report by Contractor
Avg. Time to Prepare a Transmittal (hours/transmittal) | 0.083333 | hours / transmittal | Average time spent compiling Product Installation for transmittal by Assistant Construction Manager
Start-Up
Product Inspection
Avg. Time Spent Documenting Report per Site Visit (hours / visit) | 2.75 | hours / visit | Average time spent in the field documenting data during site visits.
Avg. Number of Site Visits per month | 4 | visits / month | Average number of times site is visited in a month
Avg Number of Months of Construction | 12 | months | Average construction duration of a project
Total Time Spent in Office | 8 | hours / day | Total time spent in the office on a daily basis
Avg. Percentage of Office Time Spent Quantifying products in place | 25% | % | Average percentage of time spent in the office documenting data recorded from the field.
Avg. Number of Transmittals | 2 | Transmittals | Average number of times Inspection Reports are sent and received between Architect and Contractor times the number of recipients for each exchange
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 16.5 | $ / Transmittal | Average cost for mailing Inspection Reports by Architect
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.083333 | hours / transmittal | Average time spent compiling Inspection Report for transmittal by Architect
Punch list Issue
Avg. Time Spent Documenting Punchlist Report per Site Visit | 0.25 | hours / visit | Average time spent in the office recording information gathered from a walkthrough of completed construction work.
Avg. Number of Site Visits for Punchlist Inspection | 90% | nos of visits | Average number of times site is visited to conduct Punchlist Inspection
Total Time Spent in Office | 100% | hours / day | Total time spent in the office on a daily basis
Avg. Percentage of Office Time Spent Documenting Site Visit | 0% | % | Average percentage of time spent in the office documenting data recorded from the field.
Avg. Number of Transmittals | 2 | Transmittals | Average number of times Punch list Reports are sent and received between Architect and Contractor times the number of recipients for each exchange
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 16.5 | $ / Transmittal | Average cost for mailing Punch list Reports by Architect
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.25 | hours / transmittal | Average time spent compiling Punch list Report for transmittal by Architect
Turnover Package
Avg. Time Spent Searching and Assembling Operations & Maintenance Manuals (hours / document) | 3 | hours / document | Time spent compiling O&M Manual
Avg. Time Spent Searching and Assembling Commissioning Report (hours / document) | 0 | hours / document | Time spent compiling Commissioning Report
Avg. Time Spent Searching and Assembling Record Specifications (hours / document) | 1.5 | hours / document | Time spent compiling Record Specifications
Avg. Time Spent Searching and Assembling Record (As-Built) Drawings (hours / sheet) | 0.0008 | hours / sheet | Time spent compiling Record (As-Built) Drawings
Avg. Time Spent Searching and Assembling Final Approved Shop Drawings (hours / sheet) | 0.0083333 | hours / sheet | Time spent compiling Final Approved Shop Drawings
Avg. Number of Pages in Operations & Maintenance Manuals | 5425 | pages | Number of Pages in Operations & Maintenance Manuals
Avg. Number of Pages in Commissioning Report | 0 | pages | Number of Pages in Commissioning Report
Avg. Number of Pages in Record Specifications | 2156 | pages | Number of Pages in Record Specifications
Avg. Number of Sheets in Record (As-Built) Drawings | 364 | sheets | Number of Sheets in Record (As-Built) Drawings
Avg. Number of Sheets in Final Approved Shop Drawings | 1 | sheets | Number of Sheets in Final Approved Shop Drawings
Avg. Time Spent Reviewing Operations & Maintenance Manuals (hours/page) | 0.0016667 | hours / page | Time Spent Reviewing Operations & Maintenance Manuals
Avg. Time Spent Reviewing Commissioning Report (hours / page) | 0 | hours / page | Time Spent Reviewing Commissioning Report
Avg. Time Spent Reviewing Record Specifications (hours / page) | 0.0016667 | hours / page | Time Spent Reviewing Record Specifications
Avg. Time Spent Reviewing Record (As-Built) Drawings (hours/ sheet) | 0.0083333 | hours / sheet | Time Spent Reviewing Record (As-Built) Drawings
Avg. Time Spent Reviewing Final Approved Shop Drawings (hours / sheet) | 0.0083333 | hours / sheet | Time Spent Reviewing Final Approved Shop Drawings
Avg. Time Spent Filing Operations & Maintenance Manuals (hours/document) | 0.08333 | hours / document | Time Spent Filing Operations & Maintenance Manuals
Avg. Time Spent Filing Commissioning Report (hours/document) | 0 | hours / document | Time Spent Filing Commissioning Report
Avg. Time Spent Filing Record Specifications (hours/document) | 0.08333 | hours / document | Time Spent Filing Record Specifications
Avg. Time Spent Filing Record (As-Built) Drawings (hours / sheet) | 0.0016667 | hours / sheet | Time Spent Filing Record (As-Built) Drawings
Avg. Time Spent Filing Final Approved Shop Drawings(hours / sheet) | 0.0016667 | hours / sheet | Time Spent Filing Final Approved Shop Drawings
Percentage of Time Spent by Construction Project Manager | 10% | % | Percentage of time spent by Construction Project Manager in compiling Turnover Package
Percentage of Time Spent by Assistant (Construction) Project Manager | 90% | % | Percentage of time spent by Assistant Construction Project Manager in compiling Turnover Package
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 9 | hours / submittal set | Average time spent in printing and making copies of Turnover Package by Contractor
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 350.32 | $ / Transmittal | Average cost for mailing Turnover Package by Contractor
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.5 | hours / transmittal | Average time spent compiling Turnover Package for transmittal by Contractor

## Expected Assumptions
NOTE: Red text indicates variables affected by the expected process.
Inputs
| Value | Unit | Redution Factor | Expected Outcome | Definitions | Process
Owner Project / Program Variables
Avg. Number of Pages in Facility Criteria | 14 | pages |  | 14 | Estimated number of pages in Owners initial analysis of Project need and Scope. | 10
Avg. Number of Pages in Discipline Specification | 400 | pages |  | 400 | Estimated number of pages in Equipment performance requirements during planning | 20
Avg. Number of Pages in Project Definition | 14 | pages |  | 14 | Estimated number of pages in Project Definition document. The Project Definition defines the project scope, budget requirements, site details, economic analysis and facility planning data | 40,70,80
Avg. Number of Pages in Front Matter | 50 | pages |  | 50 | Estimated number of pages that precede the technical content of the RFP for Design Services and Construction Services. | 70, 120
Project Variables
Avg. Number of Equipment (product) Types (Types / project) | 155 | types / project |  | 155 | Number of different equipment types that will be installed. | 60,80,90,100,110,180,190
Avg. Count Tagged Components (components / project) | 3950 | components / project |  | 3950 | Total number of pieces of equipment that will have asset tags and will be managed by the owner | 230,240
Avg. Number of Space Types per Building | 159 | space types / building |  | 159 | Average number of space types found in building. | 50,80
Avg. Time to Log (hours / transmittal) | 0.25 | hours / transmittal | 0 | 0 | Average Time spent logging documents In and Out | 30,50,60,70,80,90,100,110,120,130,150,180,190,230,240,250
Pre-Design Variables
Avg. Number of Options | 3 | count |  | 3 | Average number of options created per project | 30
Avg. Pre-Design Submittal Sets Reqd. (sets / submittal) | 4 | sets / submittal | 0 | 0 | Average number of pre-design drawing sets required for each submittal. | 30,50,60,70
Avg. Number of Sheets per Option | 6 | pages |  | 6 | Average number of drawings per option. | 30
Avg. Number of Letter-Sized Pages in Design Narrative per Option | 10 | pages |  | 10 | Average number of pages in narrative for each option. | 30
Avg. Number of Pages in Space Program | 65 | pages |  | 65 | Typical number of pages in Space Program. | 50,70,80
Avg. Number of Pages in Product Program | 33 | pages |  | 33 | Typical number of pages in Product Program that documents Owners equipment specifications and performance | 60,70,80
Design Variables
Number of Design Submittal Sets Reqd. (sets / submittal) | 6 | sets / submittal | 0 | 0 | Number of Design Phase drawing sets required | 80,90,100,110
Avg. Number of Sheets in Design Early Drawings | 48 | drawings |  | 48 | Average number of Design Early or (Schematic Design) drawings for other disciplines | 80
Avg. Number of Letter-Sized Pages in Design Early Narrative | 60 | pages |  | 60 | Average number of Letter-Sized Pages | 80
Avg. Number of Sheets in Design Schematic Drawings | 167 | drawings |  | 167 | Average number of Design Schematic (Design Development) drawings | 90
Avg. Number of Letter Sized Pages in Design Schematic Narrative | 60 | pages |  | 60 | Average number of pages in Design Schematic narrative | 90
Avg. Number of Letter Sized Pages in a Design Schematic Specification | 10 | pages |  | 10 | Average number of pages in Design Schematic (Design Development) specifications. | 90
Avg. Number of Sheets in Design Coordinated Drawings | 218 | drawings |  | 218 | Average number of Design Coordinated drawings | 100
Avg. Number of Letter Sized Pages in a Design Coordinated Narrative | 60 | pages |  | 60 | Average number of pages in Design Coordinated narrative. | 100
Avg. Number of Letter Sized Pages in a Design Coordinated Specification | 2156 | pages |  | 2156 | Average number of pages in Design Coordinated specifications. | 100
Avg. Number of Sheets in Design Final Drawings | 316 | drawings |  | 316 | Average number of Design Final drawings. | 110,120
Avg. Number of Letter Sized 'Pages in Design Final Narrative | 60 | pages |  | 60 | Average number of pages in Design Final narrative. | 110,120
Avg. Number of Letter Sized Pages in Design Final Specification | 2156 | pages |  | 2156 | Average number of pages in Design Final specifications. | 110,120
Estimating Process Variables
Avg QTO Time for Equipment Components (hours / plan drawing) | 0.083333 | hours / plan drawing | 40% | 0.033333 | Average time spent to take off all equipment pieces installed or specified in project. | 90,100,110
Avg QTO Time for Spaces in building (hours / plan drawing) | 0.16667 | hours / plan drawing | 40% | 0.066667 | Average time spent to calculate areas. | 90,100,110
Submittal Process Variables
Number of Submittal Sets Reqd. (sets / submittal) | 6 | sets / submittal | 0 | 0 | Number of construction phase submittal sets required | 180,190, 250
Avg. Number of Submittal Items in a Submittal Package for each Equipment (product) Type (submittal items/submittal package) | 3 | submittal items / submittal package |  | 3 | Average number of product Items per submittal package | 180,190
Avg. Number of Submittal Pages in a Submittal Item (pages/submittal item) | 18 | pages/submittal item |  | 18 | Average number of letter-sized pages per submittal item | 180,190
Avg. Number of Submittal Sheets in a Submittal Item (sheets/submittal item) | 1 | sheets/submittal item |  | 1 | Average number of drawings required | 180,190
Organizational Variables
Owner Administrative Rate ($ / hour) | 23.71 | $ / hour |  | 23.71 | Rate for activities that cover Handling of documents | 10,20,30,40,250
Owners Rep. Rate ($ / hour) | 62.2 | $ / hour |  | 62.2 | Rate for activities that include Validating of documents | 50,60,80,90,100
Owners Rep. Administrative Rate ($ / hour) | 16.88 | $ / hour |  | 16.88 | Rate for activities that cover Handling of documents | 50,60,70,80,90,100,110,120,130,150,180
Planner Rate ($ / hour) | 37.84 | $ / hour |  | 37.84 | Rate for professional assisting owner in Pre-design activities. | 50,60
Planner Administrative Rate ($ / hour) | 16.82 | $ / hour |  | 16.82 | Rate for activities that cover Handling of documents | 30,50,60
Licensed Professional Architect Rate ($ / hour) | 109.989 | $ / hour |  | 109.989 | Rate including Professional Services, Overhead and Profit | 80,90,100,110,190,230,240
Specifier | 109.99 | $ / hour |  | 109.99
Architect Drafter Rate ($ / hour) | 70.7033 | $ / hour |  | 70.7033 | Rate including Professional Services, Overhead and Profit | 70,80,90,100,110,130,150,180,190,230,240
Architect Administrative Rate ($ / hour) | 45.9558 | $ / hour |  | 45.9558 | Rate for activities that cover Handling of documents
Construction Project Manager Rate ($ / hour) | 125.8125 | $ / hour |  | 125.8125 | Rate including Professional Services, Overhead and Profit | 180190200210250
Assistant (Construction) Project Manager Rate ($ / hour) | 70.526 | $ / hour |  | 70.526 | Rate including Professional Services, Overhead and Profit | 180190250
Contractor Administrative Rate ($ / hour) | 44.188 | $ / hour |  | 44.188 | Rate for activities that cover Handling of documents | 130,150,180,190,230,240,250
General Repro/Postal Delivery Cost
Avg. Per Page Copy Cost ($ / page) | 0.15 | $ / sheet | 0 | 0 | - | 10,20,30,40,50,60,70,80,90,100,110,120,180,250
Avg. Per Sheet Copy Cost ($ / sheet) | 3 | $ / sheet | 0 | 0 | - | 30,70,80,90,100,110,120,180,250
Project Phase Variables
Facility Criteria |  |  | Redution Factor | Expected Outcome
Avg. Number of Sets Required (sets / submittal) | 2 | sets / submittal | 0 | 0 | Average number of sets required
Avg. In-house Reproduction Time Per Set (hours/set) | 0.009 | hours/set | 0 | 0 | Average time spent in printing and making copies of Facility Criteria by Owner
Discipline Specification
Avg. Number of Sets Required (sets / submittal) | 2 | sets | 0 | 0 | Average number of sets required
Avg. In-house Reproduction Time Per Set (hours/set) | 0.27 | hours/set | 0 | 0 | Average time spent in printing and making copies of Discipline Specification by Owner
Feasibility Study
Avg. Number of Transmittals | 2 | Transmittals | - | 2 | Average number of times options / comments are exchanged between the Planner and Owner times the number of recipients for each exchange
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 0.02 | hours / submittal set | 0 | 0 | Average time spent in printing and making copies of feasibility study by Planner
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 21.6 | $ / Transmittal | 0 | 0 | Average cost for delivering documents/comments sent between Planner and Owner
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.16667 | hours / transmittal | - | 0.16667 | Average time spent in compiling documents for transmittal
Project Definition
Avg. Number of Sets Required (sets / submittal) | 2 | sets | 0 | 0 | Average number of sets required
Avg. In-house Reproduction Time Per Set (hours/set) | 0.009 | hours/set | 0 | 0 | Average time spent in printing and making copies of Project Definition by Owner
Space Program
Avg. Time Spent Recreating Space Program Criteria (hours/space) | 0.25 | hours / space | 10% | 0.025 | Average time spent by Planner recreating Space Program Criteria
Avg. Time Spent Reformatting Room Data Sheet (hours/space) | 0.08333 | hours | 10% | 0.008333 | Average time spent in evaluating information in Project Definition and identifying and creating a detailed spatial program
Avg. Time to Compare Space Program with Owner Standards (hours) | 1 | hours | 5% | 0.05 | Average time spent by Owners Rep in validating Space Program provided by planner
Avg. Percentage of errors in Space Program | 0.3 | % | - | 30% | Average percentage of errors found by Owners Rep in Space Program
Avg. Time Spent Recreating Space Program (hours/space) | 0.25 | hours / space | 5% | 0.0125 | Average time spent by Planner recreating Space Program
Avg. Number of Transmittals | 2 | Transmittals | - | 2 | Average number of times Space Program / Comments are sent between the Planner and Owners Rep times the number of recipients for each exchange.
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 16.5 | $ / Transmittal | 0 | 0 | Average cost for delivering documents/comments sent between Planner and Owners Rep
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.16667 | hours / transmittal | - | 0.16667 | Average time spent in compiling documents for transmittal
Product Program
Avg. Time Spent Recreating Product Program Criteria (hours / product) | 0.25 | hours / product | 10% | 0.025 | Average time spent by Planner recreating Product Program Criteria
Avg Time to Compare Product Program with Owner Standards (hours/product) | 0.05 | hour | 10% | 0.005 | Average time spent by Owners Rep in validating Product Program provided by Planner
Avg. Percentage of errors in Product Program | 0.3 | % | - | 30% | Average percentage of errors found by Owners Rep in Product Program
Avg. Time Spent Recreating Product Program (hours/product) | 0.083333 | hours / product | 5% | 0.0041667 | Average time spent by Planner recreating Product Program
Avg. Number of Transmittals | 2 | Transmittals | - | 2 | Average number of times Product Program / Comments are sent between the Planner and Owners Rep times the number of recipients for each exchange.
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 23.95 | $ / Transmittal | 0 | 0 | Average cost for mailing documents/comments sent between Planner and Owners Rep.
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.16667 | hours / transmittal | - | 0.16667 | Average time spent in compiling documents for transmittal.
Request for Proposal
Avg. Number of Letter Sized Pages in RFP (pages / proposal) | 50 | pages / proposal |  | 50 | Average number of Letter-Sized Pages
Avg. Number of Drawing Sheets in Proposal (sheets / proposal) | 2 | sheets / proposal |  | 2 | Average number of Drawings
Number of RFP copies Reqd. (sets / submittal) | 5 | sets / submittal | 0 | 0 | Number of RFP copies required
Avg. Number of Transmittals - Owners Rep documents to Bidders | 5 | Transmittals | - | 5 | Average number of times Proposal is sent from the Owners Rep to the Bidders times the number of recipients for each exchange.
Avg. Number of Transmittals - Architect to Owner | 1 | Transmittals | - | 1 | Average number of times Proposal is sent from the Architect to the Owners Rep times the number of recipients for each exchange.
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 0.04 | hours / submittal set | 0 | 0 | Average time spent in printing and making copies of Proposal by Architect
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Owners Rep documents to Bidders | 18.8 | $ / Transmittal | 0 | 0 | Average cost for mailing proposal between Architect and Owners Rep.
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Architect to Owners Rep | 18.8 | $ / Transmittal | 0 | 0 | Average cost for mailing proposal between Architect and Owners Rep.
Avg. Time to Prepare Transmittal (hours / transmittal) - Owners Rep | 0.75 | hours / transmittal | - | 0.75 | Average time spent in compiling documents for transmittal / submission
Avg. Time to Prepare Transmittal (hours / transmittal) - Architect | 1 | hours / transmittal | - | 1 | Average time spent in compiling documents for transmittal / submission
Design Early
Avg. Time Spent Reformatting Space Program Requirements(hours / space type) | 0.16666 | hours / space type | 30% | 0.049998 | Average time spent by Architect in reformatting spatial requirements
Avg. Time Spent Reformatting Equipment Type (hours /product) | 0.25 | hours / product | 30% | 0.075 | Average Time spent by Architect reformatting equipment types
Avg. Time Spent Evaluating Design Early Drawings against Design Requirements - Space and Equipment | 12 | hours | 50% | 6 | Average time spent by Architect in validating Design Early drawings before submission to Owners Rep
Avg Time to Compare Design Early Documents with Owner Standards | 24 | hours | 50% | 12 | Average time spent by Owners Rep in validating Design Early documents
Avg. Time spent making corrections due to non-conformance with Space or Product Program | 7.8497 | hours | 10% | 0.78497 | Average time spent by Architect making corrections based on feedback from Owners Rep.
Avg. Number of Review Cycles | 3 | Cycles | - | 3 | Average number of times submitted docmentation is examined.
Percentage of Time Spent by Licensed Professional Architect | 0.9 | % | - | 90% | Percentage of time spent by Licensed Architect reformatting Space Program, Equipment Type and Project Definition
Percentage of Time Spent by Architect Drafter | 0.1 | % | - | 10% | Percentage of time spent by Architect Drafter reformatting Space Program, Equipment Type and Project Definition
Avg. Number of Transmittals | 3 | Transmittals | - | 3 | Average number of times drawings, narratives and comments are sent and received between the Architect / Planner and Owner times the number of recipients for each exchange
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 0.173 | hours / submittal set | 0% | 0 | Average time spent in printing and making copies of drawings and narratives by Architect / Planner
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Owners Rep to Architect | 16.5 | $ / Transmittal | 0 | 0 | Average cost for mailing documents/comments sent between Owners Rep and Architect
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Architect to Owners Rep | 27.1 | $ / Transmittal | 0 | 0 | Average cost for mailing documents/comments between Architect and Owners Rep.
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.5 | hours / transmittal | 40% | 0.2 | Average time spent compiling copies of drawings, narratives and comments for transmittal by Architect and Owners Rep.
Design Schematic
Avg. Number of Plan Drawings in Design Schematic Drawings | 18.4 | plans / drawing set | - | 18.4 | Average number of Plan Drawings
Avg. Time Spent Developing Equipment (product) Type Template (hours / product type) | 0.25 | hours / product type | 10% | 0.025 | Time spent by Architect in developing product requirment for equipment types required for the project
Avg. Time Spent Evaluating Design Schematic Drawings against Design Requirements - Space and Equipment | 41 | hours | 50% | 20.5 | Average time spent by Architect in validating Design Schematic drawings before submission to Owners Rep
Avg Time to Compare Design Schematic Documents with Owner Standards | 16 | hours | 50% | 8 | Average time spent by Owners Rep in validating Design Schematic documents
Avg. Time spent making corrections due to non-conformance with Space or Product Program | 11.7745 | hours | 10% | 1.1775 | Average time spent by Architect making corrections based on feedback from Owners Rep.
Avg. Number of Review Cycles | 3 | Cycles | - | 3 | Average number of times submitted docmentation is examined.
Percentage of Time Spent by Licensed Professional Architect | 0.8 | % | - | 80% | Percentage of time spent by Licensed Architect to take off all equipment pieces and to calculate areas
Percentage of Time Spent by Architect Drafter | 0.2 | % | - | 20% | Percentage of time spent by Architect Drafter to take off all equipment pieces and to calculate areas
Avg. Number of Transmittals | 3 | Transmittals | - | 3 | Average number of times schematic drawings, narratives, specifications and comments are sent and received between the Architect / Planner and Owner times the number of recipients for each exchange
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 0.504 | hours/submittal set | 0% | 0 | Average time spent in printing and making copies of drawings, narratives and specifications by Architect / Planner
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Owners Rep to Architect | 16.5 | $ / Transmittal | 0 | 0 | Average cost for mailing documents/comments sent between Owners Rep and Architect
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Architect to Owners Rep | 47.7 | $ / Transmittal | 0 | 0 | Average cost for mailing documents/comments between Architect and Owners Rep.
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.5 | hours / transmittal | 40% | 0.2 | Average time spent compiling copies of schematic drawings, narratives, specifications and comments for transmittal by Architect and Owners Rep.
Design Coordinated
Avg. Number of Plan Drawings in Design Coordinate Drawings | 36.8 | plans / drawing set | - | 36.8 | Average number of Plan Drawings
Avg. Time Spent Developing Detailed Equipment (products) Type Template (hours / product) | 2 | hours / product | 10% | 0.2 | Time spent by Architect in preparing a detailed product requirment list based on equipment types
Avg. Time Searching for Product Literature for Candidates (Hours/product) | 1 | hours / product | 10% | 0.1 | Average Time spent by Architect in searching for product data
Avg. Time Spent Evaluating Design Coordinated Drawings against Design Requirements - Space and Equipment | 38 | hours | 50% | 19 | Average time spent by Architect in validating Design Coordinated drawings before submission to Owners Rep
Avg. Percent of Errors in Product Type Candidate | 0.15 | % | - | 15% | Percentage of errors in Product Type List
Avg Time to Compare Design Coordinated & Product Type Candidate Documents with Owner Standards | 16 | hours | 50% | 8 | Average time spent by Owners Rep in validating Design Coordinated documents
Avg. Time Spent making Corrections due to Non-Conformance with Space or Product Program | 6.5414 | hours | 10% | 0.65414 | Average time spent by Architect making corrections based on feedback from Owners Rep.
Avg. Number of Review Cycles | 3 | Cycles | - | 3 | Average number of times submitted docmentation is examined.
Percentage of Time Spent by Licensed Professional Architect | 0.8 | % | - | 80% | Percentage of time spent by Licensed Architect to take off all equipment pieces and to calculate areas
Percentage of Time Spent by Architect Drafter | 0.2 | % | - | 20% | Percentage of time spent by Architect Drafter to take off all equipment pieces and to calculate areas
Avg. Number of Transmittals | 3 | Transmittals | - | 3 | Average number of times coordinated drawings, narratives, specifications and comments are sent and received between the Architect and Owners Rep times the number of recipients for each exchange
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 2 | hours / submittal set | 0 | 0 | Average time spent in printing and making copies of drawings, narratives and specifications by Architect
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Owners Rep to Architect | 16.5 | $ / Transmittal | 0 | 0 | Average cost for mailing documents/comments sent between Architect and Owners Rep
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Architect to Owners Rep | 87.3 | $ / Transmittal | 0 | 0 | Average cost for mailing documents between Architect and Owners Rep.
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.5 | hours / transmittal | 40% | 0.2 | Average time spent compiling copies of coordinated drawings, narratives, specifications and comments for transmittal by Architect and Owners Rep
Design Final
Avg. Number of Plan Drawings in Design Final Drawings | 115 | plans / drawing set | - | 115 | Average number of Plan Drawings
Avg. Time Spent Developing Detailed Equipment (products) Type Candidate (hours / product) | 1 | hours / product | 10% | 0.1 | Time spent by Architect in preparing a detailed product requirment list based on equipment types
Avg. Time Spent Evaluating Design Final Drawings against Design Requirements - Space and Equipment | 12 | hours | 50% | 6 | Average time spent by Architect in validating Design Final drawings before submission to Owners Rep
Percentage of Time Spent by Licensed Professional Architect | 0.9 | % | - | 90% | Percentage of time spent by Licensed Architect to take off all equipment pieces and to calculate areas
Percentage of Time Spent by Architect Drafter | 0.1 | % | - | 10% | Percentage of time spent by Architect Drafter to take off all equipment pieces and to calculate areas
Avg. Number of Transmittals | 1 | Transmittals | - | 1 | Average number of times final drawings, narratives, specifications and comments are sent and received between the Architect and Owners Rep times the number of recipients for each exchange.
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 2.3 | hours / submittal set | 0 | 0 | Average time spent in printing and making copies of drawings, narratives and specifications by Architect / Planner
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Owners Rep to Architect | 16.5 | $ / Transmittal | 0 | 0 | Average cost for mailing documents/comments sent between Architect and Owners Rep
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Architect to Owners Rep | 118 | $ / Transmittal | 0 | 0 | Average cost for mailing proposal between Architect and Owners Rep.
Avg. Time to Prepare Transmittal (hours / transmittal) | 1 | hours / transmittal | 40% | 0.4 | Average time spent compiling copies of final drawings, narratives, specifications for transmittal by Architect
Request for Proposal
Avg. Number of Transmittals | 5 | Transmittals | - | 5 | Average number of times RFP Package is sent from Owners Rep to Contractor times the number of recipients for purpose of bidding.
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 2.36 | hours / submittal set | 0 | 0 | Average time spent in printing and making copies of RFP Package by Owners Rep.
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 119.7 | $ / Transmittal | 0 | 0 | Average cost for mailing RFP by Owners Rep.
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.75 | hours / transmittal | - | 0.75 | Time spent compiling documents, drawings or specifications for transmittal by Owners Rep.
Avg. Number of Request for Proposal Submittal Sets Reqd. | 1 | submittal sets | 0 | 0 | Average number of RFP sets required for submission
Inquiry Issue
Avg. Number of Transmittals | 3 | Transmittals | - | 3 | Average number of times Inquiry Issues and responses are sent and received between Owners Rep, Architect and Contractor times the number of recipients for each exchange
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 16.5 | $ / Transmittal | 0 | 0 | Average cost for mailing documents/comments sent between Owners Rep, Architect, and Contractor
Avg. Time to Prepare Transmittals for Inquiry Issues (hours / transmittal) - Contractor / Architect | 0.16667 | hours / transmittal | 40% | 0.066667 | Time spent compiling documents, drawings or specifications for transmittal by Architect and Contractor
Avg. Time to Prepare Transmittals for Inquiry Issues (hours / transmittal) - Owners Rep | 0.083 | hours / transmittal | 40% | 0.0332 | Time spent compiling documents, drawings or specifications for transmittal by Owners Rep.
Pre-Construction Plan
0
Inquiry Issue (RFI)
Avg. Number of RFIs | 87 | Transmittals | - | 87 | Average number of times Inquiry Issues (RFI) and responses are sent and received between Owners Rep, Architect and Contractor times the number of recipients for each exchange
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 16.5 | $ / Transmittal | 0 | 0 | Average cost for mailing documents/comments sent between Owners Rep, Architect, and Contractor
Avg. Time to Prepare Transmittals for Inquiry Issues (RFI) (hours / transmittal) - Contractor / Architect | 0.16667 | hours / transmittal | 40% | 0.066667 | Average Time spent compiling Inquiry Issues (RFI) for transmittal by Architect and Contractor
Avg. Time to Prepare Transmittals for Inquiry Issues (RFI) (hours / transmittal) - Owner | 0.033333 | hours / transmittal | 40% | 0.013333 | Average Time spent compiling Inquiry Issues (RFI) for transmittal by Owners Rep
Product Type Selection
Time Spent Validating Equipment (products) Type against Template (hours / product) | 0.5 | hours / product | 50% | 0.25 | Time spent by Contractor in comparing equipment specifications against submittal information
System Layout
Submittal Package
Avg. Time Spent Organizing Equipment (product) Type information (hours / submittal item) | 0.16667 | hours / submittal item | 10% | 0.016667 | Time spent by asst. project manager in producing submittal information by organizing equipment type information
Avg. Time Spent Evaluating Equipment (product) Type Submittal Items against Contract Documents (hours / submittal item) | 0.5 | hours / submittal item | 50% | 0.25 | Time spent evaluating submittal items
Avg. Time to Sign each Page (hours/page) | 0.083333 | hours/page | 0% | 0 | Average time required by Contractor to sign pages of Submittal Package
Avg. Time to Stamp each Sheet (hours / sheet) | 0.083333 | hours/sheet | 0% | 0 | Average time required by Contractor to stamp sheets of Submittal Package
Percentage of Submittals Items rejected | 0.2 | % | - | 20% | Percentage of items rejected
Percentage of Time Spent by Construction Project Manager | 0.1 | % | - | 10% | Percentage of time spent by Construction Project Manager in validating Submittal Information
Percentage of Time Spent by Assistant (Construction) Project Manager | 0.9 | % | - | 90% | Percentage of time spent by Assistant Construction Project Manager in validating Submittal Information
Avg. Number of Transmittals | 342 | Transmittals | - | 342 | Average number of times Submittal Packages are sent and received between Owners Rep, Architect and Contractor times the number of recipients for each exchange
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 0.015 | hours / submittal set | 0 | 0 | Average time spent in printing and making copies of Submittal Package by Contractor
Average Mailing Costs per Transmittal ($) | 16.5 | $ / Transmittal | 0 | 0 | Average cost for Mailing documents/transmittals sent between Owners Rep and Contractor
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.5 | hours / transmittal | 40% | 0.2 | Average time spent compiling Submittal Package for transmittal by Architect / Contractor
Submittal Issue
Avg. Time Spent Evaluating Product Type Submittal Items against Contract Documents (hours / product type submittal item) | 1 | hours / submittal item | 50% | 0.5 | Average Time spent by Architect in evaluating submittal package of equipment types
Avg. Time Spent Revising one Product Submittal Item (hours / product) | 0.5 | hours / product | 10% | 0.05 | Average Time spent by Contractor recreating Submittal Items
Percentage of Product Submittals reviewed by Licensed Architect | 25% | % | - | 25% | Percentage of submittals reviewed by Architect
Percentage of Product Submittals rejected on first review | 42.5% | % | - | 42.5% | Percentage of submittals rejected upon review
Percentage of Product Submittals rejected on second review | 25% | % | - | 25% | Percentage of submittals rejected upon review
Percentage of Product Submittals rejected on third review | 8% | % | - | 8% | Percentage of submittals rejected upon review
Avg. Time Spent Transferring Comments per Page | 0.033333 | hours / submittal package | 0 | 0 | Time spent by Architect in marking up submittal with comments
Avg. Time Spent Transferring Comments per Sheet | 0.083333 | hours / submittal package | 0 | 0 | Time spent by Architect in marking up submittal with comments
Percentage of Time Spent by Construction Project Manager | 0.8 | % | - | 80% | Percentage of time spent by Construction Project Manager in recreating Submittal Package
Percentage of Time Spent by Assistant (Construction) Project Manager | 0.2 | % | - | 20% | Percentage of time spent by Assistant Construction Project Manager in recreating Submittal Package
Avg. Number of Transmittals | 6 | Transmittals | - | 6 | Average number of times Submittal Packages (pages and sheets) are sent and received between Architect and Contractor times the number of recipients for each exchange
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.083333 | hours / transmittal | 40% | 0.033333 | Average time spent compiling Submittal Package for transmittal by Architect
Avg. Mailing Cost per Transmittal | 16.5 | $ / Transmittal | 0 | 0 | Average cost for Mailing documents/transmittals between Architect / Planner and Contractor
Purchase Order
Product Installation
Avg. Time Spent Recording Components Data | 0.16667 | hours / component | 40% | 0.066667 | Average time spent by Contractor recording data for installed components
Avg Number of Months of Construction (months) | 12 | months | - | 12 | Average duration of project
Total Time Spent in Office (hours / day) | 8 | hours / day | - | 8 | Total time spent in the office on a daily basis
Avg. Percentage of Office Time Spent formatting Product Installation Report | 0.25 | % | 10% | 2.5% | Average percentage of time spent by Contractor in the office formatting report
Avg. Number of Transmittals (Transmittals) | 2 | Transmittals | - | 2 | Average number of times Product Installation Reports are sent and received between Contractor and Architect / Owner times the number of recipients for each exchange
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 16.5 | $ / Transmittal | 0 | 0 | Average cost for mailing Product Installlation Report by Contractor
Avg. Time to Prepare a Transmittal (hours/transmittal) | 0.083333 | hours / transmittal | 40% | 0.033333 | Average time spent compiling Product Installation for transmittal by Assistant Construction Manager
Start-Up
Product Inspection
Avg. Time Spent Documenting Report per Site Visit (hours / visit) | 2.75 | hours / visit | 40% | 1.1 | Average time spent in the field documenting data during site visits.
Avg. Number of Site Visits per month | 4 | nos | - | 4 | Average number of times site is visited in a month
Avg Number of Months of Construction | 12 | months | - | 12 | Average duration of project
Total Time Spent in Office (hours / day) | 8 | hours / day | - | 8 | Total time spent in the office on a daily basis
Avg. Percentage of Office Time Spent Quantifying products in place | 0.25 | % | 10% | 2.5% | Average percentage of time spent in the office documenting data recorded from the field.
Avg. Number of Transmittals | 2 | Transmittals | - | 2
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 16.5 | $ / Transmittal | 0 | 0 | Average cost for mailing Inspection Reports by Architect
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.083333 | hours / transmittal | 40% | 0.033333 | Average time spent compiling Inspection Report for transmittal by Architect
Punch list Issue
Avg. Time Spent Documenting Punchlist Report per Site Visit | 0.25 | hours / component | 10% | 0.025 | Average time spent in the office recording information gathered from a walkthrough of completed construction work.
Avg. Number of Site Visits for Punchlist Inspection | 0.9 | nos of visits | - | 0.9 | Average number of times site is visited to conduct Punchlist Inspection
Total Time Spent in Office | 1 | hours | - | 1 | Total time spent in the office on a daily basis
Avg. Percentage of Office Time Spent Documenting Site Visit | 0 | % | 10% | 0% | Average percentage of time spent in the office documenting data recorded from the field.
Avg. Number of Transmittals | 2 | Transmittals | - | 2 | Average number of times Punch list Reports are sent and received between Architect and Contractor times the number of recipients for each exchange
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 16.5 | $ / Transmittal | 0 | 0 | Average cost for mailing Punch list Reports by Architect
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.25 | hours / transmittal | 40% | 0.1 | Average time spent compiling Punch list Report for transmittal by Architect
Turnover Package
Avg. Time Spent Searching and Assembling Operations & Maintenance Manuals (hours / document) | 3 | hours / document | 10% | 0.3 | Time spent compiling O&M Manual
Avg. Time Spent Searching and Assembling Commissioning Report (hours / document) | 0 | hours / document | 10% | 0 | Time spent compiling Commissioning Report
Avg. Time Spent Searching and Assembling Record Specifications (hours / document) | 1.5 | hours / document | 10% | 0.15 | Time spent compiling Record Specifications
Avg. Time Spent Searching and Assembling Record (As-Built) Drawings (hours / sheet) | 0.0008 | hours / sheet | 10% | 8e-05 | Time spent compiling Record (As-Built) Drawings
Avg. Time Spent Searching and Assembling Final Approved Shop Drawings (hours / sheet) | 0.0083333 | hours / sheet | 10% | 0.00083333 | Time spent compiling Final Approved Shop Drawings
Avg. Number of Pages in Operations & Maintenance Manuals | 5425 | pages | - | 5425 | Number of Pages in Operations & Maintenance Manuals
Avg. Number of Pages in Commissioning Report | 0 | pages | - | 0 | Number of Pages in Commissioning Report
Avg. Number of Pages in Record Specifications | 2156 | pages | - | 2156 | Number of Pages in Record Specifications
Avg. Number of Sheets in Record (As-Built) Drawings | 364 | sheets | - | 364 | Number of Sheets in Record (As-Built) Drawings
Avg. Number of Sheets in Final Approved Shop Drawings | 1 | sheets | - | 1 | Number of Sheets in Final Approved Shop Drawings
Avg. Time Spent Reviewing Operations & Maintenance Manuals (hours/page) | 0.0016667 | hours / page | 40% | 0.00066667 | Time Spent Reviewing Operations & Maintenance Manuals
Avg. Time Spent Reviewing Commissioning Report (hours / page) | 0 | hours / page | 40% | 0 | Time Spent Reviewing Commissioning Report
Avg. Time Spent Reviewing Record Specifications (hours / page) | 0.0016667 | hours / page | 40% | 0.00066667 | Time Spent Reviewing Record Specifications
Avg. Time Spent Reviewing Record (As-Built) Drawings (hours/ sheet) | 0.0083333 | hours / sheet | 40% | 0.0033333 | Time Spent Reviewing Record (As-Built) Drawings
Avg. Time Spent Reviewing Final Approved Shop Drawings (hours / sheet) | 0.0083333 | hours / sheet | 40% | 0.0033333 | Time Spent Reviewing Final Approved Shop Drawings
Avg. Time Spent Filing Operations & Maintenance Manuals (hours/document) | 0.08333 | hours / document | 0 | 0 | Time Spent Filing Operations & Maintenance Manuals
Avg. Time Spent Filing Commissioning Report (hours/document) | 0 | hours / document | 0 | 0 | Time Spent Filing Commissioning Report
Avg. Time Spent Filing Record Specifications (hours/document) | 0.08333 | hours / document | 0 | 0 | Time Spent Filing Record Specifications
Avg. Time Spent Filing Record (As-Built) Drawings (hours / sheet) | 0.0016667 | hours / sheet | 0 | 0 | Time Spent Filing Record (As-Built) Drawings
Avg. Time Spent Filing Final Approved Shop Drawings(hours / sheet) | 0.0016667 | hours / sheet | 0 | 0 | Time Spent Filing Final Approved Shop Drawings
Percentage of Time Spent by Construction Project Manager | 0.1 | % | - | 10% | Percentage of time spent by Construction Project Manager in compiling Turnover Package
Percentage of Time Spent by Assistant (Construction) Project Manager | 0.9 | % | - | 90% | Percentage of time spent by Assistant Construction Project Manager in compiling Turnover Package
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 9 | hours / submittal set | 0 | 0 | Average time spent in printing and making copies of Turnover Package by Contractor
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 350.32 | $ / Transmittal | 0 | 0 | Average cost for mailing Turnover Package by Contractor
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.5 | hours / transmittal | 40% | 0.2 | Average time spent compiling Turnover Package for transmittal by Contractor

## 010_Facility_Criteria
| Process Name | Facility Criteria
| OmniClass Stage | 31-10 11 14 Project Description Phase
| Omniclass Role | 34-21 14 00 Owner
| Description | Standard facility information must be available in order to determine the basic requirements for a potential project. The owner indentifies the need and either develops technical criteria for the facility if none exist or utilizes existing technical criteria if available. If it does exist, this information must be checked for relevancy every five years to remain consistent with overall needs.
Information Attributes
|  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor
|  | Current process cost: | 4.6268 | 4.6268 | 0 | 0 |  | Elec. Doc Current process cost: | 4.6268 | 4.6268 | 0 | 0 |  | COBie Current process cost: | 0 | 0 | 0 | 0
|  | Expected process cost: | 0 | 0 | 0 | 0 |  | Elec. Doc Expected process cost: | 0 | 0 | 0 | 0 |  | COBie Expected process cost: | 0 | 0 | 0 | 0
|  | Process Cost Difference: | 4.6268 | 4.6268 | 0 | 0 |  | Process Cost Difference: | 4.6268 | 4.6268 | 0 | 0 |  | Process Cost Difference: | 0 | 0 | 0 | 0
Process
Reference Chapter 2 Appendix for Process Map:
| Current Process | [7 empty] | Expected Process
| 010.01 | Identify Need | [6 empty] | 010.01 | Identify Need
| 010.02.10 | Review Existing Facility Criteria | [6 empty] | 010.02.10 | Review Existing Facility Criteria
| 010.02.30 | Produce Technical Criteria | [6 empty] | 010.02.30 | Produce Technical Criteria
COPYING/ ELEC.DOC. | 010.02.40 | Copy Facility Criteria (UFC Criteria) | [6 empty] | 010.02.40 | Copy Facility Criteria (UFC Criteria)
|  | 14 | Avg. Number of Pages in Facility Criteria | [6 empty] | 14 | Avg. Number of Pages in Facility Criteria
|  | 2 | Avg. Number of Sets Required (sets / submittal) | [6 empty] | 0 | Avg. Number of Sets Required (sets / submittal)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 0.009 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 23.71 | Owner Administrative Rate ($ / hour) |  |  | 0.42678 |  |  |  | 23.71 | Owner Administrative Rate ($ / hour) |  | 0
|  |  | Reproduction Costs |  |  | 4.2 |  |  |  |  | Reproduction Costs |  | 0
|  |  | SubTotal |  |  |  | 4.6268 |  |  |  | SubTotal |  |  | 0
[6 empty] | Current Process Total | 4.6268 | [5 empty] | Current Process Total | 0

## 020_Discipline_Specifications
| Process Name | Discipline Specifications
OmniClass Stage
Omniclass Role
| Description | Specification information for equipment based on facility criteria is generated early in the planning process by the Owner. This information must be check for relevancy every five years to remain consistent with overall needs.
Information Attributes
|  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor
|  | Current process cost: | 132.8034 | 132.8034 | 0 | 0 |  | Elec. Doc Current process cost: | 132.8034 | 132.8034 | 0 | 0 |  | COBie Current process cost: | 0 | 0 | 0 | 0
|  | Expected process cost: | 0 | 0 | 0 | 0 |  | Elec. Doc Expected process cost: | 0 | 0 | 0 | 0 |  | COBie Expected process cost: | 0 | 0 | 0 | 0
|  | Process Cost Difference: | 132.8034 | 132.8034 | 0 | 0 |  | Process Cost Difference: | 132.8034 | 132.8034 | 0 | 0 |  | Process Cost Difference: | 0 | 0 | 0 | 0
Process
Reference Chapter 2 Appendix for Process Map
| Current Process | [7 empty] | Expected Process
| 020.01 | Identify Need | [6 empty] | 020.01 | Identify Need
| 020.02.10 | Review Existing Discipline Specification | [6 empty] | 020.02.10 | Review Existing Discipline Specification
| 020.02.30 | Produce Discipline Specification | [6 empty] | 020.02.30 | Produce Discipline Specification
COPYING/ ELEC.DOC. | 020.02.40 | Copy Discipline Specification | [6 empty] | 020.02.40 | Copy Discipline Specification
|  | 400 | Avg. Number of Pages in Discipline Specification | [6 empty] | 400 | Avg. Number of Pages in Discipline Specification
|  | 2 | Avg. Number of Sets Required (sets / submittal) | [6 empty] | 0 | Avg. Number of Sets Required (sets / submittal)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 0.27 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 23.71 | Owner Administrative Rate ($ / hour) |  |  | 12.8034 |  |  |  | 23.71 | Owner Administrative Rate ($ / hour) |  | 0
|  |  | Reproduction Costs |  |  | 120 |  |  |  |  | Reproduction Costs |  | 0
|  |  | SubTotal |  |  |  | 132.8034 |  |  |  | SubTotal |  |  | 0
[6 empty] | Current Process Total | 132.8034 | [5 empty] | Current Process Total | 0

## 030_Feasibility_Study
| Process Name | Feasibility Study
OmniClass Stage
Omniclass Role
| Description | The Feasibility Study allows the Owner to evaluate different options (typically three) based on the identified requirements before finalizing specific information about the project. The Architect or Planner develops the study based on the information contained in the Facility Criteria and Discipline Specification information exchanges.
Information Attributes
|  |  |  | Owner | Architect/ Planner | Contractor |  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor
|  | Current process cost: | 668.3479 | 74.8133 | 593.5345 | 0 |  | Elec. Doc Current process cost: | 668.3479 | 74.8133 | 593.5345 | 0 |  | COBie Current process cost: | 0 | 0 | 0 | 0
|  | Expected process cost: | 19.1167 | 7.9033 | 11.2133 | 0 |  | Elec. Doc Expected process cost: | 19.1167 | 7.9033 | 11.2133 | 0 |  | COBie Expected process cost: | 0 | 0 | 0 | 0
|  | Process Cost Difference: | 649.2312 | 66.91 | 582.3212 | 0 |  | Process Cost Difference: | 649.2312 | 66.91 | 582.3212 | 0 |  | Process Cost Difference: | 0 | 0 | 0 | 0
Process
Reference Chapter 2 Appendix for Process Map
| Current Process | [7 empty] | Expected Process
| 030.01 | Receive Facility Criteria and Discipline Specifications | [6 empty] | 030.01 | Receive Facility Criteria and Discipline Specifications
| 030.02 | Review Facility Criteria and Discipline Specifications Data | [6 empty] | 030.02 | Review Facility Criteria and Discipline Specifications Data
| 030.03 | Produce Feasibility Study | [6 empty] | 030.03 | Produce Feasibility Study
COPYING/ ELEC.DOC. | 030.04 | Copy Feasibility Study | [6 empty] | 030.04 | Copy Feasibility Study
|  | 3 | Avg. Number of Options | [6 empty] | 3 | Avg. Number of Options
|  | 6 | Avg. Number of Sheets per Option | [6 empty] | 6 | Avg. Number of Sheets per Option
|  | 10 | Avg. Number of Letter-Sized Pages in Design Narrative per Option | [6 empty] | 10 | Avg. Number of Letter-Sized Pages in Design Narrative per Option
|  | 4 | Avg. Pre-Design Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Avg. Pre-Design Submittal Sets Reqd. (sets / submittal)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 3 | Avg. Per Sheet Copy Cost ($ / sheet) | [6 empty] | 0 | Avg. Per Sheet Copy Cost ($ / sheet)
|  | 0.02 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 1.3456 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) |  | 0
|  |  | Reproduction Costs |  |  | 234 |  |  |  |  | Reproduction Costs |  | 0
|  |  | SubTotal |  |  |  | 235.3456 |  |  |  | SubTotal |  |  | 0
HANDLING/ ELEC.DOC. | 030.05 | Send Feasibility Study | [6 empty] | 030.05 | Send Feasibility Study
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 21.6 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.16667 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.16667 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 5.6067 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) |  | 5.6067
|  |  | Mailing Costs |  |  | 43.2 |  |  |  |  | Mailing Costs |  | 0
|  |  | SubTotal |  |  |  | 48.8067 |  |  |  | SubTotal |  |  | 5.6067
HANDLING/ ELEC.DOC. | 030.06 | Log Transmittal of Feasibility Study | [6 empty] | 030.06 | Log Transmittal of Feasibility Study
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 8.41 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 8.41 |  |  |  | SubTotal |  |  | 0
| 030.07 | Receive Feasibility Study | [6 empty] | 030.07 | Receive Feasibility Study
HANDLING/ ELEC.DOC. | 030.08 | Log Receipt of Feasibility Study | [6 empty] | 030.08 | Log Receipt of Feasibility Study
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 23.71 | Owner Administrative Rate ($ / hour) |  |  | 11.855 |  |  |  | 23.71 | Owner Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 11.855 |  |  |  | SubTotal |  |  | 0
| 030.09 | Review Feasibility Study | [6 empty] | 030.09 | Review Feasibility Study
HANDLING/ ELEC.DOC. | 030.10.20 | Send Comments to Planner | [6 empty] | 030.10.20 | Send Comments to Planner
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 21.6 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.16667 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.16667 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 23.71 | Owner Administrative Rate ($ / hour) |  |  | 7.9033 |  |  |  | 23.71 | Owner Administrative Rate ($ / hour) |  | 7.9033
|  |  | Mailing Costs |  |  | 43.2 |  |  |  |  | Mailing Costs |  | 0
|  |  | SubTotal |  |  |  | 51.1033 |  |  |  | SubTotal |  |  | 7.9033
HANDLING/ ELEC.DOC. | 030.10.21 | Log Transmittal of Feasibility Study Comments | [6 empty] | 030.10.21 | Log Transmittal of Feasibility Study Comments
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 23.71 | Owner Administrative Rate ($ / hour) |  |  | 11.855 |  |  |  | 23.71 | Owner Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 11.855 |  |  |  | SubTotal |  |  | 0
| 030.11 | Receive Feasibility Review Comments | [6 empty] | 030.11 | Receive Feasibility Review Comments
HANDLING/ ELEC.DOC. | 030.12 | Log Receipt of Review Comments | [6 empty] | 030.12 | Log Receipt of Review Comments
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 8.41 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 8.41 |  |  |  | SubTotal |  |  | 0
| 030.13 | Revise Feasibility Study | [6 empty] | 030.13 | Revise Feasibility Study
COPYING/ ELEC.DOC. | 030.14 | Copy Revised Feasibility Study | [6 empty] | 030.14 | Copy Revised Feasibility Study
|  | 3 | Avg. Number of Options | [6 empty] | 3 | Avg. Number of Options
|  | 6 | Avg. Number of Sheets per Option | [6 empty] | 6 | Avg. Number of Sheets per Option
|  | 10 | Avg. Number of Letter-Sized Pages in Design Narrative per Option | [6 empty] | 10 | Avg. Number of Letter-Sized Pages in Design Narrative per Option
|  | 4 | Avg. Pre-Design Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Avg. Pre-Design Submittal Sets Reqd. (sets / submittal)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 3 | Avg. Per Sheet Copy Cost ($ / sheet) | [6 empty] | 0 | Avg. Per Sheet Copy Cost ($ / sheet)
|  | 0.02 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 1.3456 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) |  | 0
|  |  | Reproduction Costs |  |  | 234 |  |  |  |  | Reproduction Costs |  | 0
|  |  | SubTotal |  |  |  | 235.3456 |  |  |  | SubTotal |  |  | 0
HANDLING/ ELEC.DOC. | 030.15 | Send Revised Feasibility Study | [6 empty] | 030.15 | Send Revised Feasibility Study
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 21.6 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.16667 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.16667 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 5.6067 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) |  | 5.6067
|  |  | Mailing Costs |  |  | 43.2 |  |  |  |  | Mailing Costs |  | 0
|  |  | SubTotal |  |  |  | 48.8067 |  |  |  | SubTotal |  |  | 5.6067
HANDLING/ ELEC.DOC. | 030.16 | Log Transmittal of Revised Feasibility Study | [6 empty] | 030.16 | Log Transmittal of Revised Feasibility Study
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 8.41 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 8.41 |  |  |  | SubTotal |  |  | 0
[6 empty] | Current Process Total | 668.3479 | [5 empty] | Current Process Total | 19.1167

## 040_Project_Definition
| Process Name | Project Definition
| OmniClass Stage | 31-10 11 14 Project Description Phase
| Omniclass Role | 34-21 14 00 Owner
| Description | Initial criteria about a project must be established in order to evaluate the project feasibility. The Owner evaluates the Facility Criteria, Discipline Specification, and Feasibility Study to determine whether or not to move forward with the project.
Information Attributes
|  |  |  | Owner | Architect/ Planner | Contractor |  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor
|  | Current process cost: | 4.6268 | 4.6268 | 0 | 0 |  | Elec. Doc Current process cost: | 4.6268 | 4.6268 | 0 | 0 |  | COBie Current process cost: | 0 | 0 | 0 | 0
|  | Expected process cost: | 0 | 0 | 0 | 0 |  | Elec. Doc Expected process cost: | 0 | 0 | 0 | 0 |  | COBie Expected process cost: | 0 | 0 | 0 | 0
|  | Process Cost Difference: | 4.6268 | 4.6268 | 0 | 0 |  | Process Cost Difference: | 4.6268 | 4.6268 | 0 | 0 |  | Process Cost Difference: | 0 | 0 | 0 | 0
Process
Reference Chapter 2 Appendix for Process Map
| Current Process | [7 empty] | Expected Process
| 040.01 | Review Information for Facility Criteria, Discipline Specifications, and Feasbility Study | [6 empty] | 040.01 | Review Information for Facility Criteria, Discipline Specifications, and Feasbility Study
| 040.02 | Evaluate Total Risk | [6 empty] | 040.02 | Evaluate Total Risk
| 040.03.10 | Produce Project Definition | [6 empty] | 040.03.10 | Produce Project Definition
COPYING/ ELEC.DOC. | 040.03.30 | Copy Project definition | [6 empty] | 040.03.30 | Copy Project definition
|  | 14 | Avg. Number of Pages in Project Definition | [6 empty] | 14 | Avg. Number of Pages in Project Definition
|  | 2 | Avg. Number of Sets Required (sets / submittal) | [6 empty] | 0 | Avg. Number of Sets Required (sets / submittal)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 0.009 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 23.71 | Owner Administrative Rate ($ / hour) |  |  | 0.42678 |  |  |  | 23.71 | Owner Administrative Rate ($ / hour) |  | 0
|  |  | Reproduction Costs |  |  | 4.2 |  |  |  |  | Reproduction Costs |  | 0
|  |  | SubTotal |  |  |  | 4.6268 |  |  |  | SubTotal |  |  | 0
[6 empty] | Current Process Total | 4.6268 | [5 empty] | Current Process Total | 0

## 050_Space_Program
| Process Name | Space Program
| OmniClass Stage | 31-10 14 21 Project Programming Phase
| Omniclass Role | 34-21 17 00 Planner
| Description | Once the Project Definition has been established and approved, further development of the project requirements can occur. The Architect or Planner evaluates information contained in the Project Definition information exchange to identify space needs based on the facility type. If no standard facility space criteria exist, it must be created by referencing similar facility types.
Information Attributes
|  |  |  | Owner | Planner/ Architect | Contractor |  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor
|  | Current process cost: | 2832.8919 | 117.7067 | 2715.1853 | 0 |  | Elec. Doc Current process cost: | 313.95 | 55.5067 | 258.4433 | 0 |  | COBie Current process cost: | 2518.9419 | 62.2 | 2456.7419 | 0
|  | Expected process cost: | 243.0621 | 8.7367 | 234.3254 | 0 |  | Elec. Doc Expected process cost: | 16.84 | 5.6267 | 11.2133 | 0 |  | COBie Expected process cost: | 226.2221 | 3.11 | 223.1121 | 0
|  | Process Cost Difference: | 2589.8299 | 108.97 | 2480.8599 | 0 |  | Process Cost Difference: | 297.11 | 49.88 | 247.23 | 0 |  | Process Cost Difference: | 2292.7199 | 59.09 | 2233.6299 | 0
Process
Reference Chapter 2 Appendix for Process Map
| Current Process | [7 empty] | Expected Process
| 050.01 | Utilize Project Definition to Develop Space Program Criteria | [6 empty] | 050.01 | Utilize Project Definition to Develop Space Program Criteria
| 050.02 | Evaluate Space Program Information | [6 empty] | 050.02 | Evaluate Space Program Information
RECREATING/ COBie | 050.03 | Recreate Space Program Criteria as Necessary | [6 empty] | 050.03 | Recreate Space Program Criteria as Necessary
|  | 159 | Avg. Number of Space Types per Building | [6 empty] | 159 | Avg. Number of Space Types per Building
|  | 0.25 | Avg. Time Spent Recreating Space Program Criteria (hours /space) | [6 empty] | 0.025 | Avg. Time Spent Recreating Space Program Criteria (hours /space)
|  | 37.84 | Planner Rate ($ / hour) |  |  | 1504.14 |  |  |  | 37.84 | Planner Rate ($ / hour) |  | 150.414
|  |  | SubTotal |  |  |  | 1504.14 |  |  |  | SubTotal |  |  | 150.414
REFORMATTING/ COBie | 050.04 | Reformat Requirements into Room Data Sheets for Project | [6 empty] | 050.04 | Reformat Requirements into Room Data Sheets for Project
|  | 159 | Avg. Number of Space Types per Building | [6 empty] | 159 | Avg. Number of Space Types per Building
|  | 0.08333 | Avg. Time Spent Reformatting Room Data Sheet (hours) | [6 empty] | 0.008333 | Avg. Time Spent Reformatting Room Data Sheet (hours)
|  | 37.84 | Planner Rate ($ / hour) |  |  | 501.3599 |  |  |  | 37.84 | Planner Rate ($ / hour) |  | 50.136
|  |  | SubTotal |  |  |  | 501.3599 |  |  |  | SubTotal |  |  | 50.136
COPYING & HANDLING/ ELEC.DOC. | 050.05 | Send Copies of Space Program | [6 empty] | 050.05 | Send Copies of Space Program
|  | 65 | Avg. Number of Pages in Space Program | [6 empty] | 65 | Avg. Number of Pages in Space Program
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 4 | Avg. Pre-Design Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Avg. Pre-Design Submittal Sets Reqd. (sets / submittal)
|  | 0.16667 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.16667 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 5.6067 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) |  | 5.6067
|  |  | Copying Costs |  |  | 78 |  |  |  |  | Copying Costs |  | 0
|  |  | Mailing Costs |  |  | 33 |  |  |  |  | Mailing Costs |  | 0
|  |  | SubTotal |  |  |  | 116.6067 |  |  |  | SubTotal |  |  | 5.6067
HANDLING/ ELEC.DOC. | 050.06 | Log Transmittal of Space Program | [6 empty] | 050.06 | Log Transmittal of Space Program
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 8.41 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 8.41 |  |  |  | SubTotal |  |  | 0
| 050.07 | Receive Space Program | [6 empty] | 050.07 | Receive Space Program
HANDLING/ ELEC.DOC. | 050.08 | Log Receipt of Space Program | [6 empty] | 050.08 | Log Receipt of Space Program
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 8.44 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 8.44 |  |  |  | SubTotal |  |  | 0
VALIDATING/ COBie | 050.09 | Validate Space Program | [6 empty] | 050.09 | Validate Space Program
|  | 1 | Avg time to Compare Space Program with Owner Standards | [6 empty] | 0.05 | Avg time to Compare Space Program with Owner Standards
|  | 62.2 | Owners Rep. Rate ($ / hour) |  |  | 62.2 |  |  |  | 62.2 | Owners Rep. Rate ($ / hour) |  | 3.11
|  |  | SubTotal |  |  |  | 62.2 |  |  |  | SubTotal |  |  | 3.11
HANDLING/ ELEC.DOC. | 050.10.10 | Send Comments | [6 empty] | 050.10.10 | Send Comments
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.16667 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.16667 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 5.6267 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  | 5.6267
|  |  | Mailing Costs |  |  | 33 |  |  |  |  | Mailing Costs |  | 0
|  |  | SubTotal |  |  |  | 38.6267 |  |  |  | SubTotal |  |  | 5.6267
HANDLING/ ELEC.DOC. | 050.10.20 | Log Transmittal of Space Program Comments | [6 empty] | 050.10.20 | Log Transmittal of Space Program Comments
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 8.44 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 8.44 |  |  |  | SubTotal |  |  | 0
| 050.11 | Receive Comments | [6 empty] | 050.11 | Receive Comments
HANDLING/ ELEC.DOC. | 050.12 | Log Receipt of Space Program | [6 empty] | 050.12 | Log Receipt of Space Program
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 8.41 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 8.41 |  |  |  | SubTotal |  |  | 0
RECREATING/ COBie | 050.13 | Recreate Space Program | [6 empty] | 050.13 | Recreate Space Program
|  | 30% | Avg. Percentage of errors in Space Program | [6 empty] | 30% | Avg. Percentage of errors in Space Program
|  | 159 | Avg. Number of Space Types per Building | [6 empty] | 159 | Avg. Number of Space Types per Building
|  | 0.25 | Avg. Time Spent Recreating Space Program (hours/space) | [6 empty] | 0.0125 | Avg. Time Spent Recreating Space Program (hours/space)
|  | 37.84 | Planner Rate ($ / hour) |  |  | 451.242 |  |  |  | 37.84 | Planner Rate ($ / hour) |  | 22.5621
|  |  | SubTotal |  |  |  | 451.242 |  |  |  | SubTotal |  |  | 22.5621
COPYING & HANDLING/ ELEC.DOC. | 050.14 | Send Revised Copies of Space Program | [6 empty] | 050.14 | Send Revised Copies of Space Program
|  | 65 | Avg. Number of Pages in Space Program | [6 empty] | 65 | Avg. Number of Pages in Space Program
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 4 | Avg. Pre-Design Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Avg. Pre-Design Submittal Sets Reqd. (sets / submittal)
|  | 0.16667 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.16667 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 5.6067 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) |  | 5.6067
|  |  | Copying Costs |  |  | 78 |  |  |  |  | Copying Costs |  | 0
|  |  | Mailing Costs |  |  | 33 |  |  |  |  | Mailing Costs |  | 0
|  |  | SubTotal |  |  |  | 116.6067 |  |  |  | SubTotal |  |  | 5.6067
HANDLING/ ELEC.DOC. | 050.15 | Log Transmittal of Revised Space Program | [6 empty] | 050.15 | Log Transmittal of Revised Space Program
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 8.41 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 8.41 |  |  |  | SubTotal |  |  | 0
[6 empty] | Current Process Total | 2832.8919 | [5 empty] | Current Process Total | 243.0621

## 060_Product_Program
| Process Name | Product Program
| OmniClass Stage | 31-10 14 21 Project Programming Phase
| Omniclass Role | 34-21 17 00 Planner
| Description | The Architect or Planner evaluates information contained in the Project Definition information exchange to identify product needs based on the facility type. If no standard facility product criteria exist, it must be created by refernecing similar facility types.
Information Attributes
|  |  |  | Owner | Planner/ Architect | Contractor |  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor
|  | Current process cost: | 1897.8894 | 73.5167 | 1824.3727 | 0 |  | Elec. Doc Current process cost: | 281.85 | 70.4067 | 211.4433 | 0 |  | COBie Current process cost: | 1616.0394 | 3.11 | 1612.9294 | 0
|  | Expected process cost: | 171.1125 | 5.9377 | 165.1748 | 0 |  | Elec. Doc Expected process cost: | 16.84 | 5.6267 | 11.2133 | 0 |  | COBie Expected process cost: | 154.2725 | 0.311 | 153.9615 | 0
|  | Process Cost Difference: | 1726.7769 | 67.579 | 1659.1979 | 0 |  | Process Cost Difference: | 265.01 | 64.78 | 200.23 | 0 |  | Process Cost Difference: | 1461.7669 | 2.799 | 1458.9679 | 0
Process
Reference Chapter 2 Appendix for Process Map
| Current Process | [7 empty] | Expected Process
| 060.01 | Utilize Project Definition & Space Requirements to Determine Product Program | [6 empty] | 060.01 | Utilize Project Definition & Space Requirements to Determine Product Program
| 060.02 | Evaluate Product Program Information | [6 empty] | 060.02 | Evaluate Product Program Information
RECREATING/ COBie | 060.03 | Recreate Product Program Criteria as Necessary | [6 empty] | 060.03 | Recreate Product Program Criteria as Necessary
|  | 155 | Avg. Number of Equipment (product) Types (Types / project) | [6 empty] | 155 | Avg. Number of Equipment (product) Types (Types / project)
|  | 0.25 | Avg. Time Spent Recreating Product Program Criteria(hours / product) | [6 empty] | 0.025 | Avg. Time Spent Recreating Product Program Criteria(hours / product)
|  | 37.84 | Planner Rate ($ / hour) |  |  | 1466.3 |  |  |  | 37.84 | Planner Rate ($ / hour) |  | 146.63
|  |  | SubTotal |  |  |  | 1466.3 |  |  |  | SubTotal |  |  | 146.63
HANDLING/ ELEC.DOC. | 060.04 | Send Copies of Product Program to Owner for Review | [6 empty] | 060.04 | Send Copies of Product Program to Owner for Review
|  | 33 | Avg. Number of Pages in Product Program | [6 empty] | 33 | Avg. Number of Pages in Product Program
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 23.95 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 4 | Avg. Pre-Design Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Avg. Pre-Design Submittal Sets Reqd. (sets / submittal)
|  | 0.16667 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.16667 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 5.6067 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) |  | 5.6067
|  |  | Copying Costs |  |  | 39.6 |  |  |  |  | Copying Costs |  | 0
|  |  | Mailing Costs |  |  | 47.9 |  |  |  |  | Mailing Costs |  | 0
|  |  | SubTotal |  |  |  | 93.1067 |  |  |  | SubTotal |  |  | 5.6067
HANDLING/ ELEC.DOC. | 60.05 | Log Transmittal of Product Program | [6 empty] | 60.05 | Log Transmittal of Product Program
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 8.41 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 8.41 |  |  |  | SubTotal |  |  | 0
| 060.06 | Receive Product Program | [6 empty] | 060.06 | Receive Product Program
HANDLING/ ELEC.DOC. | 060.07 | Log Receipt of Product Program | [6 empty] | 060.07 | Log Receipt of Product Program
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 8.44 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 8.44 |  |  |  | SubTotal |  |  | 0
VALIDATING/ COBie | 060.08 | Validate Product Program | [6 empty] | 060.08 | Validate Product Program
|  | 0.05 | Avg Time to Compare Product Program with Owner Standards (hours) | [6 empty] | 0.005 | Avg Time to Compare Product Program with Owner Standards (hours)
|  | 62.2 | Owners Rep. Rate ($ / hour) |  |  | 3.11 |  |  |  | 62.2 | Owners Rep. Rate ($ / hour) |  | 0.311
|  |  | SubTotal |  |  |  | 3.11 |  |  |  | SubTotal |  |  | 0.311
HANDLING/ ELEC.DOC. | 060.09.10 | Send Comments | [6 empty] | 060.09.10 | Send Comments
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 23.95 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.16667 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.16667 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 5.6267 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  | 5.6267
|  |  | Mailing Costs |  |  | 47.9 |  |  |  |  | Mailing Costs |  | 0
|  |  | SubTotal |  |  |  | 53.5267 |  |  |  | SubTotal |  |  | 5.6267
HANDLING/ ELEC.DOC. | 060.09.20 | Log Transmittal of Product Program Comments | [6 empty] | 060.09.20 | Log Transmittal of Product Program Comments
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 8.44 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 8.44 |  |  |  | SubTotal |  |  | 0
| 060.10 | Receive Comments | [6 empty] | 060.10 | Receive Comments
HANDLING/ ELEC.DOC. | 060.11 | Log Receipt of Product Program | [6 empty] | 060.11 | Log Receipt of Product Program
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 8.41 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 8.41 |  |  |  | SubTotal |  |  | 0
RECREATING/ COBie | 060.12 | Recreate Product Program | [6 empty] | 060.12 | Recreate Product Program
|  | 30% | Avg. Percent of errors in Product Program | [6 empty] | 30% | Avg. Percent of errors in Product Program
|  | 155 | Avg. Number of Equipment (product) Types (Types / project) | [6 empty] | 155 | Avg. Number of Equipment (product) Types (Types / project)
|  | 0.083333 | Avg. Time Spent Recreating Product Program (hours / product) | [6 empty] | 0.0041667 | Avg. Time Spent Recreating Product Program (hours / product)
|  | 37.84 | Planner Rate ($ / hour) |  |  | 146.6294 |  |  |  | 37.84 | Planner Rate ($ / hour) |  | 7.3315
|  |  | SubTotal |  |  |  | 146.6294 |  |  |  | SubTotal |  |  | 7.3315
COPYING & HANDLING/ ELEC.DOC. | 060.13 | Send Revised Copies of Product Program | [6 empty] | 060.13 | Send Revised Copies of Product Program
|  | 33 | Avg. Number of Pages in Product Program | [6 empty] | 33 | Avg. Number of Pages in Product Program
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 23.95 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 4 | Avg. Pre-Design Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Avg. Pre-Design Submittal Sets Reqd. (sets / submittal)
|  | 0.16667 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.16667 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 5.6067 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) |  | 5.6067
|  |  | Copying Costs |  |  | 39.6 |  |  |  |  | Copying Costs |  | 0
|  |  | Mailing Costs |  |  | 47.9 |  |  |  |  | Mailing Costs |  | 0
|  |  | SubTotal |  |  |  | 93.1067 |  |  |  | SubTotal |  |  | 5.6067
HANDLING/ ELEC.DOC. | 060.14 | Log Transmittal of Revised Product Program | [6 empty] | 060.14 | Log Transmittal of Revised Product Program
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 8.41 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 8.41 |  |  |  | SubTotal |  |  | 0
[6 empty] | Current Process Total | 1897.8894 | [5 empty] | Current Process Total | 171.1125

## 070_Request_For_Proposal
| Process Name | Request For Proposal
| OmniClass Stage | 31-10 14 21 Project Programming Phase
| Omniclass Role | 34-21 17 00 Planner
| Description | Once the major criteria have been determined, the Owner prepares and distributes a Request for Proposal (RFP).
Information Attributes
|  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor
|  | Current process cost: | 937.2917 | 764.8 | 172.4917 | 0 |  | Elec. Doc Current process cost: | 937.2917 | 764.8 | 172.4917 | 0 |  | COBie Current process cost: | 0 | 0 | 0 | 0
|  | Expected process cost: | 134.0033 | 63.3 | 70.7033 | 0 |  | Elec. Doc Expected process cost: | 134.0033 | 63.3 | 70.7033 | 0 |  | COBie Expected process cost: | 0 | 0 | 0 | 0
|  | Process Cost Difference: | 803.2884 | 701.5 | 101.7884 | 0 |  | Process Cost Difference: | 803.2884 | 701.5 | 101.7884 | 0 |  | Process Cost Difference: | 0 | 0 | 0 | 0
Process
Reference Chapter 2 Appendix for Process Map
| Current Process | [7 empty] | Expected Process
| 070.01 | Produce Request for Proposal Documents | [6 empty] | 070.01 | Produce Request for Proposal Documents
COPYING & HANDLING/ ELEC.DOC. | 070.02 | Send Copies of Request for Proposal (RFP) Package | [6 empty] | 070.02 | Send Copies of Request for Proposal (RFP) Package
|  | 65 | Avg. Number of Pages in Space Program | [6 empty] | 65 | Avg. Number of Pages in Space Program
|  | 33 | Avg. Number of Pages in Product Program | [6 empty] | 33 | Avg. Number of Pages in Product Program
|  | 14 | Avg. Number of Pages in Project Definition | [6 empty] | 14 | Avg. Number of Pages in Project Definition
|  | 50 | Avg. Number of Pages in Front Matter | [6 empty] | 50 | Avg. Number of Pages in Front Matter
|  | 5 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 5 | Avg. Number of Transmittals (Transmittals)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 18.8 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 5 | Number of RFP Submittal sets Reqd. | [6 empty] | 0 | Number of RFP Submittal sets Reqd.
|  | 0.75 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.75 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 63.3 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  | 63.3
|  |  | Copying Cost |  |  | 607.5 |  |  |  |  | Copying Cost |  | 0
|  |  | Mailing Cost |  |  | 94 |  |  |  |  | Mailing Cost |  | 0
|  |  | SubTotal |  |  |  | 764.8 |  |  |  | SubTotal |  |  | 63.3
| 070.03 | Receive Request for Proposal (RFP) Package | [6 empty] | 070.03 | Receive Request for Proposal (RFP) Package
HANDLING/ ELEC.DOC. | 070.04 | Log Receipt of Request for Proposal (RFP) Package | [6 empty] | 070.04 | Log Receipt of Request for Proposal (RFP) Package
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 17.6758 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 17.6758 |  |  |  | SubTotal |  |  | 0
| 070.05 | Review Request for Proposal (RFP) Package | [6 empty] | 070.05 | Review Request for Proposal (RFP) Package
| 070.06 | Produce Proposal | [6 empty] | 070.06 | Produce Proposal
COPYING/ ELEC.DOC. | 070.07 | Copy Proposal | [6 empty] | 070.07 | Copy Proposal
|  | 50 | Avg. Number of Letter Sized Pages in Proposal | [6 empty] | 50 | Avg. Number of Letter Sized Pages in Proposal
|  | 2 | Avg. Number of Drawing Sheets in Proposal | [6 empty] | 2 | Avg. Number of Drawing Sheets in Proposal
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 3 | Avg. Per Sheet Copy Cost ($ / sheet) | [6 empty] | 0 | Avg. Per Sheet Copy Cost ($ / sheet)
|  | 4 | Avg. Pre-Design Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Avg. Pre-Design Submittal Sets Reqd. (sets / submittal)
|  | 0.04 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 11.3125 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | Reproduction Costs |  |  | 54 |  |  |  |  | Reproduction Costs |  | 0
|  |  | SubTotal |  |  |  | 65.3125 |  |  |  | SubTotal |  |  | 0
HANDLING/ ELEC.DOC. | 070.08 | Send Proposal | [6 empty] | 070.08 | Send Proposal
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 18.8 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 1 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 1 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 70.7033 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 70.7033
|  |  | Mailing Costs |  |  | 18.8 |  |  |  |  | Mailing Costs |  | 0
|  |  | SubTotal |  |  |  | 89.5033 |  |  |  | SubTotal |  |  | 70.7033
[6 empty] | Current Process Total | 937.2917 | [5 empty] | Current Process Total | 134.0033

## 080_Design_Early
| Process Name | Design Early
| OmniClass Stage | 31-20 10 14 Conceptual Design Phase
| Omniclass Role | 34-25 21 00 Architect
| Description | The Architect utilizes the specific information produced during pre-design to develop a solution that reflects the requirements stated in the Project Definition, Space Program, and Product Program. The Architect performs a QA/QC check before submitting to the owner. After receiving the submission, the Owner's Representative reviews and provides comments to the Architect. The Architect and Consultants are then required to update the documents based on the comments. After revisions are made, the Archtect resubmits.
Information Attributes
|  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor
|  | Current process cost: | 22549.9846 | 6844.7325 | 15705.2521 | 0 |  | Elec. Doc Current process cost: | 5748.4485 | 873.5325 | 4874.916 | 0 |  | COBie Current process cost: | 16801.5361 | 5971.2 | 10830.3361 | 0
|  | Expected process cost: | 5558.0755 | 3111.064 | 2447.0115 | 0 |  | Elec. Doc Expected process cost: | 182.368 | 125.464 | 56.904 | 0 |  | COBie Expected process cost: | 5375.7075 | 2985.6 | 2390.1075 | 0
|  | Process Cost Difference: | 16991.9091 | 3733.6685 | 13258.2407 | 0 |  | Process Cost Difference: | 5566.0805 | 748.0685 | 4818.012 | 0 |  | Process Cost Difference: | 11425.8287 | 2985.6 | 8440.2287 | 0
Process
Reference Chapter 2 Appendix for Process Map
| Current Process | [7 empty] | Expected Process
| 080.01 | Receive NTP | [6 empty] | 080.01 | Receive NTP
| 080.02 | Request Design Requirements | [6 empty] | 080.02 | Request Design Requirements
HANDLING/ ELEC.DOC. | 080.03 | Send Copies of Design Requirements | [6 empty] | 080.03 | Send Copies of Design Requirements
|  | 65 | Avg. Number of Pages in Space Program | [6 empty] | 65 | Avg. Number of Pages in Space Program
|  | 33 | Avg. Number of Pages in Product Program | [6 empty] | 33 | Avg. Number of Pages in Product Program
|  | 14 | Avg. Number of Pages in Project Definition | [6 empty] | 14 | Avg. Number of Pages in Project Definition
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 8.44 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  | 3.376
|  |  | Copying Cost |  |  | 16.8 |  |  |  |  | Copying Cost |  | 0
|  |  | Mailing Cost |  |  | 16.5 |  |  |  |  | Mailing Cost |  | 0
|  |  | SubTotal |  |  |  | 41.74 |  |  |  | SubTotal |  |  | 3.376
HANDLING/ ELEC.DOC. | 080.04 | Log Transmittal of Design Requirements | [6 empty] | 080.04 | Log Transmittal of Design Requirements
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 4.22 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 4.22 |  |  |  | SubTotal |  |  | 0
| 080.05 | Receive Design Requirements | [6 empty] | 080.05 | Receive Design Requirements
HANDLING/ ELEC.DOC. | 080.06 | Log Receipt of Design Requirements | [6 empty] | 080.06 | Log Receipt of Design Requirements
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 17.6758 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 17.6758 |  |  |  | SubTotal |  |  | 0
| 080.07 | Review Design Requirements | [6 empty] | 080.07 | Review Design Requirements
REFORMATTING/ COBie | 080.08 | Reformat Design Requirements | [6 empty] | 080.08 | Reformat Design Requirements
|  | 159 | Avg. Number of Space Types per Building | [6 empty] | 159 | Avg. Number of Space Types per Building
|  | 0.16666 | Avg. Time Spent Reformatting Space Program Requirements(hours / space type) | [6 empty] | 0.049998 | Avg. Time Spent Reformatting Space Program Requirements(hours / space type)
|  | 155 | Avg. Number of Equipment (product) Types (Types / project) | [6 empty] | 155 | Avg. Number of Equipment (product) Types (Types / project)
|  | 0.25 | Avg. Time Spent Reformatting Equipment Type (hours /product) | [6 empty] | 0.075 | Avg. Time Spent Reformatting Equipment Type (hours /product)
|  | 90% | Percentage of Time Spent by Licensed Professional Architect | [6 empty] | 90% | Percentage of Time Spent by Licensed Professional Architect
|  | 10% | Percentage of Time Spent by Architect Drafter | [6 empty] | 10% | Percentage of Time Spent by Architect Drafter
|  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  |  | 6458.9991 |  |  |  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  | 1937.6997
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 461.3317 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 138.3995
|  |  | SubTotal |  |  |  | 6920.3308 |  |  |  | SubTotal |  |  | 2076.0992
| 080.09 | Produce Design Early Documents | [6 empty] | 080.09 | Produce Design Early Documents
| 080.10 | Receive Consultant's Early Design Documents | [6 empty] | 080.10 | Receive Consultant's Early Design Documents
| 080.11 | Produce Checkset of Design Early Documents | [6 empty] | 080.11 | Produce Checkset of Design Early Documents
VALIDATING/ COBie | 080.12 | Validate Checkset before Submission through manual QA/QC Process | [6 empty] | 080.12 | Validate Checkset before Submission through manual QA/QC Process
|  | 12 | Avg. Time Spent Evaluating Design Early Drawings against Design Requirements - Space and Equipment | [6 empty] | 0.5 | Avg. Time Spent Evaluating Design Early Drawings against Design Requirements - Space and Equipment
|  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  |  | 1319.868 |  |  |  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  | 54.9945
|  |  | SubTotal |  |  |  | 1319.868 |  |  |  | SubTotal |  |  | 54.9945
| 080.13.10 | Make Corrections (Architect and/or Consultants) | [6 empty] | 080.13.10 | Make Corrections (Architect and/or Consultants)
COPYING/ ELEC.DOC. | 080.13.20 | Copy Design Early Documents | [6 empty] | 080.13.20 | Copy Design Early Documents
|  | 48 | Avg. Number of Sheets in Design Early Drawings | [6 empty] | 48 | Avg. Number of Sheets in Design Early Drawings
|  | 60 | Avg. Number of Letter-Sized Pages in Design Early Narrative | [6 empty] | 60 | Avg. Number of Letter-Sized Pages in Design Early Narrative
|  | 6 | Number of Design Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Number of Design Submittal Sets Reqd. (sets / submittal)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 3 | Avg. Per Sheet Copy Cost ($ / sheet) | [6 empty] | 0 | Avg. Per Sheet Copy Cost ($ / sheet)
|  | 0.173 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 73.3901 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | Copying Cost |  |  | 918 |  |  |  |  | Copying Cost |  | 0
|  |  | SubTotal |  |  |  | 991.3901 |  |  |  | SubTotal |  |  | 0
HANDLING/ ELEC.DOC. | 080.13.30 | Send Design Early Documents | [6 empty] | 080.13.30 | Send Design Early Documents
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 27.1 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 23.71 | Architect Drafter Rate ($ / hour) |  |  | 35.565 |  |  |  | 23.71 | Architect Drafter Rate ($ / hour) |  | 14.226
|  |  | Mailing Cost |  |  | 81.3 |  |  |  |  | Mailing Cost |  | 0
|  |  | SubTotal |  |  |  | 116.865 |  |  |  | SubTotal |  |  | 14.226
HANDLING/ ELEC.DOC. | 080.13.40 | Log Transmittal of Design Early Documents | [6 empty] | 080.13.40 | Log Transmittal of Design Early Documents
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 53.0275 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 53.0275 |  |  |  | SubTotal |  |  | 0
| 080.14 | Receive Design Early Documents | [6 empty] | 080.14 | Receive Design Early Documents
HANDLING/ ELEC.DOC. | 080.15 | Log Receipt of Design Early Documents | [6 empty] | 080.15 | Log Receipt of Design Early Documents
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 12.66 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 12.66 |  |  |  | SubTotal |  |  | 0
VALIDATING/ COBie | 080.16 | Validate Design Early Documents | [6 empty] | 080.16 | Validate Design Early Documents
|  | 24 | Avg Time to Compare Design Early Documents with Owner Standards | [6 empty] | 12 | Avg Time to Compare Design Early Documents with Owner Standards
|  | 62.2 | Owners Rep. Rate ($ / hour) |  |  | 1492.8 |  |  |  | 62.2 | Owners Rep. Rate ($ / hour) |  | 746.4
|  |  | SubTotal |  |  |  | 1492.8 |  |  |  | SubTotal |  |  | 746.4
HANDLING/ ELEC.DOC. | 080.17.20 | Send Comments to Design Team | [6 empty] | 080.17.20 | Send Comments to Design Team
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 25.32 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  | 10.128
|  |  | Mailing Cost |  |  | 49.5 |  |  |  |  | Mailing Cost |  | 0
|  |  | SubTotal |  |  |  | 74.82 |  |  |  | SubTotal |  |  | 10.128
HANDLING/ ELEC.DOC. | 080.17.30 | Log Transmittal of Comments | [6 empty] | 080.17.30 | Log Transmittal of Comments
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 12.66 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 12.66 |  |  |  | SubTotal |  |  | 0
| 080.18 | Receive Review Comments | [6 empty] | 080.18 | Receive Review Comments
HANDLING/ ELEC.DOC. | 080.19 | Log Receipt of Comments | [6 empty] | 080.19 | Log Receipt of Comments
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 53.0275 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 53.0275 |  |  |  | SubTotal |  |  | 0
RECREATING/ COBie | 080.20 | Make Corrections (Architect and/or Consultants) | [6 empty] | 080.20 | Make Corrections (Architect and/or Consultants)
|  | 7.8497 | Avg. Time spent making corrections due to non-conformance with Space or Product Program | [6 empty] | 0.78497 | Avg. Time spent making corrections due to non-conformance with Space or Product Program
|  | 3 | Avg. Number of Review Cycles | [6 empty] | 3 | Avg. Number of Review Cycles
|  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  |  | 2590.1373 |  |  |  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  | 259.0137
|  |  | SubTotal |  |  |  | 2590.1373 |  |  |  | SubTotal |  |  | 259.0137
COPYING/ ELEC.DOC. | 080.21 | Copy Revised Design Early Documents | [6 empty] | 080.21 | Copy Revised Design Early Documents
|  | 48 | Avg. Number of Sheets in Design Early Drawings | [6 empty] | 48 | Avg. Number of Sheets in Design Early Drawings
|  | 60 | Avg. Number of Letter-Sized Pages in Design Early Narrative | [6 empty] | 60 | Avg. Number of Letter-Sized Pages in Design Early Narrative
|  | 6 | Number of Design Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Number of Design Submittal Sets Reqd. (sets / submittal)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 3 | Avg. Per Sheet Copy Cost ($ / sheet) | [6 empty] | 0 | Avg. Per Sheet Copy Cost ($ / sheet)
|  | 0.173 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 3 | Avg. Number of Review Cycles | [6 empty] | 3 | Avg. Number of Review Cycles
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 220.1702 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | Copying Cost |  |  | 2754 |  |  |  |  | Copying Cost |  | 0
|  |  | SubTotal |  |  |  | 2974.1702 |  |  |  | SubTotal |  |  | 0
HANDLING/ ELEC.DOC. | 080.22 | Send Revised Design Early Documents | [6 empty] | 080.22 | Send Revised Design Early Documents
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 27.1 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 3 | Avg. Number of Review Cycles | [6 empty] | 3 | Avg. Number of Review Cycles
|  | 23.71 | Architect Drafter Rate ($ / hour) |  |  | 106.695 |  |  |  | 23.71 | Architect Drafter Rate ($ / hour) |  | 42.678
|  |  | Mailing Cost |  |  | 243.9 |  |  |  |  | Mailing Cost |  | 0
|  |  | SubTotal |  |  |  | 350.595 |  |  |  | SubTotal |  |  | 42.678
HANDLING/ ELEC.DOC. | 080.23 | Log Transmittal of Revised Design Early Documents | [6 empty] | 080.23 | Log Transmittal of Revised Design Early Documents
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 3 | Avg. Number of Review Cycles | [6 empty] | 3 | Avg. Number of Review Cycles
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 159.0825 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 159.0825 |  |  |  | SubTotal |  |  | 0
| 080.24 | Receive Design Early Documents | [6 empty] | 080.24 | Receive Design Early Documents
HANDLING/ ELEC.DOC. | 080.25 | Log Receipt of Revised Design Early Documents | [6 empty] | 080.25 | Log Receipt of Revised Design Early Documents
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 3 | Avg. Number of Review Cycles | [6 empty] | 3 | Avg. Number of Review Cycles
|  | 62.2 | Owners Rep. Administrative Rate ($ / hour) |  |  | 139.95 |  |  |  | 62.2 | Owners Rep. Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 139.95 |  |  |  | SubTotal |  |  | 0
VALIDATING/ COBie | 080.26 | Validate Revised Design Early Documents | [6 empty] | 080.26 | Validate Revised Design Early Documents
|  | 24 | Avg Time to Compare Design Early Documents with Owner Standards | [6 empty] | 12 | Avg Time to Compare Design Early Documents with Owner Standards
|  | 3 | Avg. Number of Review Cycles | [6 empty] | 3 | Avg. Number of Review Cycles
|  | 62.2 | Owners Rep. Rate ($ / hour) |  |  | 4478.4 |  |  |  | 62.2 | Owners Rep. Rate ($ / hour) |  | 2239.2
|  |  | SubTotal |  |  |  | 4478.4 |  |  |  | SubTotal |  |  | 2239.2
HANDLING/ ELEC.DOC. | 080.27 | Send Comments to Design Team | [6 empty] | 080.27 | Send Comments to Design Team
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 3 | Avg. Number of Review Cycles | [6 empty] | 3 | Avg. Number of Review Cycles
|  | 62.2 | Owners Rep. Administrative Rate ($ / hour) |  |  | 279.9 |  |  |  | 62.2 | Owners Rep. Administrative Rate ($ / hour) |  | 111.96
|  |  | Mailing Cost |  |  | 148.5 |  |  |  |  | Mailing Cost |  | 0
|  |  | SubTotal |  |  |  | 428.4 |  |  |  | SubTotal |  |  | 111.96
HANDLING/ ELEC.DOC. | 080.28 | Log Transmittal of Comments | [6 empty] | 080.28 | Log Transmittal of Comments
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 3 | Avg. Number of Review Cycles | [6 empty] | 3 | Avg. Number of Review Cycles
|  | 70.7033 | Owners Rep. Administrative Rate ($ / hour) |  |  | 159.0825 |  |  |  | 70.7033 | Owners Rep. Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 159.0825 |  |  |  | SubTotal |  |  | 0
| 080.29 | Receive Review Comments | [6 empty] | 080.29 | Receive Review Comments
HANDLING/ ELEC.DOC. | 080.30 | Log Receipt of Comments | [6 empty] | 080.30 | Log Receipt of Comments
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 3 | Avg. Number of Review Cycles | [6 empty] | 3 | Avg. Number of Review Cycles
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 159.0825 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 159.0825 |  |  |  | SubTotal |  |  | 0
[6 empty] | Current Process Total | 22549.9846 | [5 empty] | Current Process Total | 5558.0755

## 090_Design_Schematic
| Process Name | Design Schematic, Product Type Template, & Product Type Candidate
| OmniClass Stage | 31-20 10 17 Schematic Design Phase
| Omniclass Role | 34-25 21 00 Architect
| Description | The Architect further devlops the approved Design Early deliverable documents to produce the Design Schematic documents. The Archtect performs a QA/QC check before submitting to the Owner. After receiving the submission, the Owner's Representative reviews and provides comments to the Architect. The Architect and Consultants are then required to update the documents based on the comments. After revisions are made the Archtect resubmits.
Information Attributes
|  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor
|  | Current process cost: | 32060.1014 | 4381.36 | 27678.7414 | 0 |  | Elec. Doc Current process cost: | 14952.6273 | 400.56 | 14552.0673 | 0 |  | COBie Current process cost: | 17107.4741 | 3980.8 | 13126.6741 | 0
|  | Expected process cost: | 5458.029 | 2030.912 | 3427.117 | 0 |  | Elec. Doc Expected process cost: | 210.2 | 40.512 | 169.688 | 0 |  | COBie Expected process cost: | 5247.829 | 1990.4 | 3257.429 | 0
|  | Process Cost Difference: | 26602.0724 | 2350.448 | 24251.6244 | 0 |  | Process Cost Difference: | 14742.4273 | 360.048 | 14382.3793 | 0 |  | Process Cost Difference: | 11859.6451 | 1990.4 | 9869.2451 | 0
Process
Reference Chapter 2 Appendix for Process Map
| Current Process | [7 empty] | Expected Process
| 090.01 | Receive Design Early Approval Document from Owner's Rep | [6 empty] | 090.01 | Receive Design Early Approval Document from Owner's Rep
RECREATING/ COBie | 090.02.10 | Produce Design Schematic Documents | [6 empty] | 090.02.10 | Produce Design Schematic Documents
|  | 18.4 | Avg. Number of Plan Drawings in Design Schematic Drawings | [6 empty] | 18.4 | Avg. Number of Plan Drawings in Design Schematic Drawings
|  | 0.083333 | Avg QTO Time for Equipment Components (hours / plan drawing) | [6 empty] | 0.033333 | Avg QTO Time for Equipment Components (hours / plan drawing)
|  | 0.16667 | Avg QTO Time for Spaces in building (hours / plan drawing) | [6 empty] | 0.066667 | Avg QTO Time for Spaces in building (hours / plan drawing)
|  | 80% | Percentage of Time Spent by Licensed Professional Architect | [6 empty] | 80% | Percentage of Time Spent by Licensed Professional Architect
|  | 20% | Percentage of Time Spent by Architect Drafter | [6 empty] | 20% | Percentage of Time Spent by Architect Drafter
|  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  |  | 404.7595 |  |  |  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  | 161.9038
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 65.0471 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 26.0188
|  |  | SubTotal |  |  |  | 469.8066 |  |  |  | SubTotal |  |  | 187.9226
REFORMATTING/COBie | 090.02.20 | Produce Outline Specification / Product Types Template | [6 empty] | 090.02.20 | Produce Outline Specification / Product Types Template
|  | 155 | Avg. Number of Equipment (product) Types (Types / project) | [6 empty] | 155 | Avg. Number of Equipment (product) Types (Types / project)
|  | 0.25 | Avg. Time Spent Developing Equipment (product) Type Template (hours / product type) | [6 empty] | 0.025 | Avg. Time Spent Developing Equipment (product) Type Template (hours / product type)
|  | 109.99 | Specifier |  |  | 4262.1125 |  |  |  | 109.99 | Specifier |  | 426.2113
|  |  | SubTotal |  |  |  | 4262.1125 |  |  |  | SubTotal |  |  | 426.2113
| 090.03 | Receive Consultant's Design Schematic Documents | [6 empty] | 090.03 | Receive Consultant's Design Schematic Documents
| 090.04 | Produce Checkset of Design Schematic Documents | [6 empty] | 090.04 | Produce Checkset of Design Schematic Documents
VALIDATING/ COBie | 090.05 | Validate Checkset before Submission through manual QA/QC Process | [6 empty] | 090.05 | Validate Checkset before Submission through manual QA/QC Process
|  | 41 | Avg. Time Spent Evaluating Design Schematic Drawings against Design Requirements - Space and Equipment | [6 empty] | 20.5 | Avg. Time Spent Evaluating Design Schematic Drawings against Design Requirements - Space and Equipment
|  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  |  | 4509.549 |  |  |  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  | 2254.7745
|  |  | SubTotal |  |  |  | 4509.549 |  |  |  | SubTotal |  |  | 2254.7745
| 090.06.10 | Make Corrections (Architect and/or Consultants) | [6 empty] | 090.06.10 | Make Corrections (Architect and/or Consultants)
COPYING/ ELEC.DOC. | 090.06.20 | Copy Design Schematic Documents | [6 empty] | 090.06.20 | Copy Design Schematic Documents
|  | 167 | Avg. Number of Sheets in Design Schematic Drawings | [6 empty] | 167 | Avg. Number of Sheets in Design Schematic Drawings
|  | 60 | Avg. Number of Letter Sized Pages in Design Schematic Narrative | [6 empty] | 60 | Avg. Number of Letter Sized Pages in Design Schematic Narrative
|  | 10 | Avg. Number of Letter Sized Pages in a Design Schematic Specification | [6 empty] | 10 | Avg. Number of Letter Sized Pages in a Design Schematic Specification
|  | 6 | Number of Design Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Number of Design Submittal Sets Reqd. (sets / submittal)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 3 | Avg. Per Sheet Copy Cost ($ / sheet) | [6 empty] | 0 | Avg. Per Sheet Copy Cost ($ / sheet)
|  | 0.504 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 213.8069 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | Copying Cost |  |  | 3069 |  |  |  |  | Copying Cost |  | 0
|  |  | SubTotal |  |  |  | 3282.8069 |  |  |  | SubTotal |  |  | 0
HANDLING/ ELEC.DOC. | 090.06.30 | Send Copies of Design Schematic Documents | [6 empty] | 090.06.30 | Send Copies of Design Schematic Documents
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 47.7 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 106.055 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 42.422
|  |  | Mailing Cost |  |  | 143.1 |  |  |  |  | Mailing Cost |  | 0
|  |  | SubTotal |  |  |  | 249.155 |  |  |  | SubTotal |  |  | 42.422
HANDLING/ ELEC.DOC. | 090.06.40 | Log Transmittal of Design Schematic Documents | [6 empty] | 090.06.40 | Log Transmittal of Design Schematic Documents
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 53.0275 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 53.0275 |  |  |  | SubTotal |  |  | 0
| 090.07 | Receive Design Schematic & Product Type Template | [6 empty] | 090.07 | Receive Design Schematic & Product Type Template
HANDLING/ ELEC.DOC. | 090.08 | Log Receipt of Design Schematic & Product Type Template Documents | [6 empty] | 090.08 | Log Receipt of Design Schematic & Product Type Template Documents
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 12.66 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 12.66 |  |  |  | SubTotal |  |  | 0
VALIDATING/ COBie | 090.09 | Validate Design Schematic & Product Type Template Documents | [6 empty] | 090.09 | Validate Design Schematic & Product Type Template Documents
|  | 16 | Avg Time to Compare Design Schematic Documents with Owner Standards | [6 empty] | 8 | Avg Time to Compare Design Schematic Documents with Owner Standards
|  | 62.2 | Owners Rep. Rate ($ / hour) |  |  | 995.2 |  |  |  | 62.2 | Owners Rep. Rate ($ / hour) |  | 497.6
|  |  | SubTotal |  |  |  | 995.2 |  |  |  | SubTotal |  |  | 497.6
HANDLING/ ELEC.DOC. | 090.10.20 | Send Comments to Design Team | [6 empty] | 090.10.20 | Send Comments to Design Team
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 25.32 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  | 10.128
|  |  | Mailing Cost |  |  | 49.5 |  |  |  |  | Mailing Cost |  | 0
|  |  | SubTotal |  |  |  | 74.82 |  |  |  | SubTotal |  |  | 10.128
HANDLING/ ELEC.DOC. | 090.10.30 | Log Transmittal of Comments | [6 empty] | 090.10.30 | Log Transmittal of Comments
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 12.66 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 12.66 |  |  |  | SubTotal |  |  | 0
| 090.11 | Receive Review Comments | [6 empty] | 090.11 | Receive Review Comments
HANDLING/ ELEC.DOC. | 090.12 | Log Receipt of Comments | [6 empty] | 090.12 | Log Receipt of Comments
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 53.0275 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 53.0275 |  |  |  | SubTotal |  |  | 0
RECREATING/ COBie | 090.13 | Make Corrections (Architect and/or Consultants) | [6 empty] | 090.13 | Make Corrections (Architect and/or Consultants)
|  | 11.7745 | Avg. Time spent making corrections due to non-conformance with Space or Product Program | [6 empty] | 1.1775 | Avg. Time spent making corrections due to non-conformance with Space or Product Program
|  | 3 | Avg. Number of Review Cycles | [6 empty] | 3 | Avg. Number of Review Cycles
|  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  |  | 3885.206 |  |  |  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  | 388.5206
[7 empty] | 3885.206 | [6 empty] | 388.5206
COPYING/ ELEC.DOC. | 090.14 | Copy Revised Design Schematic Documents | [6 empty] | 090.14 | Copy Revised Design Schematic Documents
|  | 167 | Avg. Number of Sheets in Design Schematic Drawings | [6 empty] | 167 | Avg. Number of Sheets in Design Schematic Drawings
|  | 60 | Avg. Number of Letter Sized Pages in Design Schematic Narrative | [6 empty] | 60 | Avg. Number of Letter Sized Pages in Design Schematic Narrative
|  | 10 | Avg. Number of Letter Sized Pages in a Design Schematic Specification | [6 empty] | 10 | Avg. Number of Letter Sized Pages in a Design Schematic Specification
|  | 6 | Number of Design Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Number of Design Submittal Sets Reqd. (sets / submittal)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 3 | Avg. Per Sheet Copy Cost ($ / sheet) | [6 empty] | 0 | Avg. Per Sheet Copy Cost ($ / sheet)
|  | 0.504 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 3 | Avg. Number of Review Cycles | [6 empty] | 3 | Avg. Number of Review Cycles
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 641.4206 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | Copying Cost |  |  | 9207 |  |  |  |  | Copying Cost |  | 0
|  |  | SubTotal |  |  |  | 9848.4206 |  |  |  | SubTotal |  |  | 0
HANDLING/ ELEC.DOC. | 090.15 | Send Revised Design Schematic Documents | [6 empty] | 090.15 | Send Revised Design Schematic Documents
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 47.7 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 3 | Avg. Number of Review Cycles | [6 empty] | 3 | Avg. Number of Review Cycles
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 318.165 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 127.266
|  |  | Mailing Cost |  |  | 429.3 |  |  |  |  | Mailing Cost |  | 0
|  |  | SubTotal |  |  |  | 747.465 |  |  |  | SubTotal |  |  | 127.266
HANDLING/ ELEC.DOC. | 090.16 | Log Transmittal of Revised Design Schematic Documents | [6 empty] | 090.16 | Log Transmittal of Revised Design Schematic Documents
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 3 | Avg. Number of Review Cycles | [6 empty] | 3 | Avg. Number of Review Cycles
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 159.0825 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 159.0825 |  |  |  | SubTotal |  |  | 0
| 090.17 | Receive Design Early Documents | [6 empty] | 090.17 | Receive Design Early Documents
HANDLING/ ELEC.DOC. | 090.18 | Log Receipt of Revised Design Schematic Documents | [6 empty] | 090.18 | Log Receipt of Revised Design Schematic Documents
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 3 | Avg. Number of Review Cycles | [6 empty] | 3 | Avg. Number of Review Cycles
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 37.98 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 37.98 |  |  |  | SubTotal |  |  | 0
VALIDATING/ COBie | 090.19 | Validate Revised Design Schematic Documents | [6 empty] | 090.19 | Validate Revised Design Schematic Documents
|  | 16 | Avg Time to Compare Design Schematic Documents with Owner Standards | [6 empty] | 8 | Avg Time to Compare Design Schematic Documents with Owner Standards
|  | 3 | Avg. Number of Review Cycles | [6 empty] | 3 | Avg. Number of Review Cycles
|  | 62.2 | Owners Rep. Rate ($ / hour) |  |  | 2985.6 |  |  |  | 62.2 | Owners Rep. Rate ($ / hour) |  | 1492.8
|  |  | SubTotal |  |  |  | 2985.6 |  |  |  | SubTotal |  |  | 1492.8
HANDLING/ ELEC.DOC. | 090.20 | Send Comments to Design Team | [6 empty] | 090.20 | Send Comments to Design Team
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 3 | Avg. Number of Review Cycles | [6 empty] | 3 | Avg. Number of Review Cycles
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 75.96 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  | 30.384
|  |  | Mailing Cost |  |  | 148.5 |  |  |  |  | Mailing Cost |  | 0
|  |  | SubTotal |  |  |  | 224.46 |  |  |  | SubTotal |  |  | 30.384
HANDLING/ ELEC.DOC. | 090.21 | Log Transmittal of Comments | [6 empty] | 090.21 | Log Transmittal of Comments
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 3 | Avg. Number of Review Cycles | [6 empty] | 3 | Avg. Number of Review Cycles
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 37.98 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 37.98 |  |  |  | SubTotal |  |  | 0
| 090.22 | Receive Review Comments | [6 empty] | 090.22 | Receive Review Comments
HANDLING/ ELEC.DOC. | 090.23 | Log Receipt of Comments | [6 empty] | 090.23 | Log Receipt of Comments
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 3 | Avg. Number of Review Cycles | [6 empty] | 3 | Avg. Number of Review Cycles
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 159.0825 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 159.0825 |  |  |  | SubTotal |  |  | 0
[6 empty] | Current Process Total | 32060.1014 | [5 empty] | Current Process Total | 5458.029
Note on C48: Naila Crawford: Add - for the production of the specification or some of the assets in the COBie format
Note on L48: Naila Crawford: Add - for the production of the specification or some of the assets in the COBie format
Note on C56: Naila Crawford: add for COBie
Note on L56: Naila Crawford: add for COBie
Note on C102: Naila Crawford: Add back costs
Note on L102: Naila Crawford: Add back costs

## 100_Design_Coordinated_PTT_PTC
| Process Name | Design Coordinated & Product Type Candidate
| OmniClass Stage | 31-20 20 11 Detailed Design Phase
| Omniclass Role | 34-25 21 00 Architect
| Description | The Architect further develops the approved Design Schematic deliverable documents to produce the Design Coordinated documents. In addition, the building systems are coordinated to eliminate spatial interferences. This is a major coordination submittal before the final delivery package. The Architect performs a QA/QC check before distributing to the Owner's Representative. After receiving the submission, the Owner's Representative reviews and provides comments to the Architect. The Architect and Consultants are then required to update the documents based on the comments. After revisions are made, the Architect resubmits.
Information Attributes
|  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor
|  | Current process cost: | 94324.5317 | 4381.36 | 89943.1717 | 0 |  | Elec. Doc Current process cost: | 29363.9595 | 400.56 | 28963.3995 | 0 |  | COBie Current process cost: | 64960.5722 | 3980.8 | 60979.7722 | 0
|  | Expected process cost: | 9754.6939 | 1533.312 | 8221.3819 | 0 |  | Elec. Doc Expected process cost: | 210.2 | 40.512 | 169.688 | 0 |  | COBie Expected process cost: | 9544.494 | 1492.8 | 8051.694 | 0
|  | Process Cost Difference: | 84569.8377 | 2848.048 | 81721.7897 | 0 |  | Process Cost Difference: | 29153.7595 | 360.048 | 28793.7115 | 0 |  | Process Cost Difference: | 55416.0782 | 2488 | 52928.0782 | 0
Process
Reference Chapter 2 Appendix for Process Map
| Current Process | [7 empty] | Expected Process
| 100.01 | Receive Design Schematic Approval Document from Owner | [6 empty] | 100.01 | Receive Design Schematic Approval Document from Owner
RECREATING/ COBie | 100.02.10 | Produce Design Coordinated Documents | [6 empty] | 100.02.10 | Produce Design Coordinated Documents
|  | 36.8 | Avg. Number of Plan Drawings in Design Coordinated Drawings | [6 empty] | 36.8 | Avg. Number of Plan Drawings in Design Coordinated Drawings
|  | 0.083333 | Avg QTO Time for Equipment Components (hours / plan drawing) | [6 empty] | 0.033333 | Avg QTO Time for Equipment Components (hours / plan drawing)
|  | 0.16667 | Avg QTO Time for Spaces in building (hours / plan drawing) | [6 empty] | 0.066667 | Avg QTO Time for Spaces in building (hours / plan drawing)
|  | 80% | Percentage of Time Spent by Licensed Professional Architect | [6 empty] | 80% | Percentage of Time Spent by Licensed Professional Architect
|  | 20% | Percentage of Time Spent by Architect Drafter | [6 empty] | 20% | Percentage of Time Spent by Architect Drafter
|  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  |  | 809.519 |  |  |  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  | 323.8076
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 130.0941 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 52.0376
|  |  | SubTotal |  |  |  | 939.6132 |  |  |  | SubTotal |  |  | 375.8453
REFORMATTING/ COBie | 100.02.20 | Produce Detailed Specification / Product Type Template | [6 empty] | 100.02.20 | Produce Detailed Specification / Product Type Template
|  | 155 | Avg. Number of Equipment (product) Types (Types / project) | [6 empty] | 155 | Avg. Number of Equipment (product) Types (Types / project)
|  | 2 | Avg. Time Spent Developing Detailed Equipment (products) Type Template (hours / product) | [6 empty] | 0.2 | Avg. Time Spent Developing Detailed Equipment (products) Type Template (hours / product)
|  | 109.989 | Specifier |  |  | 34096.59 |  |  |  | 109.989 | Specifier |  | 3409.659
|  |  | SubTotal |  |  |  | 34096.59 |  |  |  | SubTotal |  |  | 3409.659
SEARCHING/ COBie | 100.03 | Search for Product Type Candidates | [6 empty] | 100.03 | Search for Product Type Candidates
|  | 155 | Avg. Number of Equipment (product) Types (Types / project) | [6 empty] | 155 | Avg. Number of Equipment (product) Types (Types / project)
|  | 1 | Avg. Time Searching for Product Literature for Candidates (Hours/product) | [6 empty] | 0.1 | Avg. Time Searching for Product Literature for Candidates (Hours/product)
|  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  |  | 17048.295 |  |  |  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  | 1704.8295
|  |  | SubTotal |  |  |  | 17048.295 |  |  |  | SubTotal |  |  | 1704.8295
| 100.04 | Receive Consultant's Design Coordinated Documents | [6 empty] | 100.04 | Receive Consultant's Design Coordinated Documents
| 100.05 | Produce Checkset of Design Coordinated Documents | [6 empty] | 100.05 | Produce Checkset of Design Coordinated Documents
VALIDATING/ COBie | 100.06 | Validate Checkset before Submission through manual QA/QC Process | [6 empty] | 100.06 | Validate Checkset before Submission through manual QA/QC Process
|  | 38 | Avg. Time Spent Evaluating Design Coordinated Drawings against Design Requirements - Space and Equipment | [6 empty] | 19 | Avg. Time Spent Evaluating Design Coordinated Drawings against Design Requirements - Space and Equipment
|  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  |  | 4179.582 |  |  |  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  | 2089.791
|  |  | SubTotal |  |  |  | 4179.582 |  |  |  | SubTotal |  |  | 2089.791
SEARCHING & RECREATING/ COBie | 100.07.10 | Re- Search and Recreate Product Type Candidates and Detailed Specifications based on QA/QC Results | [6 empty] | 100.07.10 | Re- Search and Recreate Product Type Candidates and Detailed Specifications based on QA/QC Results
|  | 15% | Avg. Percent of Errors in Product Type Candidate | [6 empty] | 15% | Avg. Percent of Errors in Product Type Candidate
|  | 155 | Avg. Number of Equipment (product) Types (Types / project) | [6 empty] | 155 | Avg. Number of Equipment (product) Types (Types / project)
|  | 1 | Avg. Time Searching for Product Literature for Candidates (Hours/product) | [6 empty] | 0.1 | Avg. Time Searching for Product Literature for Candidates (Hours/product)
|  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  |  | 2557.2443 |  |  |  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  | 255.7244
|  |  | SubTotal |  |  |  | 2557.2443 |  |  |  | SubTotal |  |  | 255.7244
COPYING/ ELEC.DOC. | 100.07.20 | Copy Design Coordinated Documents | [6 empty] | 100.07.20 | Copy Design Coordinated Documents
|  | 218 | Avg. Number of Sheets in Design Coordinated Drawings | [6 empty] | 218 | Avg. Number of Sheets in Design Coordinated Drawings
|  | 60 | Avg. Number of Letter Sized Pages in a Design Coordinated Narrative | [6 empty] | 60 | Avg. Number of Letter Sized Pages in a Design Coordinated Narrative
|  | 2156 | Avg. Number of Letter Sized Pages in a Design Coordinated Specification | [6 empty] | 2156 | Avg. Number of Letter Sized Pages in a Design Coordinated Specification
|  | 6 | Number of Design Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Number of Design Submittal Sets Reqd. (sets / submittal)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 3 | Avg. Per Sheet Copy Cost ($ / sheet) | [6 empty] | 0 | Avg. Per Sheet Copy Cost ($ / sheet)
|  | 2 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 848.4399 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | Copying Cost |  |  | 5918.4 |  |  |  |  | Copying Cost |  | 0
|  |  | SubTotal |  |  |  | 6766.8399 |  |  |  | SubTotal |  |  | 0
HANDLING/ ELEC.DOC. | 100.07.30 | Send Design Coordinated Documents | [6 empty] | 100.07.30 | Send Design Coordinated Documents
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 87.3 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 106.055 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 42.422
|  |  | Mailing Cost |  |  | 261.9 |  |  |  |  | Mailing Cost |  | 0
|  |  | SubTotal |  |  |  | 367.955 |  |  |  | SubTotal |  |  | 42.422
HANDLING/ ELEC.DOC. | 100.07.40 | Log Transmittal of Design Coordinated Documents | [6 empty] | 100.07.40 | Log Transmittal of Design Coordinated Documents
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 53.0275 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 53.0275 |  |  |  | SubTotal |  |  | 0
| 100.08 | Receive Design Coordinated & Product Type Candidate Documents | [6 empty] | 100.08 | Receive Design Coordinated & Product Type Candidate Documents
HANDLING/ ELEC.DOC. | 100.09 | Log Receipt of Design Coordinated & Product Type Candidate Documents | [6 empty] | 100.09 | Log Receipt of Design Coordinated & Product Type Candidate Documents
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 12.66 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 12.66 |  |  |  | SubTotal |  |  | 0
VALIDATING/ COBie | 100.1 | Validate Design Coordinated & Product Type Candidate Documents | [6 empty] | 100.1 | Validate Design Coordinated & Product Type Candidate Documents
|  | 16 | Avg Time to Compare Design Coordinated & Product Type Candidate Documents with Owner Standards | [6 empty] | 0 | Avg Time to Compare Design Coordinated & Product Type Candidate Documents with Owner Standards
|  | 62.2 | Owners Rep. Rate ($ / hour) |  |  | 995.2 |  |  |  | 62.2 | Owners Rep. Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 995.2 |  |  |  | SubTotal |  |  | 0
HANDLING/ ELEC.DOC. | 100.11.20 | Send Comments to Design Team | [6 empty] | 100.11.20 | Send Comments to Design Team
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 25.32 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  | 10.128
|  |  | Mailing Costs |  |  | 49.5 |  |  |  |  | Mailing Costs |  | 0
|  |  | SubTotal |  |  |  | 74.82 |  |  |  | SubTotal |  |  | 10.128
HANDLING/ ELEC.DOC. | 100.11.30 | Log Transmittal of Comments | [6 empty] | 100.11.30 | Log Transmittal of Comments
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 12.66 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 12.66 |  |  |  | SubTotal |  |  | 0
| 100.12 | Receive Review Comments | [6 empty] | 100.12 | Receive Review Comments
HANDLING/ ELEC.DOC. | 100.13 | Log Receipt of Comments | [6 empty] | 100.13 | Log Receipt of Comments
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 53.0275 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 53.0275 |  |  |  | SubTotal |  |  | 0
RECREATING/ COBie | 100.14 | Make Corrections (Architect and/or Consultants) | [6 empty] | 100.14 | Make Corrections (Architect and/or Consultants)
|  | 6.5414 | Avg. Time Spent making Corrections due to Non-Conformance with Space or Product Program | [6 empty] | 0.65414 | Avg. Time Spent making Corrections due to Non-Conformance with Space or Product Program
|  | 3 | Avg. Number of Review Cycles | [6 empty] | 3 | Avg. Number of Review Cycles
|  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  |  | 2158.4478 |  |  |  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  | 215.8448
[7 empty] | 2158.4478 | [6 empty] | 215.8448
COPYING/ ELEC.DOC. | 100.15 | Copy Revised Design Coordinated & Product Type Candidate Documents | [6 empty] | 100.15 | Copy Revised Design Coordinated & Product Type Candidate Documents
|  | 218 | Avg. Number of Sheets in Design Coordinated Drawings | [6 empty] | 218 | Avg. Number of Sheets in Design Coordinated Drawings
|  | 60 | Avg. Number of Letter Sized Pages in a Design Coordinated Narrative | [6 empty] | 60 | Avg. Number of Letter Sized Pages in a Design Coordinated Narrative
|  | 2156 | Avg. Number of Letter Sized Pages in a Design Coordinated Specification | [6 empty] | 2156 | Avg. Number of Letter Sized Pages in a Design Coordinated Specification
|  | 6 | Number of Design Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Number of Design Submittal Sets Reqd. (sets / submittal)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 3 | Avg. Per Sheet Copy Cost ($ / sheet) | [6 empty] | 0 | Avg. Per Sheet Copy Cost ($ / sheet)
|  | 2 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 3 | Avg. Number of Review Cycles | [6 empty] | 3 | Avg. Number of Review Cycles
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 2545.3197 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | Copying Cost |  |  | 17755.2 |  |  |  |  | Copying Cost |  | 0
|  |  | SubTotal |  |  |  | 20300.5197 |  |  |  | SubTotal |  |  | 0
HANDLING/ ELEC.DOC. | 100.16 | Send Revised Design Coordinated & Product Type Candidate Documents | [6 empty] | 100.16 | Send Revised Design Coordinated & Product Type Candidate Documents
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 87.3 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 3 | Avg. Number of Review Cycles | [6 empty] | 3 | Avg. Number of Review Cycles
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 318.165 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 127.266
|  |  | Mailing Cost |  |  | 785.7 |  |  |  |  | Mailing Cost |  | 0
|  |  | SubTotal |  |  |  | 1103.865 |  |  |  | SubTotal |  |  | 127.266
HANDLING/ ELEC.DOC. | 100.17 | Log Transmittal of Revised Design Coordinated & Product Type Candidate Documents | [6 empty] | 100.17 | Log Transmittal of Revised Design Coordinated & Product Type Candidate Documents
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 3 | Avg. Number of Review Cycles | [6 empty] | 3 | Avg. Number of Review Cycles
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 159.0825 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 159.0825 |  |  |  | SubTotal |  |  | 0
| 100.18 | Receive Design Early Documents | [6 empty] | 100.18 | Receive Design Early Documents
HANDLING/ ELEC.DOC. | 100.19 | Log Receipt of Revised Design Coordinated & Product Type Candidate Documents | [6 empty] | 100.19 | Log Receipt of Revised Design Coordinated & Product Type Candidate Documents
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 3 | Avg. Number of Review Cycles | [6 empty] | 3 | Avg. Number of Review Cycles
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 37.98 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 37.98 |  |  |  | SubTotal |  |  | 0
VALIDATING/ COBie | 100.20 | Validate Revised Design Coordinated & Product Type Candidate Documents | [6 empty] | 100.20 | Validate Revised Design Coordinated & Product Type Candidate Documents
|  | 16 | Avg Time to Compare Design Coordinated & Product Type Candidate Documents with Owner Standards | [6 empty] | 8 | Avg Time to Compare Design Coordinated & Product Type Candidate Documents with Owner Standards
|  | 3 | Avg. Number of Review Cycles | [6 empty] | 3 | Avg. Number of Review Cycles
|  | 62.2 | Owners Rep. Rate ($ / hour) |  |  | 2985.6 |  |  |  | 62.2 | Owners Rep. Rate ($ / hour) |  | 1492.8
|  |  | SubTotal |  |  |  | 2985.6 |  |  |  | SubTotal |  |  | 1492.8
HANDLING/ ELEC.DOC. | 100.21 | Send Comments to Design Team | [6 empty] | 100.21 | Send Comments to Design Team
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 3 | Avg. Number of Review Cycles | [6 empty] | 3 | Avg. Number of Review Cycles
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 75.96 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  | 30.384
|  |  | Mailing Cost |  |  | 148.5 |  |  |  |  | Mailing Cost |  | 0
|  |  | SubTotal |  |  |  | 224.46 |  |  |  | SubTotal |  |  | 30.384
HANDLING/ ELEC.DOC. | 100.22 | Log Transmittal of Comments | [6 empty] | 100.22 | Log Transmittal of Comments
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 3 | Avg. Number of Review Cycles | [6 empty] | 3 | Avg. Number of Review Cycles
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 37.98 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 37.98 |  |  |  | SubTotal |  |  | 0
| 100.23 | Receive Review Comments | [6 empty] | 100.23 | Receive Review Comments
HANDLING/ ELEC.DOC. | 100.24 | Log Receipt of Comments | [6 empty] | 100.24 | Log Receipt of Comments
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 3 | Avg. Number of Review Cycles | [6 empty] | 3 | Avg. Number of Review Cycles
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 159.0825 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 159.0825 |  |  |  | SubTotal |  |  | 0
[6 empty] | Current Process Total | 94324.5317 | [5 empty] | Current Process Total | 9754.6939

## 110_Design_Final
| Process Name | Design Final & Product Type Template
| OmniClass Stage | 31-20 20 24 Product Selection Phase
31-20 20 27 Material Selection Phase
31-20 20 31 Equipment Selection Phase
| Omniclass Role | 34-25 41 00 Specifier
| Description | The Design Final package is the final set of contract documents ready for bid solicitation by the Government. This final design deliverable does not require another review by the Owner's Representative.
Information Attributes
|  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor |  |  |  |  | Owner | Architect | Contractor
|  | Current process cost: | 30286.1055 | 4.22 | 30281.8855 | 0 |  | Elec. Doc Current process cost: | 8868.705 | 4.22 | 8864.485 | 0 |  |  | COBie Current process cost: | 21417.4004 | 0 | 21417.4004 | 0
|  | Expected process cost: | 3612.7398 | 0 | 3612.7398 | 0 |  | Elec. Doc Expected process cost: | 28.2813 | 0 | 28.2813 | 0 |  |  | COBie Expected process cost: | 3584.4585 | 0 | 3584.4585 | 0
|  | Process Cost Difference: | 26673.3657 | 4.22 | 26669.1457 | 0 |  | Process Cost Difference: | 8840.4237 | 4.22 | 8836.2037 | 0 |  |  | Process Cost Difference: | 17832.942 | 0 | 17832.942 | 0
Process
Reference Chapter 2 Appendix for Process Map
| Current Process | [6 empty] | Expected Process
| 110.01 | Receive Design Coordinated Documents Approval from Owner | [5 empty] | 110.01 | Receive Design Coordinated Documents Approval from Owner
RECREATING/ COBie | 110.02.10 | Produce Design Final Documents | [5 empty] | 110.02.10 | Produce Design Final Documents
|  | 115 | Avg. Number of Plan Drawings in Design Final Drawings | [5 empty] | 115 | Avg. Number of Plan Drawings in Design Final Drawings
|  | 0.083333 | Avg QTO Time for Equipment Components (hours / plan drawing) | [5 empty] | 0.033333 | Avg QTO Time for Equipment Components (hours / plan drawing)
|  | 0.16667 | Avg QTO Time for Spaces in building (hours / plan drawing) | [5 empty] | 0.066667 | Avg QTO Time for Spaces in building (hours / plan drawing)
|  | 90% | Percentage of Time Spent by Licensed Professional Architect | [5 empty] | 90% | Percentage of Time Spent by Licensed Professional Architect
|  | 10% | Percentage of Time Spent by Architect Drafter | [5 empty] | 10% | Percentage of Time Spent by Architect Drafter
|  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  |  | 2845.9654 |  |  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  |  | 1138.3862
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 203.2721 |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 81.3088
|  |  | SubTotal |  |  |  | 3049.2374 |  |  | SubTotal |  |  |  | 1219.695
REFORMATTING/ COBie | 110.02.20 | Produce Detailed Specification / Product Type Candidates | [5 empty] | 110.02.20 | Produce Detailed Specification / Product Type Candidates
|  | 155 | Avg. Number of Equipment (product) Types (Types / project) | [5 empty] | 155 | Avg. Number of Equipment (product) Types (Types / project)
|  | 1 | Avg. Time Spent Developing Detailed Equipment (products) Type Candidate (hours / product) | [5 empty] | 0.1 | Avg. Time Spent Developing Detailed Equipment (products) Type Candidate (hours / product)
|  | 109.989 | Specifier |  |  | 17048.295 |  |  | 109.989 | Specifier |  |  | 1704.8295
|  |  | SubTotal |  |  |  | 17048.295 |  |  | SubTotal |  |  |  | 1704.8295
| 110.03 | Receive Consultant's Design Final Documents | [5 empty] | 110.03 | Receive Consultant's Design Final Documents
| 110.04 | Produce Check Set of Design Final Documents | [5 empty] | 110.04 | Produce Check Set of Design Final Documents
VALIDATING/ COBie | 110.05 | Validate Checkset before Submission through manual QA/QC Process | [5 empty] | 110.05 | Validate Checkset before Submission through manual QA/QC Process
|  | 12 | Avg. Time Spent Evaluating Design Final Drawings against Design Requirements - Space and Equipment | [5 empty] | 6 | Avg. Time Spent Evaluating Design Final Drawings against Design Requirements - Space and Equipment
|  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  |  | 1319.868 |  |  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  |  | 659.934
|  |  | SubTotal |  |  |  | 1319.868 |  |  | SubTotal |  |  |  | 659.934
| 110.06.10 | Make Corrections | [5 empty] | 110.06.10 | Make Corrections
COPYING/ ELEC.DOC. | 110.06.20 | Copy Design Final Documents | [5 empty] | 110.06.20 | Copy Design Final Documents
|  | 316 | Avg. Number of Sheets in Design Final Drawings | [5 empty] | 316 | Avg. Number of Sheets in Design Final Drawings
|  | 60 | Avg. Number of Letter Sized 'Pages in Design Final Narrative | [5 empty] | 60 | Avg. Number of Letter Sized 'Pages in Design Final Narrative
|  | 2156 | Avg. Number of Letter Sized Pages in Design Final Specification | [5 empty] | 2156 | Avg. Number of Letter Sized Pages in Design Final Specification
|  | 6 | Number of Design Submittal Sets Reqd. (sets / submittal) | [5 empty] | 0 | Number of Design Submittal Sets Reqd. (sets / submittal)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [5 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 3 | Avg. Per Sheet Copy Cost ($ / sheet) | [5 empty] | 0 | Avg. Per Sheet Copy Cost ($ / sheet)
|  | 2.3 | Avg. In-house Reproduction Time Per Set (hours/set) | [5 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 975.7059 |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 0
|  |  | Copying Cost |  |  | 7682.4 |  |  |  | Copying Cost |  |  | 0
|  |  | SubTotal |  |  |  | 8658.1059 |  |  | SubTotal |  |  |  | 0
HANDLING/ ELEC.DOC. | 110.06.30 | Send Design Final Documents | [5 empty] | 110.06.30 | Send Design Final Documents
|  | 1 | Avg. Number of Transmittals (Transmittals) | [5 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 118 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [5 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 1 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [5 empty] | 0.4 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 70.7033 |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 28.2813
|  |  | Mailing Cost |  |  | 118 |  |  |  | Mailing Cost |  |  | 0
|  |  | SubTotal |  |  |  | 188.7033 |  |  | SubTotal |  |  |  | 28.2813
HANDLING/ ELEC.DOC. | 110.06.40 | Log Transmittal of Design Final Documents | [5 empty] | 110.06.40 | Log Transmittal of Design Final Documents
|  | 1 | Avg. Number of Transmittals (Transmittals) | [5 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [5 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 17.6758 |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 0
|  |  | SubTotal |  |  |  | 17.6758 |  |  | SubTotal |  |  |  | 0
| 110.07 | Receive Design Final and Product Type Candidate Documents | [5 empty] | 110.07 | Receive Design Final and Product Type Candidate Documents
HANDLING/ ELEC.DOC. | 110.08 | Log Receipt of Design Final Documents for Bidding Process | [5 empty] | 110.08 | Log Receipt of Design Final Documents for Bidding Process
|  | 1 | Avg. Number of Transmittals (Transmittals) | [5 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [5 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 4.22 |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 0
|  |  | SubTotal |  |  |  | 4.22 |  |  | SubTotal |  |  |  | 0
| 110.09 | Produce Design Final Documents for Bidding Process | [5 empty] | 110.09 | Produce Design Final Documents for Bidding Process
[6 empty] | Current Process Total | 30286.1055 | [5 empty] | Current Process Total | 3612.7398

## 120_Request_For_Proposal
| Process Name | Request For Proposal
| OmniClass Stage | 31-20 20 24 Product Selection Phase
31-20 20 27 Material Selection Phase
31-20 20 31 Equipment Selection Phase
| Omniclass Role | 34-25 41 00 Specifier
| Description | Once the design is complete, the Owner packages the Design Final Documents information together with the owner-supplied information (e.g., contractual terms) and creates a Request for Proposals (RFP). This becomes the official bid set.
Information Attributes
|  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor |  |  |  |  | Owner | Architect | Contractor
|  | Current process cost: | 1993.7568 | 1993.7568 | 0 | 0 |  | Elec. Doc Current process cost: | 1993.7568 | 1993.7568 | 0 | 0 |  |  | COBie Current process cost: | 0 | 0 | 0 | 0
|  | Expected process cost: | 63.3 | 63.3 | 0 | 0 |  | Elec. Doc Expected process cost: | 63.3 | 63.3 | 0 | 0 |  |  | COBie Expected process cost: | 0 | 0 | 0 | 0
|  | Process Cost Difference: | 1930.4568 | 1930.4568 | 0 | 0 |  | Process Cost Difference: | 1930.4568 | 1930.4568 | 0 | 0 |  |  | Process Cost Difference: | 0 | 0 | 0 | 0
Process
Reference Chapter 2 Appendix for Process Map
| Current Process | [6 empty] | Expected Process
HANDLING/ ELEC.DOC. | 120.01 | Receive Information from A/E to Develop Bid Documents | [5 empty] | 120.01 | Receive Information from A/E to Develop Bid Documents
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [5 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 4.22 |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 0
|  |  | SubTotal |  |  |  | 4.22 |  |  | SubTotal |  |  |  | 0
| 120.02 | Produce RFP Front Matter | [5 empty] | 120.02 | Produce RFP Front Matter
COPYING/ ELEC.DOC. | 120.03 | Copy Request for Proposal (RFP) Package | [5 empty] | 120.03 | Copy Request for Proposal (RFP) Package
|  | 50 | Avg. Number of Pages in Front Matter | [5 empty] | 50 | Avg. Number of Pages in Front Matter
|  | 316 | Avg. Number of Sheets in Design Final Drawings | [5 empty] | 316 | Avg. Number of Sheets in Design Final Drawings
|  | 60 | Avg. Number of Letter Sized 'Pages in Design Final Narrative | [5 empty] | 60 | Avg. Number of Letter Sized 'Pages in Design Final Narrative
|  | 2156 | Avg. Number of Letter Sized Pages in Design Final Specification | [5 empty] | 2156 | Avg. Number of Letter Sized Pages in Design Final Specification
|  | 1 | Avg. Number of Request for Proposal Submittal Sets Reqd. | [5 empty] | 0 | Avg. Number of Request for Proposal Submittal Sets Reqd.
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [5 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 3 | Avg. Per Sheet Copy Cost ($ / sheet) | [5 empty] | 0 | Avg. Per Sheet Copy Cost ($ / sheet)
|  | 2.36 | Avg. In-house Reproduction Time Per Set (hours/set) | [5 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 39.8368 |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 0
|  |  | Copying Cost |  |  | 1287.9 |  |  |  | Copying Cost |  |  | 0
|  |  | SubTotal |  |  |  | 1327.7368 |  |  | SubTotal |  |  |  | 0
HANDLING/ ELEC.DOC. | 120.04 | Send Request for Proposal (RFP) Package | [5 empty] | 120.04 | Send Request for Proposal (RFP) Package
|  | 5 | Avg. Number of Transmittals (Transmittals) | [5 empty] | 5 | Avg. Number of Transmittals (Transmittals)
|  | 119.7 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [5 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.75 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [5 empty] | 0.75 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 63.3 |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 63.3
|  |  | Mailing Cost |  |  | 598.5 |  |  |  | Mailing Cost |  |  | 0
|  |  | SubTotal |  |  |  | 661.8 |  |  | SubTotal |  |  |  | 63.3
| 120.05 | Receive RFP Package | [5 empty] | 120.05 | Receive RFP Package
[6 empty] | Current Process Total | 1993.7568 | [5 empty] | Current Process Total | 63.3

## 130_Inquiry_Issue
| Process Name | Inquiry Issue (Clarification)
| OmniClass Stage | 31-20 20 24 Product Selection Phase
31-20 20 27 Material Selection Phase
31-20 20 31 Equipment Selection Phase
| Omniclass Role | 34-25 41 00 Specifier
| Description | Before finalizing a bid proposal, the Contractor typically request additional information or clarification of some bid documents.
Information Attributes
|  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor |  |  |  |  | Owner | Architect | Contractor
|  | Current process cost: | 1206.7984 | 145.3862 | 243.9341 | 817.478 |  | Elec. Doc Current process cost: | 1206.7984 | 145.3862 | 243.9341 | 817.478 |  |  | COBie Current process cost: | 0 | 0 | 0 | 0
|  | Expected process cost: | 26.3408 | 3.3625 | 14.1407 | 8.8376 |  | Elec. Doc Expected process cost: | 26.3408 | 3.3625 | 14.1407 | 8.8376 |  |  | COBie Expected process cost: | 0 | 0 | 0 | 0
|  | Process Cost Difference: | 1180.4576 | 142.0237 | 229.7935 | 808.6404 |  | Process Cost Difference: | 1180.4576 | 142.0237 | 229.7935 | 808.6404 |  |  | Process Cost Difference: | 0 | 0 | 0 | 0
Process
Reference Chapter 2 Appendix for Process Map
| Current Process | [6 empty] | Expected Process
| 130.01 | Acquire/Review Bidding Documents | [5 empty] | 130.01 | Acquire/Review Bidding Documents
| 130.02 | Define Inquiry Issue (Clarification) | [5 empty] | 130.02 | Define Inquiry Issue (Clarification)
| 130.03 | Produce Inquiry Issues | [5 empty] | 130.03 | Produce Inquiry Issues
HANDLING/ ELEC.DOC. | 130.04 | Send Inquiry Issue (Clarification) | [5 empty] | 130.04 | Send Inquiry Issue (Clarification)
|  | 3 | Avg. Number of Transmittals (Transmittals) | [5 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [5 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.16667 | Avg. Time to Prepare Transmittals for Inquiry Issues (hours / transmittal) | [5 empty] | 0.066667 | Avg. Time to Prepare Transmittals for Inquiry Issues (hours / transmittal)
|  | 44.188 | Contractor Administrative Rate ($ / hour) |  |  | 22.094 |  |  | 44.188 | Contractor Administrative Rate ($ / hour) |  |  | 8.8376
|  |  | Mailing Costs |  |  | 729.102 |  |  |  | Mailing Costs |  |  | 0
|  |  | SubTotal |  |  |  | 751.196 |  |  | SubTotal |  |  |  | 8.8376
HANDLING/ ELEC.DOC. | 130.05 | Log Transmittal of Inquiry Issue (Clarification) | [5 empty] | 130.05 | Log Transmittal of Inquiry Issue (Clarification)
|  | 3 | Avg. Number of Transmittals (Transmittals) | [5 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [5 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 44.188 | Contractor Administrative Rate ($ / hour) |  |  | 33.141 |  |  | 44.188 | Contractor Administrative Rate ($ / hour) |  |  | 0
|  |  | SubTotal |  |  |  | 33.141 |  |  | SubTotal |  |  |  | 0
| 130.06 | Receive Inquiry Issue (Clarification) from Contractor | [5 empty] | 130.06 | Receive Inquiry Issue (Clarification) from Contractor
HANDLING/ ELEC.DOC. | 130.07 | Log Receipt of Inquiry Issue (Clarification) | [5 empty] | 130.07 | Log Receipt of Inquiry Issue (Clarification)
|  | 3 | Avg. Number of Transmittals (Transmittals) | [5 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [5 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 12.66 |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 0
|  |  | SubTotal |  |  |  | 12.66 |  |  | SubTotal |  |  |  | 0
HANDLING/ ELEC.DOC. | 130.08 | Send Inquiry Issue (Clarification) to Architect | [5 empty] | 130.08 | Send Inquiry Issue (Clarification) to Architect
|  | 3 | Avg. Number of Transmittals (Transmittals) | [5 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [5 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.083 | Avg. Time to Prepare Transmittals for Inquiry Issues (hours / transmittal) | [5 empty] | 0.0332 | Avg. Time to Prepare Transmittals for Inquiry Issues (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 4.2031 |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 1.6812
|  |  | Mailing Costs |  |  | 49.5 |  |  |  | Mailing Costs |  |  | 0
|  |  | SubTotal |  |  |  | 53.7031 |  |  | SubTotal |  |  |  | 1.6812
HANDLING/ ELEC.DOC. | 130.09 | Log Transmittal of Inquiry Issue (Clarification) | [5 empty] | 130.09 | Log Transmittal of Inquiry Issue (Clarification)
|  | 3 | Avg. Number of Transmittals (Transmittals) | [5 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [5 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 12.66 |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 0
|  |  | SubTotal |  |  |  | 12.66 |  |  | SubTotal |  |  |  | 0
| 130.10 | Receive Inquiry Issue (Clarification) | [5 empty] | 130.10 | Receive Inquiry Issue (Clarification)
HANDLING/ ELEC.DOC. | 130.11 | Log Receipt of Inquiry Issue (Clarification) | [5 empty] | 130.11 | Log Receipt of Inquiry Issue (Clarification)
|  | 3 | Avg. Number of Transmittals (Transmittals) | [5 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [5 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 53.0275 |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 0
|  |  | SubTotal |  |  |  | 53.0275 |  |  | SubTotal |  |  |  | 0
| 130.12 | Review Inquiry Issue (Clarification) | [5 empty] | 130.12 | Review Inquiry Issue (Clarification)
HANDLING/ ELEC.DOC. | 130.13 | Send Inquiry Issue (Clarification) Response | [5 empty] | 130.13 | Send Inquiry Issue (Clarification) Response
|  | 3 | Avg. Number of Transmittals (Transmittals) | [5 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [5 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.16667 | Avg. Time to Prepare Transmittals for Inquiry Issues (hours / transmittal) | [5 empty] | 0.066667 | Avg. Time to Prepare Transmittals for Inquiry Issues (hours / transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 35.3517 |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 14.1407
|  |  | Mailing Costs |  |  | 49.5 |  |  |  | Mailing Costs |  |  | 0
|  |  | SubTotal |  |  |  | 84.8517 |  |  | SubTotal |  |  |  | 14.1407
HANDLING/ ELEC.DOC. | 130.14 | Log Transmittal of Inquiry Issue (Clarification) Response | [5 empty] | 130.14 | Log Transmittal of Inquiry Issue (Clarification) Response
|  | 3 | Avg. Number of Transmittals (Transmittals) | [5 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [5 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 53.0275 |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 0
|  |  | SubTotal |  |  |  | 53.0275 |  |  | SubTotal |  |  |  | 0
| 130.15 | Receive Response to Inquiry Issue (Clarification) from Architect | [5 empty] | 130.15 | Receive Response to Inquiry Issue (Clarification) from Architect
HANDLING/ ELEC.DOC. | 130.16 | Log Receipt of Response of Inquiry Issue (Clarification) | [5 empty] | 130.16 | Log Receipt of Response of Inquiry Issue (Clarification)
|  | 3 | Avg. Number of Transmittals (Transmittals) | [5 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [5 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 53.0275 |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 0
|  |  | SubTotal |  |  |  | 53.0275 |  |  | SubTotal |  |  |  | 0
| 130.17 | Review Responses to Inquiry Issue (Clarification) | [5 empty] | 130.17 | Review Responses to Inquiry Issue (Clarification)
HANDLING/ ELEC.DOC. | 130.18 | Send Inquiry Issue (Clarification) Response to Contractor | [5 empty] | 130.18 | Send Inquiry Issue (Clarification) Response to Contractor
|  | 3 | Avg. Number of Transmittals (Transmittals) | [5 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [5 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.083 | Avg. Time to Prepare Transmittals for Inquiry Issues (hours / transmittal) | [5 empty] | 0.0332 | Avg. Time to Prepare Transmittals for Inquiry Issues (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 4.2031 |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 1.6812
|  |  | Mailing Costs |  |  | 49.5 |  |  |  | Mailing Costs |  |  | 0
|  |  | SubTotal |  |  |  | 53.7031 |  |  | SubTotal |  |  |  | 1.6812
HANDLING/ ELEC.DOC. | 130.19 | Log Transmittal of Inquiry Issue (Clarification) Response | [5 empty] | 130.19 | Log Transmittal of Inquiry Issue (Clarification) Response
|  | 3 | Avg. Number of Transmittals (Transmittals) | [5 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [5 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 12.66 |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 0
|  |  | SubTotal |  |  |  | 12.66 |  |  | SubTotal |  |  |  | 0
| 130.20 | Receive Inquiry Issue (Clarification) Response | [5 empty] | 130.20 | Receive Inquiry Issue (Clarification) Response
HANDLING/ ELEC.DOC. | 130.21 | Log Receipt of Inquiry Issue (Clarification) Response | [5 empty] | 130.21 | Log Receipt of Inquiry Issue (Clarification) Response
|  | 3 | Avg. Number of Transmittals (Transmittals) | [5 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [5 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 44.188 | Contractor Administrative Rate ($ / hour) |  |  | 33.141 |  |  | 44.188 | Contractor Administrative Rate ($ / hour) |  |  | 0
|  |  | SubTotal |  |  |  | 33.141 |  |  | SubTotal |  |  |  | 0
[6 empty] | Current Process Total | 1206.7984 | [5 empty] | Current Process Total | 26.3408

## 01_Facility_Criteria (hidden)
Process Name | Facility Criteria |  |  |  | Current process cost: | 0
OmniClass Stage |  |  |  |  | COBie2 process cost: | 0
Omniclass Role | 34-21 14 00 Owner |  |  |  | Savings of COBie process: | 0
Description | Developing building requirements in which are essential to the success of the stakeholder' needs (e.g. total square foot, number of beds, tempature of facility, etc.)
Information Attributes
Legend
| Color | Description | Allowed User Actions
|  | user defined information unique to this worksheet | change on this worksheet
|  | common user information, listed on assumptions worksheet | change on inputs worksheet
|  | calculated information | do not change this cell
Process
LCie not complete for this process and not part of COBie Calculator Version 0.5
Task 1: | Prepare Criteria
| Current Process |  |  | COBie2 Process
| 01 | Manually Remove Extra Information From Program |  | 01 | Simpligy COBie Data to Standard Design
| 02 | Enter Data into Spreadsheet, or Table |  | 02 | Create Space Data
|  |  |  | 03 | Create Zone Data
|  |  |  | 04 | Create Attribute Data

## 02_Dicipline_Specs (hidden)
Process Name | Dicipline Specifications |  |  |  | Current process cost: | 0
OmniClass Stage |  |  |  |  | COBie2 process cost: | 0
Omniclass Role | 34-21 14 00 Owner |  |  |  | Savings of COBie process: | 0
Description | This process completes the shop drawing and product selection phases on one sheet.
To fix this copy necessary product selection stuff into product selection and copy necessary shop drawing stuff into its sheet.
Information Attributes
Legend
| Color | Description | Allowed User Actions
|  | user defined information unique to this worksheet | change on this worksheet
|  | common user information, listed on assumptions worksheet | change on inputs worksheet
|  | calculated information | do not change this cell
Process
LCie not complete for this process and not part of COBie Calculator Version 0.5
Task 1: | Prepare Criteria
| Current Process |  |  | COBie2 Process
| 01 | Prepare Citeria in Paper Documents |  | 01 | Prepare General Instructions
|  | no equivalent |  | 02 | Prepare Criteria in eCriteria Format
|  | no equivalent |  | 03 | Automate Transformation of Criteria Document
Task 2: | Publish Criteria
| Current Process |  |  | COBie2 Process
| 01 | Publish Paper Criteria Documents |  | 01 | Publish Paper Criteria Documents
|  | no equivalent |  | 02 | Publish Criteria in eCriteria Format

## 09_Design_Issue (hidden)
Process Name | Design Issue |  |  |  | Current process cost: | 0
OmniClass Stage | 31-20 20 21 Engineering Analysis Phase |  |  |  | COBie2 process cost: | 0
Omniclass Role | 34-25 21 00 Architect |  |  |  | Savings of COBie process: | 0
Description | LCie not complete for this process and not part of COBie Calculator Version 0.5
Information Attributes
Legend
| Color | Description | Allowed User Actions
|  | user defined information unique to this worksheet | change on this worksheet
|  | common user information, listed on assumptions worksheet | change on inputs worksheet
|  | calculated information | do not change this cell
Process
LCie not complete for this process and not part of COBie Calculator Version 0.5
Task 1: | Identify Criteria Issues
| Current Process |  |  | COBie2 Process
| 01 |  |  | 01
Task 2: | Identify Specification Issues
| Current Process |  |  | COBie2 Process
| 01 |  |  | 01
Task 3: | Identify Best Practicies Issues
| Current Process |  |  | COBie2 Process
| 01 |  |  | 01
Task 4: | Collate and Resolve Comments
| Current Process |  |  | COBie2 Process
| 01 |  |  | 01

## 12_Bid_Issue (hidden)
Process Name | Bid Issue |  |  |  | Current process cost: | 0
OmniClass Stage | 31-30 30 21 Proposal Preparation Phase |  |  |  | COBie2 process cost: | 0
Omniclass Role | 34-35 14 00 Contractor |  |  |  | Savings of COBie process: | 0
Description | Review of the construction documents at Bid time where the construction teams have the ability to request additional information reagrding the design and owner intent. This includes the process of response from the owner and design team in the form of a bid addendum.
Information Attributes
Legend
| Color | Description | Allowed User Actions
|  | user defined information unique to this worksheet | change on this worksheet
|  | common user information, listed on assumptions worksheet | change on inputs worksheet
|  | calculated information | do not change this cell
Process
LCie not complete for this process and not part of COBie Calculator Version 0.5
Task 1: | Document Issues
| Current Process |  |  | COBie2 Process
| 01 | Submit Issues |  | 01 | Submit Issues
Task 2: | Collate Issues
| Current Process |  |  | COBie2 Process
| 01 | Collate Issues |  | 01 | Collate Issues
| 02 | Distribute Issues |  | 02 | Distribute Issues
Task 3: | Evaluate Issues
| Current Process |  |  | COBie2 Process
| 01 | Capture Evalutions |  | 01 | Capture Evalutions
Task 4: | Collate and Resolve Comments
| Current Process |  |  | COBie2 Process
| 01 | Collate Evaluations |  | 01 | Collate Evaluations
| 02 | Determine Final Resolution |  | 02 | Determine Final Resolution
| 03 | Publish Resolutions |  | 03 | Publish Resolutions

## 140_Pre-Construction_Plan
Process Name | Pre-Construction Plan
OmniClass Stage | 31-40 20 27 Submittal Processing Phase
Omniclass Role | 34-35 14 00 Contractor
Description | The Contractor is required to develop a Pre-Construction Plan that describes how the Contractor will provision and manage the construction of the facility. This is sent as a submittal package. Refer to the submittal Package exchange for detailed requirements related to transmitting and handling Pre-Construction Plan Submittals.
Information Attributes
|  |  | Owner | Architect | Contractor
| Current process cost: | 0 | 0 | 0 | 0
| Expected process cost: | 0 | 0 | 0 | 0
| Process Cost Difference: | 0 | 0 | 0 | 0
Process
Reference Chapter 2 Appendix for Process Map
Current Process | [6 empty] | Expected Process
140.01 | Review Specification Requirements | [5 empty] | 140.01 | Review Specification Requirements
140.02 | Develop Pre-Construction Plan | [5 empty] | 140.02 | Develop Pre-Construction Plan
140.03 | Submittal Process | [5 empty] | 140.03 | Submittal Process
[5 empty] | Current Process Total | 0 |  |  | Current Process Total | 0

## 150_Inquiry_Issue_(RFI)
| Process Name | Inquiry issue (RFI)
| OmniClass Stage | 31-40 20 27 Submittal Processing Phase
| Omniclass Role | 34-35 14 00 Contractor
| Description | The Contractor submits a Request for Information (RFI) to ask for clarification during the construction process. These questions may be due to ambuguities or contradications in the drawings or to site conditions.
Information Attributes
|  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor |  |  |  |  | Owner | Architect | Contractor
|  | Current process cost: | 13972.1608 | 4437.464 | 5536.2928 | 3998.404 |  | Elec. Doc Current process cost: | 13972.1608 | 4437.464 | 5536.2928 | 3998.404 |  |  | COBie Current process cost: | 0 | 0 | 0 | 0
|  | Expected process cost: | 705.5313 | 39.1616 | 410.0793 | 256.2904 |  | Elec. Doc Expected process cost: | 705.5313 | 39.1616 | 410.0793 | 256.2904 |  |  | COBie Expected process cost: | 0 | 0 | 0 | 0
|  | Process Cost Difference: | 13266.6296 | 4398.3024 | 5126.2136 | 3742.1136 |  | Process Cost Difference: | 13266.6296 | 4398.3024 | 5126.2136 | 3742.1136 |  |  | Process Cost Difference: | 0 | 0 | 0 | 0
Process
Reference Chapter 2 Appendix for Process Map
| Current Process | [6 empty] | Expected Process
| 150.01 | Acquire/Review Bidding Documents | [5 empty] | 150.01 | Acquire/Review Bidding Documents
| 150.02 | Define Inquiry Issue (RFI) | [5 empty] | 150.02 | Define Inquiry Issue (RFI)
| 150.03 | Produce Questions | [5 empty] | 150.03 | Produce Questions
HANDLING/ ELEC.DOC. | 150.04 | Send Inquiry Issue (RFI) | [5 empty] | 150.04 | Send Inquiry Issue (RFI)
|  | 87 | Avg. Number of RFIs | [5 empty] | 87 | Avg. Number of RFIs
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [5 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.16667 | Avg. Time to Prepare Transmittals for Inquiry Issues (RFI) (hours / transmittal) | [5 empty] | 0.066667 | Avg. Time to Prepare Transmittals for Inquiry Issues (RFI) (hours / transmittal)
|  | 44.188 | Contractor Administrative Rate ($ / hour) |  |  | 640.726 |  |  | 44.188 | Contractor Administrative Rate ($ / hour) |  |  | 256.2904
|  |  | Mailing Costs |  |  | 1435.5 |  |  |  | Mailing Costs |  |  | 0
|  |  | SubTotal |  |  |  | 2076.226 |  |  | SubTotal |  |  |  | 256.2904
HANDLING/ ELEC.DOC. | 150.05 | Log Transmittal of Inquiry Issue (RFI) | [5 empty] | 150.05 | Log Transmittal of Inquiry Issue (RFI)
|  | 87 | Avg. Number of RFIs | [5 empty] | 87 | Avg. Number of RFIs
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [5 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 44.188 | Contractor Administrative Rate ($ / hour) |  |  | 961.089 |  |  | 44.188 | Contractor Administrative Rate ($ / hour) |  |  | 0
|  |  | SubTotal |  |  |  | 961.089 |  |  | SubTotal |  |  |  | 0
| 150.06 | Receive Inquiry Issue (RFI) from Contractor | [5 empty] | 150.06 | Receive Inquiry Issue (RFI) from Contractor
HANDLING/ ELEC.DOC. | 150.07 | Log Receipt of Inquiry Issue (RFI) | [5 empty] | 150.07 | Log Receipt of Inquiry Issue (RFI)
|  | 87 | Avg. Number of Transmittals (Transmittals) | [5 empty] | 87 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [5 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 367.14 |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 0
|  |  | SubTotal |  |  |  | 367.14 |  |  | SubTotal |  |  |  | 0
HANDLING/ ELEC.DOC. | 150.08 | Send Inquiry Issue (RFI) to Architect | [5 empty] | 150.08 | Send Inquiry Issue (RFI) to Architect
|  | 87 | Avg. Number of RFIs | [5 empty] | 87 | Avg. Number of RFIs
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [5 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.033333 | Avg. Time to Prepare Transmittals for Inquiry Issues (RFI) (hours / transmittal) | [5 empty] | 0.013333 | Avg. Time to Prepare Transmittals for Inquiry Issues (RFI) (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 48.952 |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 19.5808
|  |  | Mailing Costs |  |  | 1435.5 |  |  |  | Mailing Costs |  |  | 0
|  |  | SubTotal |  |  |  | 1484.452 |  |  | SubTotal |  |  |  | 19.5808
HANDLING/ ELEC.DOC. | 150.09 | Log Transmittal of Inquiry Issue (RFI) | [5 empty] | 150.09 | Log Transmittal of Inquiry Issue (RFI)
|  | 87 | Avg. Number of RFIs | [5 empty] | 87 | Avg. Number of RFIs
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [5 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 367.14 |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 0
|  |  | SubTotal |  |  |  | 367.14 |  |  | SubTotal |  |  |  | 0
| 150.10 | Receive Inquiry Issue (RFI) | [5 empty] | 150.10 | Receive Inquiry Issue (RFI)
HANDLING/ ELEC.DOC. | 150.11 | Log Receipt of Inquiry Issue (RFI) | [5 empty] | 150.11 | Log Receipt of Inquiry Issue (RFI)
|  | 87 | Avg. Number of RFIs | [5 empty] | 87 | Avg. Number of RFIs
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [5 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 1537.7973 |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 0
|  |  | SubTotal |  |  |  | 1537.7973 |  |  | SubTotal |  |  |  | 0
| 150.12 | Review Inquiry Issue (RFI) | [5 empty] | 150.12 | Review Inquiry Issue (RFI)
HANDLING/ ELEC.DOC. | 150.13 | Send Inquiry Issue (RFI) Response | [5 empty] | 150.13 | Send Inquiry Issue (RFI) Response
|  | 87 | Avg. Number of RFIs | [5 empty] | 87 | Avg. Number of RFIs
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [5 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.16667 | Avg. Time to Prepare Transmittals for Inquiry Issues (RFI) (hours / transmittal) | [5 empty] | 0.066667 | Avg. Time to Prepare Transmittals for Inquiry Issues (RFI) (hours / transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 1025.1982 |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 410.0793
|  |  | Mailing Costs |  |  | 1435.5 |  |  |  | Mailing Costs |  |  | 0
|  |  | SubTotal |  |  |  | 2460.6982 |  |  | SubTotal |  |  |  | 410.0793
HANDLING/ ELEC.DOC. | 150.14 | Log Transmittal of Inquiry Issue (RFI) Response | [5 empty] | 150.14 | Log Transmittal of Inquiry Issue (RFI) Response
|  | 87 | Avg. Number of RFIs | [5 empty] | 87 | Avg. Number of RFIs
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [5 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 1537.7973 |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 0
|  |  | SubTotal |  |  |  | 1537.7973 |  |  | SubTotal |  |  |  | 0
| 150.15 | Receive Response to Inquiry Issue (RFI) from Architect | [5 empty] | 150.15 | Receive Response to Inquiry Issue (RFI) from Architect
HANDLING/ ELEC.DOC. | 150.16 | Log Receipt of Response of Inquiry Issue (RFI) | [5 empty] | 150.16 | Log Receipt of Response of Inquiry Issue (RFI)
|  | 87 | Avg. Number of RFIs | [5 empty] | 87 | Avg. Number of RFIs
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [5 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 367.14 |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 0
|  |  | SubTotal |  |  |  | 367.14 |  |  | SubTotal |  |  |  | 0
| 150.17 | Review Responses to Inquiry Issue (RFI) | [5 empty] | 150.17 | Review Responses to Inquiry Issue (RFI)
HANDLING/ ELEC.DOC. | 150.18 | Send Inquiry Issue (RFI) Response to Contractor | [5 empty] | 150.18 | Send Inquiry Issue (RFI) Response to Contractor
|  | 87 | Avg. Number of RFIs | [5 empty] | 87 | Avg. Number of RFIs
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [5 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.033333 | Avg. Time to Prepare Transmittals for Inquiry Issues (RFI) (hours / transmittal) | [5 empty] | 0.013333 | Avg. Time to Prepare Transmittals for Inquiry Issues (RFI) (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 48.952 |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 19.5808
|  |  | Mailing Costs |  |  | 1435.5 |  |  |  | Mailing Costs |  |  | 0
|  |  | SubTotal |  |  |  | 1484.452 |  |  | SubTotal |  |  |  | 19.5808
HANDLING/ ELEC.DOC. | 150.19 | Log Transmittal of Inquiry Issue (RFI) Response | [5 empty] | 150.19 | Log Transmittal of Inquiry Issue (RFI) Response
|  | 87 | Avg. Number of RFIs | [5 empty] | 87 | Avg. Number of RFIs
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [5 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 367.14 |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 0
|  |  | SubTotal |  |  |  | 367.14 |  |  | SubTotal |  |  |  | 0
| 150.20 | Receive Inquiry Issue (RFI) from Owner | [5 empty] | 150.20 | Receive Inquiry Issue (RFI) from Owner
HANDLING/ ELEC.DOC.
| 150.21 | Log Receipt of Inquiry Issue (RFI) Response | [5 empty] | 150.21 | Log Receipt of Inquiry Issue (RFI) Response
|  | 87 | Avg. Number of RFIs | [5 empty] | 87 | Avg. Number of RFIs
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [5 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 44.188 | Contractor Administrative Rate ($ / hour) |  |  | 961.089 |  |  | 44.188 | Contractor Administrative Rate ($ / hour) |  |  | 0
|  |  | SubTotal |  |  |  | 961.089 |  |  | SubTotal |  |  |  | 0
[6 empty] | Current Process Total | 13972.1608 | [5 empty] | Current Process Total | 705.5313

## 160_Product_Type_Selection
Process Name | Product Type Selection
OmniClass Stage | 31-40 20 27 Submittal Processing Phase
Omniclass Role | 34-35 14 00 Contractor
Description | The Contractor and Sub-Contractors gather information for products identified in the Design Final documents and prepare submittals. Refer to the Submittal Package exchange for detailed requirements related to transmitting and handling Product Type Selection submittals.
Information Attributes
|  |  | Owner | Architect | Contractor
| Current process cost: | 0 | 0 | 0 | 0
| Expected process cost: | 0 | 0 | 0 | 0
| Process Cost Difference: | 0 | 0 | 0 | 0
Process
Reference Chapter 2 Appendix for Process Map
Current Process | [5 empty] | Expected Process
160.01 | Review Contract Documents |  |  |  |  | 160.01 | Review Contract Documents
160.02 | Validate Submittal Information |  |  |  |  | 160.02 | Validate Submittal Information
160.03 | Submittal Process |  |  |  |  | 160.03 | Submittal Process
|  |  |  | Current Process Total | 0 |  |  | Current Process Total | 0

## 170_System_Layout
Process Name | System Layout
OmniClass Stage | 31-40 20 27 Submittal Processing Phase
Omniclass Role | 34-35 14 00 Contractor
Description | The Contractor and Sub-Contractors review information for products identified in the Design Final documents and prepare shop drawings. Refer to Submittal Package exchange for detailed requirements related to transmitting and handling System Layout submittals.
Information Attributes
|  |  | Owner | Architect | Contractor
| Current process cost: | 0 | 0 | 0 | 0
| Expected process cost: | 0 | 0 | 0 | 0
| Process Cost Difference: | 0 | 0 | 0 | 0
Process
Reference Chapter 2 Appendix for Process Map
Current Process | [6 empty] | Expected Process
170.01 | Review Contract Drawings | [5 empty] | 170.01 | Review Contract Drawings
170.02 | Layout and Route Building System | [5 empty] | 170.02 | Layout and Route Building System
170.03 | Overlay System Layouts (Shop Drawings) | [5 empty] | 170.03 | Overlay System Layouts (Shop Drawings)
170.04 | Identify System Interferences | [5 empty] | 170.04 | Identify System Interferences
170.05 | Resolve System Interferences | [5 empty] | 170.05 | Resolve System Interferences
170.06 | Update System Layouts (Shop Drawings) | [5 empty] | 170.06 | Update System Layouts (Shop Drawings)
170.07.10 | Submittal Process | [5 empty] | 170.07.10 | Submittal Process
[5 empty] | Current Process Total | 0 |  |  | Current Process Total | 0

## 180_Submittal_Package
| Process Name | Submittal Package
| OmniClass Stage | 31-40 20 27 Submittal Processing Phase
| Omniclass Role | 34-35 14 00 Contractor
| Description | The Contractor organizes the required submittal information and creates Submittal Packages to be reviewed by the Architect and/or Owner's Representative.
| Information Attributes | [14 empty] | 3000.7687
771.6157
|  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor
|  | Current process cost: | 60709.7922 | 11415.96 | 6045.1343 | 43248.6979 |  | Elec. Doc Current process cost: | 57709.0235 | 11415.96 | 6045.1343 | 40247.9292 |  | COBie Current process cost: | 3000.7687 | 0 | 0 | 3000.7687
|  | Expected process cost: | 4948.6669 | 1154.592 | 0 | 3794.0749 |  | Elec. Doc Expected process cost: | 4177.0512 | 1154.592 | 0 | 3022.4592 |  | COBie Expected process cost: | 771.6157 | 0 | 0 | 771.6157
|  | Process Cost Difference: | 55761.1253 | 10261.368 | 6045.1343 | 39454.623 |  | Process Cost Difference: | 53531.9723 | 10261.368 | 6045.1343 | 37225.47 |  | Process Cost Difference: | 2229.153 | 0 | 0 | 2229.153
Process
Reference Chapter 2 Appendix for Process Map
Prepare Shop Drawings
| Current Process | [7 empty] | Expected Process
| 180.01 | Identify Submittal Dates on Submittal Register | [6 empty] | 180.01 | Identify Submittal Dates on Submittal Register
| 180.02.10 | Receive Submittal Information from Sub-Contractors and Vendors | [6 empty] | 180.02.10 | Receive Submittal Information from Sub-Contractors and Vendors
HANDLING/ ELEC.DOC. | 180.02.15 | Log Receipt of Submittal Package from Sub-Contractors and Vendors | [6 empty] | 180.02.15 | Log Receipt of Submittal Package from Sub-Contractors and Vendors
|  | 342 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 342 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 44.188 | Contractor Administrative Rate ($ / hour) |  |  | 3778.074 |  |  |  | 44.188 | Contractor Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 3778.074 |  |  |  | SubTotal |  |  | 0
REFORMATTING/ COBie | 180.02.20 | Produce Submittal Information | [6 empty] | 180.02.20 | Produce Submittal Information
|  | 155 | Avg. Number of Equipment (product) Types (Types / project) | [6 empty] | 155 | Avg. Number of Equipment (product) Types (Types / project)
|  | 0.16667 | Avg. Time Spent Organizing Equipment (product) Type information (hours / submittal item) | [6 empty] | 0.016667 | Avg. Time Spent Organizing Equipment (product) Type information (hours / submittal item)
|  | 70.526 | Assistant (Construction) Project Manager Rate ($ / hour) |  |  | 1821.9217 |  |  |  | 70.526 | Assistant (Construction) Project Manager Rate ($ / hour) |  | 182.1922
|  |  | SubTotal |  |  |  | 1821.9217 |  |  |  | SubTotal |  |  | 182.1922
VALIDATING/ COBie | 180.03 | Validate Submittal Information against Contract Documents | [6 empty] | 180.03 | Validate Submittal Information against Contract Documents
|  | 155 | Avg. Number of Equipment (product) Types (Types / project) | [6 empty] | 155 | Avg. Number of Equipment (product) Types (Types / project)
|  | 0.5 | Avg. Time Spent Evaluating Equipment (product) Type Submittal Items against Contract Documents (hours / submittal item) | [6 empty] | 0.25 | Avg. Time Spent Evaluating Equipment (product) Type Submittal Items against Contract Documents (hours / submittal item)
|  | 20% | Percentage of Submittals Items rejected | [6 empty] | 20% | Percentage of Submittals Items rejected
|  | 10% | Percentage of Time Spent by Construction Project Manager | [6 empty] | 10% | Percentage of Time Spent by Construction Project Manager
|  | 90% | Percentage of Time Spent by Assistant (Construction) Project Manager | [6 empty] | 90% | Percentage of Time Spent by Assistant (Construction) Project Manager
|  | 125.8125 | Construction Project Manager Rate ($ / hour) |  |  | 195.0094 |  |  |  | 125.8125 | Construction Project Manager Rate ($ / hour) |  | 97.5047
|  | 70.526 | Assistant (Construction) Project Manager Rate ($ / hour) |  |  | 983.8377 |  |  |  | 70.526 | Assistant (Construction) Project Manager Rate ($ / hour) |  | 491.9189
|  |  | SubTotal |  |  |  | 1178.8471 |  |  |  | SubTotal |  |  | 589.4235
| 180.04 | Produce Submittal Package | [6 empty] | 180.04 | Produce Submittal Package
COPYING/ ELEC.DOC. | 180.05 | Copy Submittal Package | [6 empty] | 180.05 | Copy Submittal Package
|  | 18 | Avg. Number of Submittal Pages in a Submittal Item (pages/submittal item) | [6 empty] | 18 | Avg. Number of Submittal Pages in a Submittal Item (pages/submittal item)
|  | 1 | Avg. Number of Submittal Sheets in a Submittal Item (sheets/submittal item) | [6 empty] | 1 | Avg. Number of Submittal Sheets in a Submittal Item (sheets/submittal item)
|  | 3 | Avg. Number of Submittal Items in a Submittal Package for each Equipment (product) Type (submittal items/submittal package) | [6 empty] | 3 | Avg. Number of Submittal Items in a Submittal Package for each Equipment (product) Type (submittal items/submittal package)
|  | 155 | Avg. Number of Equipment (product) Types (Types / project) | [6 empty] | 155 | Avg. Number of Equipment (product) Types (Types / project)
|  | 6 | Number of Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Number of Submittal Sets Reqd. (sets / submittal)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 3 | Avg. Per Sheet Copy Cost ($ / sheet) | [6 empty] | 0 | Avg. Per Sheet Copy Cost ($ / sheet)
|  | 0.015 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 44.188 | Contractor Administrative Rate ($ / hour) |  |  | 3.9769 |  |  |  | 44.188 | Contractor Administrative Rate ($ / hour) |  | 0
|  |  | Copying Cost |  |  | 15903 |  |  |  |  | Copying Cost |  | 0
|  |  | SubTotal |  |  |  | 15906.9769 |  |  |  | SubTotal |  |  | 0
HANDLING/ ELEC.DOC. | 180.06 | Stamp Submittal Package | [6 empty] | 180.06 | Stamp Submittal Package
|  | 18 | Avg. Number of Submittal Pages in a Submittal Item (pages/submittal item) | [6 empty] | 18 | Avg. Number of Submittal Pages in a Submittal Item (pages/submittal item)
|  | 1 | Avg. Number of Submittal Sheets in a Submittal Item (sheets/submittal item) | [6 empty] | 1 | Avg. Number of Submittal Sheets in a Submittal Item (sheets/submittal item)
|  | 3 | Avg. Number of Submittal Items in a Submittal Package for each Equipment (product) Type (submittal items/submittal package) | [6 empty] | 3 | Avg. Number of Submittal Items in a Submittal Package for each Equipment (product) Type (submittal items/submittal package)
|  | 6 | Number of Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Number of Submittal Sets Reqd. (sets / submittal)
|  | 0.083333 | Avg. Time to Sign each Page (hours/page) | [6 empty] | 0 | Avg. Time to Sign each Page (hours/page)
|  | 0.083333 | Avg. Time to Stamp each Sheet (hours / sheet) | [6 empty] | 0 | Avg. Time to Stamp each Sheet (hours / sheet)
|  | 125.8125 | Construction Project Manager Rate ($ / hour) |  |  | 3585.6562 |  |  |  | 125.8125 | Construction Project Manager Rate ($ / hour) |  | 0
|  | 70.526 | Assistant (Construction) Project Manager Rate ($ / hour) |  |  | 2009.991 |  |  |  | 70.526 | Assistant (Construction) Project Manager Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 3585.6562 |  |  |  | SubTotal |  |  | 0
HANDLING/ ELEC.DOC. | 180.07 | Send Submittal Package | [6 empty] | 180.07 | Send Submittal Package
|  | 342 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 342 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 44.188 | Contractor Administrative Rate ($ / hour) |  |  | 7556.148 |  |  |  | 44.188 | Contractor Administrative Rate ($ / hour) |  | 3022.4592
|  |  | Mailing Costs |  |  | 5643 |  |  |  |  | Mailing Costs |  | 0
|  |  | SubTotal |  |  |  | 13199.148 |  |  |  | SubTotal |  |  | 3022.4592
HANDLING/ ELEC.DOC. | 180.08 | Log Transmittal of Submittal Package | [6 empty] | 180.08 | Log Transmittal of Submittal Package
|  | 342 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 342 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 44.188 | Contractor Administrative Rate ($ / hour) |  |  | 3778.074 |  |  |  | 44.188 | Contractor Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 3778.074 |  |  |  | SubTotal |  |  | 0
| 180.09 | Receive Submittal Package | [6 empty] | 180.09 | Receive Submittal Package
HANDLING/ ELEC.DOC. | 180.10 | Log Receipt of Submittal Package | [6 empty] | 180.10 | Log Receipt of Submittal Package
|  | 342 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 342 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 1443.24 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 1443.24 |  |  |  | SubTotal |  |  | 0
| 180.11 | Verify Submittal Package | [6 empty] | 180.11 | Verify Submittal Package
HANDLING/ ELEC.DOC. | 180.12 | Send Submittal Package to Architect | [6 empty] | 180.12 | Send Submittal Package to Architect
|  | 342 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 342 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 2886.48 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  | 1154.592
|  |  | Mailing Costs |  |  | 5643 |  |  |  |  | Mailing Costs |  | 0
|  |  | SubTotal |  |  |  | 8529.48 |  |  |  | SubTotal |  |  | 1154.592
HANDLING/ ELEC.DOC. | 180.13 | Log Transmittal of Submittal Package | [6 empty] | 180.13 | Log Transmittal of Submittal Package
|  | 342 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 342 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 1443.24 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 1443.24 |  |  |  | SubTotal |  |  | 0
| 180.14 | Receive Submittal Package | [6 empty] | 180.14 | Receive Submittal Package
HANDLING/ ELEC.DOC. | 180.15 | Log Receipt of Submittal Package | [6 empty] | 180.15 | Log Receipt of Submittal Package
|  | 342 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 342 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 6045.1343 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 6045.1343 |  |  |  | SubTotal |  |  | 0
| 180.16 | Submittal Issue | [6 empty] | 180.16 | Submittal Issue
[6 empty] | Current Process Total | 60709.7922 | [5 empty] | Current Process Total | 4948.6669

## 190_Submittal_Issue
| Process Name | Submittal Issue
| OmniClass Stage | 31-40 20 27 Submittal Processing Phase
| Omniclass Role | 34-35 14 00 Contractor
| Description | The Owner's Representative and Architect review the submittals provided by the contractor and provide comments.
Information Attributes
|  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor |  |  |  |  | Owner | Architect | Contractor
|  | Current process cost: | 213946.142 | 0 | 206966.4004 | 15873.2696 |  | Elec. Doc Current process cost: | 112983.0579 | 0 | 112916.7759 | 66.282 |  |  | COBie Current process cost: | 4262.0738 | 0 | 4262.0738 | 0
|  | Expected process cost: | 4524.5564 | 0 | 3853.095 | 1560.8142 |  | Elec. Doc Expected process cost: | 28.2813 | 0 | 28.2813 | 0 |  |  | COBie Expected process cost: | 2131.0369 | 0 | 2131.0369 | 0
|  | Process Cost Difference: | 209421.5856 | 0 | 203113.3054 | 14312.4555 |  | Process Cost Difference: | 112954.7766 | 0 | 112888.4946 | 66.282 |  |  | Process Cost Difference: | 2131.0369 | 0 | 2131.0369 | 0
Reference Chapter 2 Appendix for Process Map
| Current Process | [7 empty] | Expected Process
| 190.01 | Examine Submittal Package (Pre-Construction, Product Type Selection, System Layout) | [6 empty] | 190.01 | Examine Submittal Package (Pre-Construction, Product Type Selection, System Layout)
HANDLING/ ELEC.DOC. | 190.02.10 | Send Copies of Submittal Package (Product Type Selection, System Layout) to Sub-Consultants | [6 empty] | 190.02.10 | Send Copies of Submittal Package (Product Type Selection, System Layout) to Sub-Consultants
|  | 6 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 6 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal | [6 empty] | 0 | Avg. Mailing Cost per Transmittal
|  | 0.083333 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.033333 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 35.3517 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 14.1407
|  |  | Mailing Costs |  |  | 99 |  |  |  |  | Mailing Costs |  |  | 0
|  |  | SubTotal |  |  |  | 134.3517 |  |  |  | SubTotal |  |  |  | 14.1407
HANDLING/ ELEC.DOC. | 190.02.11 | Log Transmittal of Submittal Package (Product Type Selection, System Layout) | [6 empty] | 190.02.11 | Log Transmittal of Submittal Package (Product Type Selection, System Layout)
|  | 6 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 6 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 106.055 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 0
|  |  | SubTotal |  |  |  | 106.055 |  |  |  | SubTotal |  |  |  | 0
| 190.02.12 | Receive Copies of Sub Consultant's Submittal Mark-ups/Comments | [6 empty] | 190.02.12 | Receive Copies of Sub Consultant's Submittal Mark-ups/Comments
HANDLING/ ELEC.DOC. | 190.02.13 | Log Receipt of Sub Consultant's Submittal Mark-ups/Comments | [6 empty] | 190.02.13 | Log Receipt of Sub Consultant's Submittal Mark-ups/Comments
|  | 6 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 6 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 106.055 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 0
|  |  | SubTotal |  |  |  | 106.055 |  |  |  | SubTotal |  |  |  | 0
| 190.02.14 | Review Sub Consultant's Submittal Mark-ups/Comments | [6 empty] | 190.02.14 | Review Sub Consultant's Submittal Mark-ups/Comments
VALIDATING/ COBie | 190.02.20 | Validate Submittal Package not sent to Sub Consultants | [6 empty] | 190.02.20 | Validate Submittal Package not sent to Sub Consultants
|  | 155 | Avg. Number of Equipment (product) Types (Types / project) | [6 empty] | 155 | Avg. Number of Equipment (product) Types (Types / project)
|  | 1 | Avg. Time Spent Evaluating Product Type Submittal Items against Contract Documents (hours / product type submittal item) | [6 empty] | 0.5 | Avg. Time Spent Evaluating Product Type Submittal Items against Contract Documents (hours / product type submittal item)
|  | 25% | Percentage of Product Submittals reviewed by Licensed Architect | [6 empty] | 25% | Percentage of Product Submittals reviewed by Licensed Architect
|  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  |  | 4262.0738 |  |  |  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  |  | 2131.0369
|  |  | SubTotal |  |  |  | 4262.0738 |  |  |  | SubTotal |  |  |  | 2131.0369
HANDLING/ ELEC.DOC. | 190.02.21 | Mark-up Copies of Submittals with Comments | [6 empty] | 190.02.21 | Mark-up Copies of Submittals with Comments
|  | 18 | Avg. Number of Submittal Pages in a Submittal Item (pages/submittal item) | [6 empty] | 18 | Avg. Number of Submittal Pages in a Submittal Item (pages/submittal item)
|  | 1 | Avg. Number of Submittal Sheets in a Submittal Item (sheets/submittal item) | [6 empty] | 1 | Avg. Number of Submittal Sheets in a Submittal Item (sheets/submittal item)
|  | 3 | Avg. Number of Submittal Items in a Submittal Package for each Equipment (product) Type (submittal items/submittal package) | [6 empty] | 3 | Avg. Number of Submittal Items in a Submittal Package for each Equipment (product) Type (submittal items/submittal package)
|  | 155 | Avg. Number of Equipment (product) Types (Types / project) | [6 empty] | 155 | Avg. Number of Equipment (product) Types (Types / project)
|  | 0.033333 | Avg. Time Spent Transferring Comments per Page (hours / page) | [6 empty] | 0 | Avg. Time Spent Transferring Comments per Page (hours / page)
|  | 0.083333 | Avg. Time Spent Transferring Comments per Sheet (hours / sheet) | [6 empty] | 0 | Avg. Time Spent Transferring Comments per Sheet (hours / sheet)
|  | 6 | Number of Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Number of Submittal Sets Reqd. (sets / submittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 112329.9076 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 0
|  |  | SubTotal |  |  |  | 112329.9076 |  |  |  | SubTotal |  |  |  | 0
HANDLING/ ELEC.DOC. | 190.03.10 | Send Copies of Submittal Issues | [6 empty] | 190.03.10 | Send Copies of Submittal Issues
|  | 6 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 6 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal | [6 empty] | 0 | Avg. Mailing Cost per Transmittal
|  | 0.083333 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.033333 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 35.3517 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 14.1407
|  |  | Mailing Cost |  |  | 99 |  |  |  |  | Mailing Cost |  |  | 0
|  |  | SubTotal |  |  |  | 134.3517 |  |  |  | SubTotal |  |  |  | 14.1407
HANDLING/ ELEC.DOC. | 190.03.20 | Log Transmittal of Submittal Issues | [6 empty] | 190.03.20 | Log Transmittal of Submittal Issues
|  | 6 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 6 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 106.055 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 0
|  |  | SubTotal |  |  |  | 106.055 |  |  |  | SubTotal |  |  |  | 0
| 190.04 | Receive Submittal Issue | [6 empty] | 190.04 | Receive Submittal Issue
HANDLING/ ELEC.DOC. | 190.05 | Log Receipt of Submittal Issue | [6 empty] | 190.05 | Log Receipt of Submittal Issue
|  | 6 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 6 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 44.188 | Contractor Administrative Rate ($ / hour) |  |  | 66.282 |  |  |  | 44.188 | Contractor Administrative Rate ($ / hour) |  |  | 0
|  |  | SubTotal |  |  |  | 66.282 |  |  |  | SubTotal |  |  |  | 0
| 190.06 | Review Submittal Package | [6 empty] | 190.06 | Review Submittal Package
[5 empty] | Subtotal (1st Review Total) |  | 117245.1316 | [5 empty] | Subtotal (1st Review Total) |  | 2159.3182
RECREATING/ COBie | 190.06.10 | Recreate Submittal Package (Product Type Selection, System Layout) | [6 empty] | 190.06.10 | Recreate Submittal Package (Product Type Selection, System Layout)
|  | 155 | Avg. Number of Equipment (product) Types (Types / project) | [6 empty] | 155 | Avg. Number of Equipment (product) Types (Types / project)
|  | 0.5 | Avg. Time Spent Revising one Product Submittal Item (hours / product) | [6 empty] | 0.05 | Avg. Time Spent Revising one Product Submittal Item (hours / product)
|  | 80% | Percentage of Time Spent by Construction Project Manager | [6 empty] | 80% | Percentage of Time Spent by Construction Project Manager
|  | 20% | Percentage of Time Spent by Assistant (Construction) Project Manager | [6 empty] | 20% | Percentage of Time Spent by Assistant (Construction) Project Manager
|  | 125.8125 | Construction Project Manager Rate ($ / hour) |  |  | 7800.375 |  |  |  | 125.8125 | Construction Project Manager Rate ($ / hour) |  |  | 780.0375
|  | 70.526 | Assistant (Construction) Project Manager Rate ($ / hour) |  |  | 1093.153 |  |  |  | 70.526 | Assistant (Construction) Project Manager Rate ($ / hour) |  |  | 109.3153
|  |  | SubTotal |  |  | 8893.528 |  |  |  |  | SubTotal |  |  | 889.3528
|  | 42.5% | Percentage of Product Submittals rejected on 2nd review | [6 empty] | 42.5% | Percentage of Product Submittals rejected on 2nd review
[5 empty] | Architect's Cost | 50138.4604 | [6 empty] | Architect's Cost | 933.972
[5 empty] | Contractor's Cost | 3846.0314 | [6 empty] | Contractor's Cost | 377.9749
[7 empty] | 53984.4918 | [7 empty] | 1311.9469
|  | 25% | Percentage of Product Submittals rejected on 3rd review | [6 empty] | 25% | Percentage of Product Submittals rejected on 3rd review
[5 empty] | Architect's Cost | 29734.8636 | [6 empty] | Architect's Cost | 561.0405
[5 empty] | Contractor's Cost | 2289.664 | [6 empty] | Contractor's Cost | 222.3382
[7 empty] | 32024.5276 | [7 empty] | 783.3787
|  | 8% | Percentage of Product Submittals rejected on 4th review | [6 empty] | 8% | Percentage of Product Submittals rejected on 4th review
[5 empty] | Architect's Cost | 9914.2268 | [6 empty] | Architect's Cost | 198.7643
[5 empty] | Contractor's Cost | 777.7642 | [6 empty] | Contractor's Cost | 71.1482
[7 empty] | 10691.991 | [7 empty] | 269.9125
[6 empty] | Current Process Total | 213946.142 | [6 empty] | Current Process Total | 4524.5564

## 200_Purchase_Order
Process Name | Purchase Order
OmniClass Stage | 31-40 20 27 Submittal Processing Phase
Omniclass Role | 34-35 14 00 Contractor
Description | The Contractor contacts a Supplier to order equipment and materials. The Supplier then provides a price quote to the Contractor for the equipment and/or materials. The Contractor verifies the specifications of the equipment and/or materials in the quote against approved submittal documentation and then submits a Purchase Order.
Information Attributes
|  |  | Owner | Architect | Contractor
| Current process cost: | 0 | 0 | 0 | 0
| Expected process cost: | 0 | 0 | 0 | 0
| Process Cost Difference: | 0 | 0 | 0 | 0
Process
Reference Chapter 2 Appendix for Process Map
Current Process | [5 empty] | Expected Process
200.01 | Contact Supplier |  |  |  |  | 200.01 | Contact Supplier
200.02 | Request Quote and Technical Data |  |  |  |  | 200.02 | Request Quote and Technical Data
200.03 | Receive Quote and Technical Data |  |  |  |  | 200.03 | Receive Quote and Technical Data
200.04 | Submit Technical Data for Approval |  |  |  |  | 200.04 | Submit Technical Data for Approval
200.05 | Receive Approval |  |  |  |  | 200.05 | Receive Approval
200.06 | Issue Purchase Order |  |  |  |  | 200.06 | Issue Purchase Order
200.07 | Send Purchase Order and Approved Product Type Selection to Supplier |  |  |  |  | 200.07 | Send Purchase Order and Approved Product Type Selection to Supplier
|  |  |  | Current Process Total | 0 |  |  | Current Process Total | 0

## 210_Product_Installation
| Process Name | Product Installation
| OmniClass Stage | 31-40 40 11 17 Installation Phase
| Omniclass Role | 34-35 14 00 Contractor
| Description | The Contractor installs the building equipment, materials, and systems using the design final drawings, approved shop drawings, product data and manufacturer's instructions.
Information Attributes
|  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor |  |  |  |  | Owner | Architect | Contractor
|  | Current process cost: | 46668.479 | 0 | 35.3517 | 46633.1273 |  | Elec. Doc Current process cost: | 97.8103 | 0 | 35.3517 | 62.4587 |  |  | COBie Current process cost: | 46570.6687 | 0 | 0 | 46570.6687
|  | Expected process cost: | 18588.8977 | 0 | 0 | 18588.8977 |  | Elec. Doc Expected process cost: | 2.9459 | 0 | 0 | 2.9459 |  |  | COBie Expected process cost: | 18585.9519 | 0 | 0 | 18585.9519
|  | Process Cost Difference: | 28079.5813 | 0 | 35.3517 | 28044.2296 |  | Process Cost Difference: | 94.8645 | 0 | 35.3517 | 59.5128 |  |  | Process Cost Difference: | 27984.7168 | 0 | 0 | 27984.7168
Process
Reference Chapter 2 Appendix for Process Map
| Current Process | [6 empty] | Expected Process
| 210.01 | Receive Equipment and Materials | [5 empty] | 210.01 | Receive Equipment and Materials
| 210.02 | Review Purchase Order | [5 empty] | 210.02 | Review Purchase Order
| 210.03.10 | Log Receipt of Equipment and Materials | [5 empty] | 210.03.10 | Log Receipt of Equipment and Materials
| 210.03.11 | Review Manufacturer's Installation Instructions | [5 empty] | 210.03.11 | Review Manufacturer's Installation Instructions
COBie | 210.03.12 | Install Equipment, Materials and Building Systems - Recording Component Data | [5 empty] | 210.03.12 | Install Equipment, Materials and Building Systems - Recording Component Data
|  | 3950 | Avg. Count Tagged Components (components / project) | [5 empty] | 3950 | Avg. Count Tagged Components (components / project)
|  | 0.16667 | Avg. Time Spent Recording Components Data (hours / component) | [5 empty] | 0.066667 | Avg. Time Spent Recording Components Data (hours / component)
|  | 12 | Avg Number of Months of Construction (months) | [5 empty] | 12 | Avg Number of Months of Construction (months)
|  | 70.526 | Assistant (Construction) Project Manager Rate ($ / hour) |  |  | 46429.6167 |  |  | 70.526 | Assistant (Construction) Project Manager Rate ($ / hour) |  |  | 18571.8467
|  |  | SubTotal |  |  |  | 46429.6167 |  |  | SubTotal |  |  |  | 18571.8467
REFORMATTING/ COBie | 210.04 | Reformat Product Installation Report | [5 empty] | 210.04 | Reformat Product Installation Report
|  | 8 | Total Time Spent in Office (hours / day) | [5 empty] | 8 | Total Time Spent in Office (hours / day)
|  | 25% | Avg. Percentage of Office Time Spent formatting Product Installation Report | [5 empty] | 2.5% | Avg. Percentage of Office Time Spent formatting Product Installation Report
|  | 70.526 | Assistant (Construction) Project Manager Rate ($ / hour) |  |  | 141.052 |  |  | 70.526 | Assistant (Construction) Project Manager Rate ($ / hour) |  |  | 14.1052
|  |  | SubTotal |  |  |  | 141.052 |  |  | SubTotal |  |  |  | 14.1052
HANDLING/ ELEC.DOC. | 210.05 | Send Product Installation Report to Architect / Owners Rep | [5 empty] | 210.05 | Send Product Installation Report to Architect / Owners Rep
|  | 2 | Avg. Number of Transmittals (Transmittals) | [5 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [5 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.083333 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [5 empty] | 0.033333 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 44.188 | Contractor Administrative Rate ($ / hour) |  |  | 7.3647 |  |  | 44.188 | Contractor Administrative Rate ($ / hour) |  |  | 2.9459
|  |  | Mailing Cost |  |  | 33 |  |  |  | Mailing Cost |  |  | 0
|  |  | SubTotal |  |  |  | 40.3647 |  |  | SubTotal |  |  |  | 2.9459
HANDLING/ ELEC.DOC. | 210.06 | Log Transmittal of Product Installation Report | [5 empty] | 210.06 | Log Transmittal of Product Installation Report
|  | 2 | Avg. Number of Transmittals (Transmittals) | [5 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [5 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 44.188 | Contractor Administrative Rate ($ / hour) |  |  | 22.094 |  |  | 44.188 | Contractor Administrative Rate ($ / hour) |  |  | 0
|  |  | SubTotal |  |  |  | 22.094 |  |  | SubTotal |  |  |  | 0
| 210.07 | Receive Product Installation Report | [5 empty] | 210.07 | Receive Product Installation Report
HANDLING/ ELEC.DOC. | 210.08 | Log Receipt of Product Installation Report | [5 empty] | 210.08 | Log Receipt of Product Installation Report
|  | 2 | Avg. Number of Transmittals (Transmittals) | [5 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [5 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 35.3517 |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 0
|  |  | SubTotal |  |  |  | 35.3517 |  |  | SubTotal |  |  |  | 0
[6 empty] | Current Process Total | 46668.479 | [5 empty] | Current Process Total | 18588.8977

## 220_Start-Up
Process Name | Start-Up
OmniClass Stage | 31-40 40 11 17 Installation Phase
Omniclass Role | 34-35 14 00 Contractor
Description | After the Contractor completes the installation process, the equipment/systems must be tested by activating the equipment. This testing must be completed with the Owner's Representative and Manufacturer's representative present.
Information Attributes
|  |  | Owner | Architect | Contractor
| Current process cost: | 0 | 0 | 0 | 0
| Expected process cost: | 0 | 0 | 0 | 0
| Process Cost Difference: | 0 | 0 | 0 | 0
Process
Reference Chapter 2 Appendix for Process Map
Current Process | [6 empty] | Expected Process
220.01 | Send Start-Up Test Procedures and Recording Forms to Owner's Rep. | [5 empty] | 220.01 | Send Start-Up Test Procedures and Recording Forms to Owner's Rep.
220.02 | Schedule Start-Up Test with Owner's Rep. | [5 empty] | 220.02 | Schedule Start-Up Test with Owner's Rep.
220.03 | Review Manufacturer's Start-Up/Operation Instructions | [5 empty] | 220.03 | Review Manufacturer's Start-Up/Operation Instructions
220.04 | Conduct Start-Up/Test of Installed Equipment | [5 empty] | 220.04 | Conduct Start-Up/Test of Installed Equipment
220.05 | Record Test Results | [5 empty] | 220.05 | Record Test Results
[5 empty] | Current Process Total | 0 |  |  | Current Process Total | 0

## 230_Product_Inspection
| Process Name | Product Inspection
| OmniClass Stage | 31-40 40 91 17 Evaluation Phase
| Omniclass Role | 34-35 14 00 Contractor
| Description | When the Contractor has completed installation of equipment or systems, a notification is sent to the Architect indicating the installed item is ready for inspection/observation. The Architect conducts regular inspections of the installed construction work. The findings of the inspections including any deficiencies are identified in the inspection report, the Contractor corrects them and requests a re-inspection.
Information Attributes
|  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor
|  | Current process cost: | 29139.3256 | 0 | 29117.2316 | 22.094 |  | Elec. Doc Current process cost: | 102.2295 | 0 | 80.1355 | 22.094 |  | COBie Current process cost: | 29037.096 | 0 | 0 | 29037.096
|  | Expected process cost: | 1166.1974 | 0 | 1166.1974 | 0 |  | Elec. Doc Expected process cost: | 4.7136 | 0 | 4.7136 | 0 |  | COBie Expected process cost: | 1161.4838 | 0 | 0 | 1161.4838
|  | Process Cost Difference: | 27973.1282 | 0 | 27951.0342 | 22.094 |  | Process Cost Difference: | 97.516 | 0 | 75.422 | 22.094 |  | Process Cost Difference: | 27875.6122 | 0 | 0 | 27875.6122
Process
Reference Apendix LC.16 for Process Map
| Current Process | [7 empty] | Expected Process
| 230.02 | Review Contract Drawings and Product Inspection Report | [6 empty] | 230.02 | Review Contract Drawings and Product Inspection Report
| 230.03 | Conduct Product Inspection | [6 empty] | 230.03 | Conduct Product Inspection
REFORMATTING/COBie | 230.04 | Reformat Product Inspection Report | [6 empty] | 230.04 | Reformat Product Inspection Report
|  | 2.75 | Avg. Time Spent Documenting Report per Site Visit (hours / visit) | [6 empty] | 1.1 | Avg. Time Spent Documenting Report per Site Visit (hours / visit)
|  | 4 | Avg. Number of Site Visits per month (visit / month) | [6 empty] | 4 | Avg. Number of Site Visits per month (visit / month)
|  | 12 | Avg. Number of Months of Construction (months) | [6 empty] | 12 | Avg Number of Months of Construction (months)
|  | 8 | Total Time Spent in Office (hours / day) | [6 empty] | 8 | Total Time Spent in Office (hours / day)
|  | 25% | Avg. Percentage of Office Time Spent Quantifying products-in-place | [6 empty] | 2.5% | Avg. Percentage of Office Time Spent Quantifying products-in-place
|  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  |  | 29037.096 |  |  |  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  | 1161.4838
|  |  | SubTotal |  |  |  | 29037.096 |  |  |  | SubTotal |  |  | 1161.4838
HANDLING/ ELEC.DOC. | 230.05 | Send Product Inspection Report to Contractor | [6 empty] | 230.05 | Send Product Inspection Report to Contractor
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.083333 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.033333 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 11.7839 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 4.7136
|  |  | Mailing Cost |  |  | 33 |  |  |  |  | Mailing Cost |  | 0
|  |  | SubTotal |  |  |  | 44.7839 |  |  |  | SubTotal |  |  | 4.7136
HANDLING/ ELEC.DOC. | 230.06 | Log Transmittal of Product Inspection Report | [6 empty] | 230.06 | Log Transmittal of Product Inspection Report
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 35.3517 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 35.3517 |  |  |  | SubTotal |  |  | 0
| 230.07 | Receive Product Inspection Report | [6 empty] | 230.07 | Receive Product Inspection Report
HANDLING/ ELEC.DOC. | 230.08 | Log Receipt of Product Inspection Report | [6 empty] | 230.08 | Log Receipt of Product Inspection Report
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 44.188 | Contractor Administrative Rate ($ / hour) |  |  | 22.094 |  |  |  | 44.188 | Contractor Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 22.094 |  |  |  | SubTotal |  |  | 0
| 230.09 | Review Product Inspection Report | [6 empty] | 230.09 | Review Product Inspection Report
| 230.10 | Correct Deficiencies | [6 empty] | 230.10 | Correct Deficiencies
| 230.11 | Request Re-inspection | [6 empty] | 230.11 | Request Re-inspection
[6 empty] | Current Process Total | 29139.3256 | [5 empty] | Current Process Total | 1166.1974

## 17_Construction_Issue (hidden)
Process Name | Contruction Issue |  |  |  | Current process cost: | 0
OmniClass Stage | 31-40 40 91 17 Evaluation Phase |  |  |  | COBie2 process cost: | 0
Omniclass Role | 34-21 14 00 Owner |  |  |  | Savings of COBie process: | 0
Description | Review of the construction documents during construction where the construction teams have the ability to request additional information reagrding the design and owner intent. This includes the process of response from the owner and design team in the form of a RFI response and changes to the construction documents (bulletin, change directive, etc.)
Information Attributes
Legend
| Color | Description | Allowed User Actions
|  | user defined information unique to this worksheet | change on this worksheet
|  | common user information, listed on assumptions worksheet | change on inputs worksheet
|  | calculated information | do not change this cell
Process
LCie not complete for this process and not part of COBie Calculator Version 0.5
Task 1: | Document Issues
| Current Process |  |  | COBie2 Process
| 01 | Submit Issues |  | 01 | Submit Issues
Task 2: | Collate Issues
| Current Process |  |  | COBie2 Process
| 01 | Collate Issues |  | 01 | Collate Issues
| 02 | Distribute Issues |  | 02 | Distribute Issues
Task 3: | Evaluate Issues
| Current Process |  |  | COBie2 Process
| 01 | Capture Evalutions |  | 01 | Capture Evalutions
Task 4: | Collate and Resolve Comments
| Current Process |  |  | COBie2 Process
| 01 | Collate Evaluations |  | 01 | Collate Evaluations
| 02 | Determine Final Resolution |  | 02 | Determine Final Resolution
| 03 | Publish Resolution |  | 03 | Publish Resolution

## 240_Punchlist_Issue
| Process Name | Punchlist Issue
| OmniClass Stage | 31-40 40 91 17 Evaluation Phase
| Omniclass Role | 34-35 14 00 Contractor
| Description | The Architect creates a final punchlist based upon a survey of the completed construction work. The Contractor corrects the deficiencies identified in the punchlist. The Architect verifies that the Contractor has corrected the deficiencies in the punchlist by performing a final walkthrough.
Information Attributes
|  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor
|  | Current process cost: | 113.4236 | 0 | 91.3296 | 22.094 |  | Elec. Doc Current process cost: | 113.4236 | 0 | 91.3296 | 22.094 |  | COBie Current process cost: | 0 | 0 | 0 | 0
|  | Expected process cost: | 9.1912 | 0 | 9.1912 | 0 |  | Elec. Doc Expected process cost: | 9.1912 | 0 | 9.1912 | 0 |  | COBie Expected process cost: | 0 | 0 | 0 | 0
|  | Process Cost Difference: | 104.2324 | 0 | 82.1384 | 22.094 |  | Process Cost Difference: | 104.2324 | 0 | 82.1384 | 22.094 |  | Process Cost Difference: | 0 | 0 | 0 | 0
Process
Reference Apendix LC.16 for Process Map
| Current Process | [7 empty] | Expected Process
| 240.01 | Request Punchlist Issue Inspection | [6 empty] | 240.01 | Request Punchlist Issue Inspection
| 240.02 | Review Contract Drawings | [6 empty] | 240.02 | Review Contract Drawings
| 240.03 | Conduct Punchlist Issue Inspection | [6 empty] | 240.03 | Conduct Punchlist Issue Inspection
REFORMATTING/COBie | 240.04 | Reformat Punchlist Issue Report | [6 empty] | 240.04 | Reformat Punchlist Issue Report
|  | 0.25 | Avg. Time Spent Documenting Punchlist Report per Site Visit (hours / visit) | [6 empty] | 0.025 | Avg. Time Spent Documenting Punchlist Report per Site Visit (hours / visit)
|  | 0.9 | Avg. Number of Site Visits for Punchlist Inspection (visit / month) | [6 empty] | 0.9 | Avg. Number of Site Visits for Punchlist Inspection (visit / month)
|  | 1 | Total Time Spent in Office (hours / day) | [6 empty] | 1 | Total Time Spent in Office (hours / day)
|  | 0% | Avg. Percentage of Office Time Spent Documenting Site Visit | [6 empty] | 0% | Avg. Percentage of Office Time Spent Documenting Site Visit
|  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  |  | 0 |  |  |  | 109.989 | Licensed Professional Architect Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 0 |  |  |  | SubTotal |  |  | 0
HANDLING/ ELEC.DOC. | 240.05 | Send Punchlist Issue Report to Contractor | [6 empty] | 240.05 | Send Punchlist Issue Report to Contractor
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.25 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.1 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 45.9558 | Architect Drafter Rate ($ / hour) |  |  | 22.9779 |  |  |  | 45.9558 | Architect Drafter Rate ($ / hour) |  | 9.1912
|  |  | Mailing Costs |  |  | 33 |  |  |  |  | Mailing Costs |  | 0
|  |  | SubTotal |  |  |  | 55.9779 |  |  |  | SubTotal |  |  | 9.1912
HANDLING/ ELEC.DOC. | 240.06 | Log Transmittal of Punchlist Issue Report | [6 empty] | 240.06 | Log Transmittal of Punchlist Issue Report
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 70.7033 | Architect Drafter Rate ($ / hour) |  |  | 35.3517 |  |  |  | 70.7033 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 35.3517 |  |  |  | SubTotal |  |  | 0
| 240.07 | Receive Punchlist Issue Report | [6 empty] | 240.07 | Receive Punchlist Issue Report
HANDLING/ ELEC.DOC. | 240.08 | Log Receipt of Punchlist Issue Report | [6 empty] | 240.08 | Log Receipt of Punchlist Issue Report
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 44.188 | Contractor Administrative Rate ($ / hour) |  |  | 22.094 |  |  |  | 44.188 | Contractor Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 22.094 |  |  |  | SubTotal |  |  | 0
| 240.09 | Review Punchlist Issue Report | [6 empty] | 240.09 | Review Punchlist Issue Report
| 240.10 | Correct Deficiencies | [6 empty] | 240.10 | Correct Deficiencies
| 240.11 | Request Re-inspection | [6 empty] | 240.11 | Request Re-inspection
[6 empty] | Current Process Total | 113.4236 | [5 empty] | Current Process Total | 9.1912

## 250_Turnover_Package
| Process Name | Turnover Package
| OmniClass Stage | 31-40 40 91 17 Evaluation Phase
| Omniclass Role | 34-35 14 00 Contractor
| Description | The Contractor gathers all the as-built information related to the project and forwards the information to the owner.
Information Attributes
|  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor |  |  |  | Owner | Architect | Contractor
|  | Current process cost: | 16923.5362 | 395.9964 | 0 | 16527.5398 |  | Elec. Doc Current process cost: | 16923.5362 | 395.9964 | 0 | 16527.5398 |  | COBie Current process cost: | 0 | 0 | 0 | 0
|  | Expected process cost: | 194.0178 | 148.6775 | 0 | 45.3403 |  | Elec. Doc Expected process cost: | 194.0178 | 148.6775 | 0 | 45.3403 |  | COBie Expected process cost: | 0 | 0 | 0 | 0
|  | Process Cost Difference: | 16729.5184 | 247.3189 | 0 | 16482.1995 |  | Process Cost Difference: | 16729.5184 | 247.3189 | 0 | 16482.1995 |  | Process Cost Difference: | 0 | 0 | 0 | 0
Process
Reference Apendix LC.16 for Process Map
| Current Process | [7 empty] | Expected Process
SEARCHING/ ELEC.DOC. | 250.01 | Compile Turnover Package | [6 empty] | 250.01 | Compile Turnover Package
|  | 3 | Avg. Time Spent Searching and Assembling Operations & Maintenance Manuals (hours / document) | [6 empty] | 0.3 | Avg. Time Spent Searching and Assembling Operations & Maintenance Manuals (hours / document)
|  | 0 | Avg. Time Spent Searching and Assembling Commissioning Report (hours / document) | [6 empty] | 0 | Avg. Time Spent Searching and Assembling Commissioning Report (hours / document)
|  | 1.5 | Avg. Time Spent Searching and Assembling Record Specifications (hours / document) | [6 empty] | 0.15 | Avg. Time Spent Searching and Assembling Record Specifications (hours / document)
|  | 364 | Avg. Number of Sheets in Record (As-Built) Drawings | [6 empty] | 364 | Avg. Number of Sheets in Record (As-Built) Drawings
|  | 0.0008 | Avg. Time Spent Searching and Assembling Record (As-Built) Drawings (hours / sheet) | [6 empty] | 8e-05 | Avg. Time Spent Searching and Assembling Record (As-Built) Drawings (hours / sheet)
|  | 1 | Avg. Number of Sheets in Final Approved Shop Drawings | [6 empty] | 1 | Avg. Number of Sheets in Final Approved Shop Drawings
|  | 0.0083333 | Avg. Time Spent Searching and Assembling Final Approved Shop Drawings (hours / sheet) | [6 empty] | 0.00083333 | Avg. Time Spent Searching and Assembling Final Approved Shop Drawings (hours / sheet)
|  | 10% | Percentage of Time Spent by Construction Project Manager | [6 empty] | 10% | Percentage of Time Spent by Construction Project Manager
|  | 90% | Percentage of Time Spent by Assistant (Construction) Project Manager | [6 empty] | 90% | Percentage of Time Spent by Assistant (Construction) Project Manager
|  | 125.8125 | Construction Project Manager Rate ($ / hour) |  |  | 60.3841 |  |  |  | 125.8125 | Construction Project Manager Rate ($ / hour) |  | 6.0384
|  | 70.526 | Assistant (Construction) Project Manager Rate ($ / hour) |  |  | 304.6427 |  |  |  | 70.526 | Assistant (Construction) Project Manager Rate ($ / hour) |  | 30.4643
|  |  | SubTotal |  |  |  | 365.0268 |  |  |  | SubTotal |  |  | 36.5027
COPYING/ ELEC.DOC. | 250.02 | Copy Turnover Package | [6 empty] | 250.02 | Copy Turnover Package
|  | 5425 | Avg. Number of Pages in Operations & Maintenance Manuals | [6 empty] | 5425 | Avg. Number of Pages in Operations & Maintenance Manuals
|  | 0 | Avg. Number of Pages in Commissioning Report | [6 empty] | 0 | Avg. Number of Pages in Commissioning Report
|  | 2156 | Avg. Number of Pages in Record Specifications | [6 empty] | 2156 | Avg. Number of Pages in Record Specifications
|  | 364 | Avg. Number of Sheets in Record (As-Built) Drawings | [6 empty] | 364 | Avg. Number of Sheets in Record (As-Built) Drawings
|  | 1 | Avg. Number of Sheets in Final Approved Shop Drawings | [6 empty] | 1 | Avg. Number of Sheets in Final Approved Shop Drawings
|  | 6 | Number of Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Number of Submittal Sets Reqd. (sets / submittal)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 3 | Avg. Per Sheet Copy Cost ($ / sheet) | [6 empty] | 0 | Avg. Per Sheet Copy Cost ($ / sheet)
|  | 9 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 44.188 | Contractor Administrative Rate ($ / hour) |  |  | 2386.152 |  |  |  | 44.188 | Contractor Administrative Rate ($ / hour) |  | 0
|  |  | Reproduction Costs |  |  | 13392.9 |  |  |  |  | Reproduction Costs |  | 0
|  |  | SubTotal |  |  |  | 15779.052 |  |  |  | SubTotal |  |  | 0
HANDLING/ ELEC.DOC. | 250.03 | Send Copies of Turnover Package | [6 empty] | 250.03 | Send Copies of Turnover Package
|  | 350.32 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 44.188 | Contractor Administrative Rate ($ / hour) |  |  | 22.094 |  |  |  | 44.188 | Contractor Administrative Rate ($ / hour) |  | 8.8376
|  |  | Mailing Cost ($) |  |  | 350.32 |  |  |  |  | Mailing Cost ($) |  | 0
|  |  | SubTotal |  |  |  | 372.414 |  |  |  | SubTotal |  |  | 8.8376
HANDLING/ ELEC.DOC. | 250.04 | Log Transmittal of the Turnover Package | [6 empty] | 250.04 | Log Transmittal of the Turnover Package
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 44.188 | Contractor Administrative Rate ($ / hour) |  |  | 11.047 |  |  |  | 44.188 | Contractor Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 11.047 |  |  |  | SubTotal |  |  | 0
| 250.05 | Receive Copies of the Turnover Package | [6 empty] | 250.05 | Receive Copies of the Turnover Package
HANDLING/ ELEC.DOC. | 250.06 | Log Receipt of the Turnover Package | [6 empty] | 250.06 | Log Receipt of the Turnover Package
|  | 0.25 | Avg. Time to Log (hours / transmittal) | [6 empty] | 0 | Avg. Time to Log (hours / transmittal)
|  | 23.71 | Owner Administrative Rate ($ / hour) |  |  | 5.9275 |  |  |  | 23.71 | Owner Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 5.9275 |  |  |  | SubTotal |  |  | 0
HANDLING/ ELEC.DOC. | 250.07 | Review Turnover Package | [6 empty] | 250.07 | Review Turnover Package
|  | 5425 | Avg. Number of Pages in Operations & Maintenance Manuals | [6 empty] | 5425 | Avg. Number of Pages in Operations & Maintenance Manuals
|  | 0.0016667 | Avg. Time Spent Reviewing Operations & Maintenance Manuals (hours/page) | [6 empty] | 0.00066667 | Avg. Time Spent Reviewing Operations & Maintenance Manuals (hours/page)
|  | 0 | Avg. Number of Pages in Commissioning Report | [6 empty] | 0 | Avg. Number of Pages in Commissioning Report
|  | 0 | Avg. Time Spent Reviewing Commissioning Report (hours/page) | [6 empty] | 0 | Avg. Time Spent Reviewing Commissioning Report (hours/page)
|  | 2156 | Avg. Number of Pages in Record Specifications | [6 empty] | 2156 | Avg. Number of Pages in Record Specifications
|  | 0.0016667 | Avg. Time Spent Reviewing Record Specifications (hours / page) | [6 empty] | 0.00066667 | Avg. Time Spent Reviewing Record Specifications (hours / page)
|  | 364 | Avg. Number of Sheets in Record (As-Built) Drawings | [6 empty] | 364 | Avg. Number of Sheets in Record (As-Built) Drawings
|  | 0.0083333 | Avg. Time Spent Reviewing Record (As-Built) Drawings (hours /sheet) | [6 empty] | 0.0033333 | Avg. Time Spent Reviewing Record (As-Built) Drawings (hours /sheet)
|  | 1 | Avg. Number of Sheets in Final Approved Shop Drawings | [6 empty] | 1 | Avg. Number of Sheets in Final Approved Shop Drawings
|  | 0.0083333 | Avg. Time Spent Reviewing Final Approved Shop Drawings (hours/sheet) | [6 empty] | 0.0033333 | Avg. Time Spent Reviewing Final Approved Shop Drawings (hours/sheet)
|  | 23.71 | Owner Administrative Rate ($ / hour) |  |  | 371.6938 |  |  |  | 23.71 | Owner Administrative Rate ($ / hour) |  | 148.6775
|  |  | SubTotal |  |  |  | 371.6938 |  |  |  | SubTotal |  |  | 148.6775
HANDLING/ ELEC.DOC. | 250.08 | File Turnover Package | [6 empty] | 250.08 | File Turnover Package
|  | 0.08333 | Avg. Time Spent Filing Operations & Maintenance Manuals (hours / document) | [6 empty] | 0 | Avg. Time Spent Filing Operations & Maintenance Manuals (hours / document)
|  | 0 | Avg. Time Spent Filing Commissioning Report (hours/document) | [6 empty] | 0 | Avg. Time Spent Filing Commissioning Report (hours/document)
|  | 0.08333 | Avg. Time Spent Filing Record Specifications (hours/document) | [6 empty] | 0 | Avg. Time Spent Filing Record Specifications (hours/document)
|  | 364 | Avg. Number of Sheets in Record (As-Built) Drawings | [6 empty] | 364 | Avg. Number of Sheets in Record (As-Built) Drawings
|  | 0.0016667 | Avg. Time Spent Filing Record (As-Built) Drawings (hours/sheet) | [6 empty] | 0 | Avg. Time Spent Filing Record (As-Built) Drawings (hours/sheet)
|  | 1 | Avg. Number of Sheets in Final Approved Shop Drawings | [6 empty] | 1 | Avg. Number of Sheets in Final Approved Shop Drawings
|  | 0.0016667 | Avg. Time Spent Filing Final Approved Shop Drawings(hours/sheet) | [6 empty] | 0 | Avg. Time Spent Filing Final Approved Shop Drawings(hours/sheet)
|  | 23.71 | Owner Administrative Rate ($ / hour) |  |  | 18.3751 |  |  |  | 23.71 | Owner Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 18.3751 |  |  |  | SubTotal |  |  | 0
[6 empty] | Current Process Total | 16923.5362 | [5 empty] | Current Process Total | 194.0178

## 22_Space_Condition (hidden)
Process Name | Space Condition |  |  |  | Current process cost: | #REF!
OmniClass Stage | 31-50 20 21 Facility Inspection Phase |  |  |  | COBie2 process cost: | #REF!
Omniclass Role | 34-41 11 00 Facility Manager |  |  |  | Process Cost Difference: | #REF!
Description | During the operations of the facility, it is necessary to assess the condition of individual spaces. This is often accomplished to support facility management decisions relating to phased refurbishment and redecoration. In other cases space surveys are required to be conducted to update a variety of different attributes related to health, safety, environmental, accessibility, energy, or other topics.
Information Attributes
Legend
| Color | Description | Allowed User Actions
|  | user defined information unique to this worksheet | change on this worksheet
|  | common user information, listed on assumptions worksheet | change on inputs worksheet
|  | calculated information | do not change this cell
Process
Process is not completely defined and not part of COBie Calculator version 0.5
Reference LCie 22 for further information
| Current Process |  |  | COBie2 Process

## 23_Product_Parts_Replacement (hidden)
Process Name | Product Parts Replacement |  |  |  | Current process cost: | 0
OmniClass Stage | 31-50 20 11 Facility Operation Phase |  |  |  | COBie2 process cost: | 0
Omniclass Role | 34-41 21 00 Facility Maintenance |  |  |  | Process Cost Difference: | 0
Description | During the operations of a facility products will have to be maintained. The capture of information about the work accomplished on a specific product might include, for example, the use of replacement parts to repair or maintain that equipment. For most facility management tasks the specific corrections made to a given piece of equipment are not documented.
Information Attributes
Legend
| Color | Description | Allowed User Actions
|  | user defined information unique to this worksheet | change on this worksheet
|  | common user information, listed on assumptions worksheet | change on inputs worksheet
|  | calculated information | do not change this cell
Process
Process is not completely defined and not part of COBie Calculator version 0.5
Reference LCie 23 for further information
| Current Process |  |  | COBie2 Process

## 24_Remodel (hidden)
Process Name | Remodel |  |  | Current process cost: | 0
OmniClass Stage | 31-50 30 14 Facility Remodeling Phase |  |  | COBie2 process cost: | 0
Omniclass Role | 34-41 11 00 Facility Manager |  |  | Savings of COBie process: | 0
Description | LCie not complete for this process and not part of COBie Calculator Version 0.5
Information Attributes
Legend
| Color | Description | Allowed User Actions
|  | user defined information unique to this worksheet | change on this worksheet
|  | common user information, listed on assumptions worksheet | change on inputs worksheet
|  | calculated information | do not change this cell
Process
LCie not complete for this process and not part of COBie Calculator Version 0.5

## 25_Expand (hidden)
Process Name | Expand |  |  |  | Current process cost: | 0
OmniClass Stage | 31-50 30 17 Facility Expansion Phase |  |  |  | COBie2 process cost: | 0
Omniclass Role | 34-41 11 00 Facility Manager |  |  |  | Savings of COBie process: | 0
Description | LCie not complete for this process and not part of COBie Calculator Version 0.5
Legend
| Color | Description | Allowed User Actions
|  | user defined information unique to this worksheet | change on this worksheet
|  | common user information, listed on assumptions worksheet | change on inputs worksheet
|  | calculated information | do not change this cell
Task 1:
| Current Process |  |  | COBie2 Process

## 26_Demolosh (hidden)
Process Name | Demolish |  |  |  | Current process cost: | 0
OmniClass Stage | 31-60 35 00 Recycling Phase |  |  |  | COBie2 process cost: | 0
Omniclass Role | 34-41 11 00 Facility Manager |  |  |  | Savings of COBie process: | 0
Description | LCie not complete for this process and not part of COBie Calculator Version 0.5
Legend
| Color | Description | Allowed User Actions
|  | user defined information unique to this worksheet | change on this worksheet
|  | common user information, listed on assumptions worksheet | change on inputs worksheet
|  | calculated information | do not change this cell
Task 1:
| Current Process |  |  | COBie2 Process

## ProductCount (hidden)
Process Name | Quantity Takeoff | [8 empty] | Current process cost: | #REF!
OmniClass Stage | 31-10 45: Budgeting Phase | [8 empty] | COBie2 process cost: | 0
Omniclass Role | 34-21: Planner Role | [8 empty] | Savings of COBie process: | #REF!
Legend
| Color | Description |  |  | Allowed User Actions
|  | user defined information unique to this worksheet |  |  | change on this worksheet
|  | common user information, listed on assumptions worksheet |  |  | change on inputs worksheet
|  | calculated information |  |  | do not change this cell
Task 1: | Perform Quantity Takeoff
| Current Process | [7 empty] | COBie2 Process
| 01 | Count Doors | [6 empty] | no equvalent task
|  | #REF! | Avg. Square Footage
|  | #REF! | Avg. Cost Door Count
|  | #REF! | technical staff hours | @ | #REF! | = | #REF!
| 02 | Count Windows | [6 empty] | no equvalent task
|  | #REF! | Avg. Square Footage
|  | #REF! | Avg. Cost Window Count
|  | #REF! | technical staff hours | @ | #REF! | = | #REF!
| 03 | Count Hardware | [6 empty] | no equvalent task
|  | #REF! | Avg. Square Footage
|  | #REF! | Avg. Cost Hardware Count
|  | #REF! | technical staff hours | @ | #REF! | = | #REF!
| 04 | Estimate Carpet | [6 empty] | no equvalent task
|  | #REF! | Avg. Square Footage
|  | #REF! | Avg. Cost Carpet Estimate
|  | #REF! | technical staff hours | @ | #REF! | = | #REF!
| 05 | Estimate Wall Covering | [6 empty] | no equvalent task
|  | #REF! | Avg. Square Footage
|  | #REF! | Avg. Cost Wall Covering Estimate
|  | #REF! | technical staff hours | @ | #REF! | = | #REF!
| 06 | Count HVAC Equipment | [6 empty] | no equvalent task
|  | #REF! | Avg. Square Footage
|  | #REF! | Avg. Cost HVAC Equipment Count
|  | #REF! | technical staff hours | @ | #REF! | = | #REF!
| 07 | Count Electrical Equipment | [6 empty] | no equvalent task
|  | #REF! | Avg. Square Footage
|  | #REF! | Avg. Cost Elec Equipment Count
|  | #REF! | technical staff hours | @ | #REF! | = | #REF!
| 08 | Count Plumbing Fixtures | [6 empty] | no equvalent task
|  | #REF! | Avg. Square Footage
|  | #REF! | Avg. Cost Plumbing Fixture Count
|  | #REF! | technical staff hours | @ | #REF! | = | #REF!
|  |  | Total |  |  |  |  | #REF! |  |  | Total | 0