## LCHS SHEETS _ FLOOR PLANS (hidden)
Lake Central High School
| FLOOR LEVELS | DISCIPLINES
|  | Bidding Scope | Floor Plans | Demolition Plan | Reflected Ceiling Plan | Finish Plan | Interior Plan | HVAC Plan | HVAC Demo Plan | Lighting Plan | Electrical Demo Plan | Mech Roof Plan | Piping Plan | Demo Plumbing Plan | Plumbing Plan | Power Plan | Telecom Plan | Telecom Demo Plan | Structure
SECTOR 1 | Overall Layout
| Exisitng Building |  |  | * | [6 empty] | *
| Foundation Plan | [13 empty] | *
| First Floor Plan | * | * | * | [6 empty] | *
| Second Floor Plan |  | * | * | [6 empty] | *
| Mezzanine Floor Plan | [8 empty] | *
| Roof Plan | [14 empty] | *
Unit A
| First Floor Plan |  | * | * | * | * | * | * | * | * | * |  | * | * | * | * | * | * | *
| Second Floor Plan |  | * | * | * | * | * | [8 empty] | * | *
| Mezzanine Floor Plan |  |  | * | [5 empty] | * | * |  |  |  |  | *
| Roof Plan | [10 empty] | * |  |  | *
Unit B
| First Floor Plan |  | * | * | * | * | * | * |  | * | * |  | * | * | * | * | *
| Second Floor Plan |  | * | * | * | * | * | * |  |  | * |  | * |  |  | * | *
Mezzanine Floor Plan
| Roof Plan | [10 empty] | * |  |  | *
Unit C
| First Floor Plan |  | * | * | * | * | * | * |  | * | * |  | * | * | * | * | * | *
| Second Floor Plan |  | * | * | * | * | * |  |  |  | * |  |  | * | * | *
| Mezzanine Floor Plan | [17 empty] | *
Roof Plan
Unit D
| First Floor Plan |  | * | * | * | * | * |  |  |  | * |  |  |  | * | * | *
Second Floor Plan
Mezzanine Floor Plan
Roof Plan
Unit E
| First Floor Plan |  | * | * | * | * | * |  |  |  | * |  | * |  |  | * | *
| Second Floor Plan |  |  | * | * | * | * | * |  |  |  |  | * |  |  |  | *
| Mezzanine Floor Plan |  | *
| Roof Plan | [10 empty] | *
Unit F
| First Floor Plan |  | * | * | * | * | * | * |  |  | * |  | * |  | * | * | *
| Second Floor Plan |  |  | * | * | * | *
| Mezzanine Floor Plan |  | *
Roof Plan
|  | 1 | 13 | 15 | 11 | 11 | 11 | 6 | 1 | 5 | 12 | 3 | 7 | 4 | 9 | 11 | 9 | 2 | 2 | 133
9.2308
[5 empty] | Area |  |  | 262990sqft
[5 empty] | Number of Floors |  |  | 2
[5 empty] | Number of Architectural Plans |  |  | 13
[5 empty] | Total number of Plan Sheets |  |  | 133
[5 empty] | Number of Disciplines |  |  | 16
[5 empty] | Average nos of sheets per Discipline |  |  | 7.4375
[5 empty] | Total number of Sheets |  |  | 144
[5 empty] | % of Sheets |  |  | 92.36%
SECTOR 2 | Overall Layout
First Floor Plan
Second Floor Plan
Third Floor Plan
Roof Plan
Unit G
| First Floor Plan |  | * |  | * | * | * | * |  | * |  |  | * |  | * | * | * |  | *
| Second Floor Plan |  | * |  | * | * | * | * |  | * |  |  | * |  | * | * | * |  | *
| Third Floor Plan |  | * |  | * | * | * | * |  | * |  |  | * |  | * | * | * |  | *
| Roof Plan | [10 empty] | *
Unit H
| First Floor Plan |  | * |  | * | * | * | * |  | * |  |  | * |  | * | * | * |  | *
| Second Floor Plan |  | * |  | * | * | * | * |  | * |  |  | * |  | * | * | * |  | *
| Third Floor Plan |  | * |  | * | * | * | * |  | * |  |  | * |  | * | * | * |  | *
| Roof Plan | [10 empty] | *
Unit J
| First Floor Plan |  | * |  | * | * | * | * |  | * |  |  | * |  | * | * | * |  | *
| Second Floor Plan |  | * |  | * | * | * | * |  | * |  |  | * |  | * | * | * |  | *
| Third Floor Plan |  | * |  | * | * | * | * |  | * |  |  | * |  | * | * | * |  | *
Roof Plan
Unit K
| First Floor Plan |  | * |  | * | * | * | * |  | * |  |  | * |  | * | * | * |  | *
| Second Floor Plan |  | * |  | * | * | * | * |  | * |  |  | * |  | * | * | * |  | *
| Third Floor Plan |  | * |  | * | * | * | * |  | * |  |  | * |  | * | * | *
| Roof Plan | [10 empty] | *
|  | 0 | 12 | 0 | 12 | 12 | 12 | 12 |  | 12 |  | 3 | 12 | 0 | 12 | 12 | 12 | 0 | 11 | 134
[5 empty] | 10.1667 | [6 empty] | #REF! | [7 empty] | 122
[5 empty] | Area |  |  | 128670 sqft |  |  |  | 128670 sqft
[5 empty] | Number of Floors |  |  | 3 |  |  |  | 3
[5 empty] | Number of Architectural Plans |  |  | 12 |  |  |  | #REF!
[5 empty] | Number of Disciplines |  |  | 11 |  |  |  | 11
[5 empty] | Average nos of sheets per Discipline |  |  | 11.0909
[5 empty] | Total number of Sheets |  |  | 196
[5 empty] | Average nos of sheets per Discipline |  |  | 11.0909 |  |  |  | #REF!
[5 empty] | % of Plan Sheets |  |  | 68.37%

## OfficePaperVsExpectedDeltas (hidden)
InputVariables | Current | Expected | Deltas | ref.line |  | Current | Expected | Delta
AvgNumberofPagesinFacilityCriteria | 2 | 2 | 0 |  | LCie 01 - Facility Criteria | 0 | 0 | 0
AvgNumberofPagesinDisciplineSpecification | 52 | 52 | 0 |  | LCie 02 - Design Specification | 20 | 0 | 20
AvgNumberofPagesinProjectDefinition | 2 | 2 | 0 |  | LCie 03 - Feasibility Study | 470 | 20 | 450
AvgNumberofPagesinFrontMatter | 10 | 10 | 0 |  | LCie 04 - Project Definition | 0 | 0 | 0
NumberofEquipmentTypes | 43 | 43 | 0 | 10 | LCie 05 - Space Program | 510 | 10 | 500
NumberofTaggedComponents | 23200 | 23200 | 0 |  | LCie 06 - Product Program | 540 | 20 | 520
NumberofSpaceTypesperBuilding | 18 | 18 | 0 |  | LCie 07 - Request for Proposal | 400 | 100 | 300
TimetoLog | 0.25 | 0 | 0 |  | LCie 08 - Design Early | 4900 | 100 | 4800
AvgNumberofOptions | 3 | 3 | 0 | 16 | LCie 09 - Design Schematic | 7100 | 700 | 6400
AvgPre-DesignSubmittalSetsReqd(sets/submittal) | 4 | 0 | 0 |  | LCie 10 -Design Coordinated | 21600 | 3700 | 17900
AvgNumberofSheetsperOption | 3 | 3 | 0 |  | LCie 11 - Design Final | 9200 | 800 | 8400
AvgNumberofLetter-SizedPagesinDesignNarrativeperOption | 10 | 10 | 0 |  | LCie 12 - Request for Proposal | 410 | 30 | 380
AvgNumberofPagesinSpaceProgram | 5.94 | 5.94 | 0 |  | LCie 13 - Inquiry Issue | 1210 | 30 | 1180
AvgNumberofPagesinProductProgram | 14.19 | 14.19 | 0 |  | LCie 14 - Pre-Construction Plan | 0 | 0 | 0
NumberofDesignSubmittalSetsReqd(sets/submittal) | 6 | 0 | 0 | 24 | LCie 15 - Inquiry Issue (RFI) | 4700 | 0 | 4700
AvgNumberofSheetsinDesignEarlyDrawings | 37.3333 | 37.3333 | 0 |  | LCie 16 - Product Type Selection | 0 | 0 | 0
AvgNumberofLetter-SizedPagesinDesignEarlyNarrative | 10 | 10 | 0 |  | LCie 17 - System Layout | 0 | 0 | 0
AvgNumberofSheetsinDesignSchematicDrawings | 44.8 | 44.8 | 0 |  | LCie 18 - Submittal Package | 12200 | 600 | 11600
AvgNumberofLetterSizedPagesinDesignSchematicNarrative | 20 | 20 | 0 |  | LCie 19 - Submittal Issue | 60500 | 400 | 60100
AvgNumberofLetterSizedPagesinaDesignSchematicSpecification | 2 | 2 | 0 |  | LCie 20 - Purchase Order | 0 | 0 | 0
AvgNumberofSheetsinDesignCoordinatedDrawings | 53.3333 | 53.3333 | 0 |  | LCie 21 - Product Installation | 278300 | 0 | 278300
AvgNumberofLetterSizedPagesinaDesignCoordinatedNarrative | 20 | 20 | 0 |  | LCie 22 - Start-Up | 0 | 0 | 0
AvgNumberofLetterSizedPagesinaDesignCoordinatedSpecification | 50 | 50 | 0 |  | LCie 23 - Product Inspection | 15900 | 600 | 15300
AvgNumberofSheetsinDesignFinalDrawings | 56 | 56 | 0 |  | LCie 24 - Punchlist Issue | 0 | 0 | 0
AvgNumberofLetterSized'PagesinDesignFinalNarrative | 20 | 20 | 0 |  | LCie 25 - Turnover Package | 27400 | 100 | 27300
AvgNumberofLetterSizedPagesinDesignFinalSpecification | 50 | 50 | 0
AvgQTOTimeforEquipmentComponents(hours/plandrawing) | 0.08 | 0.008 | -0.072 | 38
AvgQTOTimeforSpacesinbuilding(hours/plandrawing) | 0.16 | 0.016 | -0.144
NumberofSubmittalSetsReqd(sets/submittal) | 6 | 0 | 0 | 42
AvgNumberofSubmittalItemsinaSubmittalPackageforeachEquipment(product)Type(submittalitems/submittalpackage) | 3 | 3 | 0
AvgNumberofSubmittalPagesinaSubmittalItem(pages/submittalitem) | 18 | 18 | 0
AvgNumberofSubmittalSheetsinaSubmittalItem(sheets/submittalitem) | 1 | 1 | 0
OwnerAdministrativeRate($/hour) | 23.71 | 23.71 | 0 | 49
OwnersRepRate($/hour) | 62.2 | 62.2 | 0
OwnersRepAdministrativeRate($/hour) | 16.88 | 16.88 | 0
PlannerRate($/hour) | 37.84 | 37.84 | 0
PlannerAdministrativeRate($/hour) | 16.82 | 16.82 | 0
LicensedProfessionalArchitectRate($/hour) | 109.99 | 109.99 | 0
Specifier | 109.99 | 109.99 | 0
ArchitectDrafterRate($/hour) | 70.7 | 70.7 | 0
ArchitectAdministrativeRate($/hour) | 45.96 | 45.96 | 0
ConstructionProjectManagerRate($/hour) | 125.81 | 125.81 | 0
Assistant(Construction)ProjectManagerRate($/hour) | 70.53 | 70.53 | 0
ContractorAdministrativeRate($/hour) | 44.19 | 44.19 | 0
AvgPerPageCopyCost($/page) | 0.15 | 0 | 0 | 64
AvgPerSheetCopyCost($/sheet) | 3 | 0 | 0
AvgNumberofSetsRequired(sets/submittal) | 2 | 0 | 0 | 70
AvgIn-houseReproductionTimePerSet(hours/set) | 0.0013333 | 0 | 0
AvgNumberofSetsRequired(sets/submittal) | 2 | 0 | 0 | 73
AvgIn-houseReproductionTimePerSet(hours/set) | 0.034667 | 0 | 0
AvgNumberofTransmittals | 2 | 2 | 0 | 76
AvgIn-houseReproductionTimePerSubmittalSet(hours/submittalset) | 0.015 | 0 | 0
AvgMailingCostperTransmittal($/Transmittal) | 18.8 | 0 | 0
AvgTimetoPrepareTransmittal(hours/transmittal) | 0.5 | 0.2 | -0.3
AvgNumberofSetsRequired(sets/submittal) | 2 | 0 | 0 | 81
AvgIn-houseReproductionTimePerSet(hours/set) | 0.0013333 | 0 | 0
AvgTimeSpentRecreatingSpaceProgramCriteria(hours/space) | 0.25 | 0 | 0 | 84
AvgTimeSpentReformattingRoomDataSheet(hours/space) | 0.08 | 0 | 0
AvgTimetoCompareSpaceProgramwithOwnerStandards(hours) | 0.72 | 0.072 | -0.648
AvgPercentageoferrorsinSpaceProgram | 0.3 | 0.03 | -0.27
AvgTimeSpentRecreatingSpaceProgram(hours/space) | 0.25 | 0 | 0
AvgNumberofReviewCycles | 1 | 0 | 0
AvgNumberofTransmittals | 2 | 2 | 0
AvgMailingCostperTransmittal($/Transmittal) | 18.8 | 0 | 0
AvgTimetoPrepareTransmittal(hours/transmittal) | 0.17 | 0.068 | -0.102
AvgTimeSpentRecreatingProductProgramCriteria(hours/product) | 0.08 | 0 | 0 | 94
AvgTimetoCompareProductProgramwithOwnerStandards(hours/product) | 2.15 | 0.215 | -1.935
AvgPercentageoferrorsinProductProgram | 0.3 | 0.03 | -0.27
AvgTimeSpentRecreatingProductProgram(hours/product) | 0.08 | 0 | 0
AvgNumberofReviewCycles | 1 | 0 | 0
AvgNumberofTransmittals | 2 | 2 | 0
AvgMailingCostperTransmittal($/Transmittal) | 23.95 | 0 | 0
AvgTimetoPrepareTransmittal(hours/transmittal) | 0.17 | 0.068 | -0.102
AvgNumberofLetterSizedPagesinRFP(pages/proposal) | 6 | 6 | 0 | 103
AvgNumberofDrawingSheetsinProposal(sheets/proposal) | 2 | 2 | 0
NumberofRFPcopiesReqd(sets/submittal) | 5 | 0 | 0
AvgNumberofTransmittals-OwnersRepdocumentstoBidders | 5 | 5 | 0
AvgNumberofTransmittals-ArchitecttoOwner | 1 | 1 | 0
AvgIn-houseReproductionTimePerSubmittalSet(hours/submittalset) | 0.0095556 | 0 | 0
AvgMailingCostperTransmittal($/Transmittal)-OwnersRepdocumentstoBidders | 16.5 | 0 | 0
AvgMailingCostperTransmittal($/Transmittal)-ArchitecttoOwnersRep | 16.5 | 0 | 0
AvgTimetoPrepareTransmittal(hours/transmittal)-OwnersRep | 0.75 | 0.3 | -0.45
AvgTimetoPrepareTransmittal(hours/transmittal)-Architect | 1 | 0.4 | -0.6
AvgTimeSpentReformattingSpaceProgramRequirements(hours/spacetype) | 0.16 | 0 | 0 | 114
AvgTimeSpentReformattingEquipmentType(hours/product) | 0.25 | 0 | 0
AvgTimeSpentEvaluatingDesignEarlyDrawingsagainstDesignRequirements-SpaceandEquipment | 9.15 | 0.915 | -8.235
AvgTimespentmakingcorrectionsduetonon-conformancewithSpaceorProductProgram | 1.5189 | 0 | 0
AvgTimetoCompareDesignEarlyDocumentswithOwnerStandards | 3.08 | 0.308 | -2.772
AvgNumberofReviewCycles | 1 | 0 | 0
PercentageofTimeSpentbyLicensedProfessionalArchitect | 0.9 | 0.9 | 0
PercentageofTimeSpentbyArchitectDrafter | 0.1 | 0.1 | 0
AvgNumberofTransmittals | 1 | 1 | 0
AvgIn-houseReproductionTimePerSubmittalSet(hours/submittalset) | 0.11037 | 0 | 0
AvgMailingCostperTransmittal($/Transmittal)-OwnersReptoArchitect | 16.5 | 0 | 0
AvgMailingCostperTransmittal($/Transmittal)-ArchitecttoOwnersRep | 21.6 | 0 | 0
AvgTimetoPrepareTransmittal(hours/transmittal) | 0.5 | 0.2 | -0.3
AvgNumberofPlanDrawingsinDesignSchematicDrawings | 11.2 | 11.2 | 0 | 128
AvgTimeSpentDevelopingEquipment(product)TypeTemplate(hours/producttype) | 0.25 | 0.075 | -0.175
AvgTimeSpentEvaluatingDesignSchematicDrawingsagainstDesignRequirements-SpaceandEquipment | 24.4 | 2.44 | -21.96
AvgTimespentmakingcorrectionsduetonon-conformancewithSpaceorProductProgram | 2.2784 | 0 | 0
AvgTimetoCompareDesignSchematicDocumentswithOwnerStandards | 3.696 | 0.3696 | -3.3264
AvgNumberofReviewCycles | 1 | 0 | 0
PercentageofTimeSpentbyLicensedProfessionalArchitect | 0.8 | 0.8 | 0
PercentageofTimeSpentbyArchitectDrafter | 0.2 | 0.2 | 0
AvgNumberofTransmittals | 1 | 1 | 0
AvgIn-houseReproductionTimePerSubmittalSet(hours/submittalset) | 0.13911 | 0 | 0
AvgMailingCostperTransmittal($/Transmittal)-OwnersReptoArchitect | 16.5 | 0 | 0
AvgMailingCostperTransmittal($/Transmittal)-ArchitecttoOwnersRep | 25.8 | 0 | 0
AvgTimetoPrepareTransmittal(hours/transmittal) | 0.5 | 0.2 | -0.3
AvgNumberofPlanDrawingsinDesignCoordinatedDrawings | 11.2 | 11.2 | 0 | 142
AvgTimeSpentDevelopingDetailedEquipment(products)TypeTemplate(hours/product) | 2 | 0.6 | -1.4
AvgTimeSearchingforProductLiteratureforCandidates(Hours/product) | 1 | 0.1 | -0.9
AvgTimeSpentEvaluatingDesignCoordinatedDrawingsagainstDesignRequirements-SpaceandEquipment | 28.06 | 2.806 | -25.254
AvgTimeSpentmakingCorrectionsduetoNon-ConformancewithSpaceorProductProgram | 1.2658 | 0 | 0
AvgPercentofErrorsinProductTypeCandidate | 0.15 | 0.015 | -0.135
AvgTimetoCompareDesignCoordinated&ProductTypeCandidateDocumentswithOwnerStandards | 4.4 | 0.44 | -3.96
AvgNumberofReviewCycles | 1 | 0 | 0
PercentageofTimeSpentbyLicensedProfessionalArchitect | 0.8 | 0.8 | 0
PercentageofTimeSpentbyArchitectDrafter | 0.2 | 0.2 | 0
AvgNumberofTransmittals | 1 | 1 | 0
AvgIn-houseReproductionTimePerSubmittalSet(hours/submittalset) | 0.19481 | 0 | 0
AvgMailingCostperTransmittal($/Transmittal)-OwnersReptoArchitect | 16.5 | 0 | 0
AvgMailingCostperTransmittal($/Transmittal)-ArchitecttoOwnersRep | 28.95 | 0 | 0
AvgTimetoPrepareTransmittal(hours/transmittal) | 0.5 | 0.2 | -0.3
AvgNumberofPlanDrawingsinDesignFinalDrawings | 11.2 | 11.2 | 0 | 158
AvgTimeSpentDevelopingDetailedEquipment(products)TypeCandidate(hours/product) | 1 | 0.1 | -0.9
AvgTimeSpentEvaluatingDesignFinalDrawingsagainstDesignRequirements-SpaceandEquipment | 26.23 | 2.623 | -23.607
AvgTimeSpentmakingCorrectionsduetoNon-ConformancewithSpaceorProductProgram | 0.5063 | 0 | 0
PercentageofTimeSpentbyLicensedProfessionalArchitect | 0.9 | 0.9 | 0
PercentageofTimeSpentbyArchitectDrafter | 0.1 | 0.1 | 0
AvgNumberofTransmittals | 1 | 1 | 0
AvgIn-houseReproductionTimePerSubmittalSet(hours/submittalset) | 0.20222 | 0 | 0
AvgMailingCostperTransmittal($/Transmittal)-OwnersReptoArchitect | 16.5 | 0 | 0
AvgMailingCostperTransmittal($/Transmittal)-ArchitecttoOwnersRep | 32.75 | 0 | 0
AvgTimetoPrepareTransmittal(hours/transmittal) | 1 | 0.4 | -0.6
AvgNumberofTransmittals | 5 | 5 | 0 | 170
AvgIn-houseReproductionTimePerSubmittalSet(hours/submittalset) | 0.20889 | 0 | 0
AvgMailingCostperTransmittal($/Transmittal) | 32.75 | 0 | 0
AvgTimetoPrepareTransmittal(hours/transmittal) | 0.75 | 0.3 | -0.45
AvgNumberofRequestforProposalSubmittalSetsReqd | 1 | 0 | 0
AvgNumberofTransmittals | 3 | 3 | 0 | 176
AvgMailingCostperTransmittal($/Transmittal) | 16.5 | 0 | 0
AvgTimetoPrepareTransmittalsforInquiryIssues(hours/transmittal)-Contractor/Architect | 0.17 | 0.068 | -0.102
AvgTimetoPrepareTransmittalsforInquiryIssues(hours/transmittal)-OwnersRep | 0.083 | 0.0332 | -0.0498
AvgNumberofRFIs | 29 | 2.9 | -26.1 | 183
AvgMailingCostperTransmittal($/Transmittal) | 16.5 | 0 | 0
AvgTimetoPrepareTransmittalsforInquiryIssues(RFI)(hours/transmittal)-Contractor/Architect | 0.17 | 0.068 | -0.102
AvgTimetoPrepareTransmittalsforInquiryIssues(RFI)(hours/transmittal)-Owner | 0.03 | 0.012 | -0.018
AvgTimeSpentOrganizingEquipment(product)Typeinformation(hours/submittalitem) | 0.17 | 0.068 | -0.102 | 192
AvgTimeSpentEvaluatingEquipment(product)TypeSubmittalItemsagainstContractDocuments(hours/submittalitem) | 0.5 | 0.05 | -0.45
AvgTimetoSigneachPage(hours/page) | 0.083 | 0 | 0
AvgTimetoStampeachSheet(hours/sheet) | 0.083 | 0 | 0
PercentageofSubmittalsItemsrejected | 0.2 | 0.2 | 0
PercentageofTimeSpentbyConstructionProjectManager | 0.1 | 0.1 | 0
PercentageofTimeSpentbyAssistant(Construction)ProjectManager | 0.9 | 0.9 | 0
AvgNumberofTransmittals | 30 | 30 | 0
AvgIn-houseReproductionTimePerSubmittalSet(hours/submittalset) | 0.014778 | 0 | 0
AverageMailingCostsperTransmittal($) | 16.5 | 0 | 0
AvgTimetoPrepareTransmittal(hours/transmittal) | 0.5 | 0.2 | -0.3
AvgTimeSpentEvaluatingProductTypeSubmittalItemsagainstContractDocuments(hours/producttypesubmittalitem) | 1 | 0.1 | -0.9 | 204
AvgTimeSpentRevisingoneProductSubmittalItem(hours/product) | 0.5 | 0.05 | -0.45
PercentageofProductSubmittalsreviewedbyLicensedArchitect | 0.75 | 0.75 | 0
PercentageofProductSubmittalsrejectedonfirstreview | 0.43 | 0.043 | -0.387
PercentageofProductSubmittalsrejectedonsecondreview | 0.25 | 0 | 0
PercentageofProductSubmittalsrejectedonthirdreview | 0 | 0 | 0
AvgTimeSpentTransferringCommentsperPage | 0.033 | 0 | 0
AvgTimeSpentTransferringCommentsperSheet | 0.083 | 0 | 0
PercentageofTimeSpentbyConstructionProjectManager | 0.8 | 0.8 | 0
PercentageofTimeSpentbyAssistant(Construction)ProjectManager | 0.2 | 0.2 | 0
AvgNumberofTransmittals | 3 | 3 | 0
AvgTimetoPrepareTransmittal(hours/transmittal) | 0.083 | 0.0332 | -0.0498
AvgMailingCostperTransmittal | 16.5 | 0 | 0
Avg.TimeSpentRe-formattingProductInstallationReportinOffice(hours/ component) | 0.17 | 0 | 0 | 220
AvgNumberofTransmittals(Transmittals) | 2 | 2 | 0
AvgMailingCostperTransmittal($/Transmittal) | 16.5 | 0 | 0
AvgTimetoPrepareaTransmittal(hours/transmittal) | 0.083 | 0.0332 | -0.0498
Avg.FieldTimeSpentDocumentingReportperSiteVisit(hours / visit) | 1.5 | 0.6 | -0.9 | 227
AvgNumberofSiteVisitspermonth | 4 | 4 | 0
AvgNumberofMonthsofConstruction | 12 | 12 | 0
TotalTimeSpentinOffice(hours/day) | 8 | 8 | 0
AvgPercentageofOfficeTimeSpentQuantifyingproductsinplace | 0.25 | 0.025 | -0.225
AvgNumberofTransmittals | 2 | 2 | 0
AvgMailingCostperTransmittal($/Transmittal) | 16.5 | 0 | 0
AvgTimetoPrepareTransmittal(hours/transmittal) | 0.083 | 0.0332 | -0.0498
AvgTimeSpentSearchingandAssemblingOperations&MaintenanceManuals(hours/document) | 3 | 0.3 | -2.7 | 238
AvgTimeSpentSearchingandAssemblingCommissioningReport(hours/document) | 0.0008 | 8e-05 | -0.00072
AvgTimeSpentSearchingandAssemblingRecordSpecifications(hours/document) | 0.008 | 0.0008 | -0.0072
AvgTimeSpentSearchingandAssemblingRecord(As-Built)Drawings(hours/sheet) | 0.008 | 0.0008 | -0.0072
AvgTimeSpentSearchingandAssemblingFinalApprovedShopDrawings(hours/sheet) | 0.0083 | 0.00083 | -0.00747
AvgNumberofPagesinOperations&MaintenanceManuals | 645 | 645 | 0
AvgNumberofPagesinCommissioningReport | 10 | 10 | 0
Avg. Number of Components & Systems to be Commissioned | 20 | 20 | 0
AvgNumberofPagesinRecordSpecifications | 50 | 50 | 0
AvgNumberofSheetsinRecord(As-Built)Drawings | 90 | 90 | 0
AvgNumberofSheetsinFinalApprovedShopDrawings | 1 | 1 | 0
AvgTimeSpentReviewingOperations&MaintenanceManuals(hours/page) | 0.0017 | 0.0017 | 0
AvgTimeSpentReviewingCommissioningReport(hours/page) | 0.0083 | 0.0083 | 0
AvgTimeSpentReviewingRecordSpecifications(hours/page) | 0.0017 | 0 | 0
AvgTimeSpentReviewingRecord(As-Built)Drawings(hours/sheet) | 0.0083 | 0.0083 | 0
AvgTimeSpentReviewingFinalApprovedShopDrawings(hours/sheet) | 0.0083 | 0 | 0
AvgTimeSpentFilingOperations&MaintenanceManuals(hours/document) | 0.083 | 0 | 0
AvgTimeSpentFilingCommissioningReport(hours/document) | 0.083 | 0 | 0
AvgTimeSpentFilingRecordSpecifications(hours/document) | 0.083 | 0 | 0
AvgTimeSpentFilingRecord(As-Built)Drawings(hours/sheet) | 0.0017 | 0 | 0
AvgTimeSpentFilingFinalApprovedShopDrawings(hours/sheet) | 0.0017 | 0 | 0
PercentageofTimeSpentbyConstructionProjectManager | 0.1 | 0.1 | 0
PercentageofTimeSpentbyAssistant(Construction)ProjectManager | 0.9 | 0.9 | 0
AvgIn-houseReproductionTimePerSubmittalSet(hours/submittalset) | 0.72278 | 0 | 0
AvgMailingCostperTransmittal($/Transmittal) | 42.5 | 0 | 0
AvgTimetoPrepareTransmittal(hours/transmittal) | 0.5 | 0.2 | -0.3
TotalDelta |  |  | -132.7252
210 | # Of line items

## Intro
COBie Calculator
Purpose: | This research will identify the potential savings/cost for a project team if information is exchanged using a COBie-based approach over the traditional “Paper-Based” approach.
Project Phase Color Coding:
Criteria
Project Definition
Requirement
Bidding
Design
Construction
Assumptions Tab | Assumptions were made when developing the COBie Calculator. These assumptions should be modified based on your project variables in order to calculate the potential savings.
Information Attributes | L E G E N D
| Color | Description | Allowed User Actions
|  | user defined information unique to this worksheet | change on inputs worksheet in project phase variables section
|  | common user information, listed on assumptions worksheet | change on inputs worksheet
|  | calculated information | do not change this cell

## Short Form Variables
Variables | Value | Unit | Definitions
PROJECT TYPE
Scaling Variables
Estimated Number of Pages in Facility Criteria | 2 | pages | Estimated number of pages in Owners initial analysis of Project need and Scope.
Estimated Number of Pages in Discipline Specification | 52 | pages | Estimated number of pages in Equipment performance requirements during planning
Estimated Number of Pages in Project Definition | 2 | pages | Estimated number of pages in Project Definition document. The Project Definition defines the project scope, budget requirements, site details, economic analysis and facility planning data
Estimated Number of Pages in Front Matter | 10 | pages | Estimated number of pages that precede the technical content of the RFP for Design Services and Construction Services.
Number of Space Types per Project | 18 | Space Types /project | Number of space types (by function) found in each project
Number of Unique Product Types | 43 | Product Types/project | Number of different product types that will be installed.
Number of Tagged Components | 23200 | components / project | Total number of pieces of equipment that will have asset tags and will be managed by the owner
Number of Pre-Design Submittal Sets Reqd. | 4 | sets/submittal | Number of pre-design drawing sets required for each submittal.
Estimated Number of Sheets per Option | 3 | sheets | Estimated number of drawing sheets included in each option.
Estimated Number of Letter Sized Pages in Pre-Design Narrative per Option | 10 | pages | Estimated number of pages included in the pre-design narrative per option.
Number of Design Submittal Sets Reqd. | 6 | sets/submittal | Number of Design Phase drawing sets required
Estimated Number of Letter- Sized pages in Design Narratives | 20 | pages | Estimated number of pages in each phase of the Design Early, Schematic, Coordinated and Final Phase
Estimated Number of Letter Sized pages in Specification | 50 | pages | Estimated number of pages in Specification documents at each phase of the Design Schematic, Coordinated and Final Phase
Number of Submittal Sets Reqd. | 6 | sets/submittal | Number of construction phase submittal sets required
Estimated Number of Letter Sized Pages in Proposal | 6 | pages | Estimated number of Letter-Sized Pages in Proposal
Estimated Number of Drawing Sheets in Proposal | 2 | sheets | Estimated number of sheets included in the Proposal
Number of RFP copies Reqd. | 5 | sets / submittal | Number of RFP sets required
Avg Number of Months of Construction | 12 | months | Average construction duration of a project
Number of Floors / levels | 2 | floors/project | Number of floors within each project
Number of 1/8" = 1' 0" Plan Drawings per Sheet | 2 | plans / sheet | Number of 1/8"= 1' 0" floor plans on a drawing sheet
Number of Design Disciplines | 7 | disciplines/project | Architectural, Structural, Mechanical, Electrical etc
Printing Speed
Small Printer - Letter Sized Pages | 25 | Pages / minute | Number of Letter Sized Pages printed per minute
Large Printer - E1 Size Sheets | 6 | Sheets / minute | Number of Sheets printed per minute
Reduction Factors
Validation
Avg. Time for Owner / Owners Rep to Validate | 90% | % | Average time spent by Owners Rep in validating documents received from third parties is reduced by 90% due to the ability to programmatically check the space and product data.
Avg. Time Spent Evaluating | 90% | % | Average time spent by Architect in validating Design drawings and submittal packages against space and equipment requirements before submission to Owners Rep is reduced by 90% due to ability to programmatically check information for completeness, conformance to standards and conformance to requirements.
Avg. Time Spent in the Field | 60% | %
Avg. Time Spent in the Office | 90% | %
Avg. Number of RFI's | 90% | %
Avg. Time spent making corrections due to non-conformance - space and product | 100% | % | Average time spent by Architect making corrections to space and product documentation based on feedback from Owner / Owners Rep is eliminated due to the use of a standard, structured data format and ability to programmatically check space and product data.
Avg. Time to Sign & Stamp Documents by Contractor | 100% | % | Average time required by Contractor to sign pages and stamp sheets eliminated due to use of an electronic collaboration system.
Avg. Percentage of Submittals Rejected on 1st Review | 90% | %
Avg. Percentage of Submittals Rejected on subsequent reviews | 100% | %
Average Time Reviewing Manuals, Reports and Drawings | 0% | %
Average Time Reviewing Specifications and Shop Drawings | 100% | %
Copying
Avg. In-house Reproduction Time Per Set (hours/set) | 100% | % | Average time spent in printing and making copies of documents is eliminated due to an electronic collaboration system.
Avg. Copying Costs | 100% | % | Copying cost eliminated due to use of an electronic collaboration system.
Avg. Time Spent Transferring Comments | 100% |  | Avergae time spent by Architect in marking up copies of submittals eliminated due to use of an electronic collaboration system.
Handling
Avg. Time to Prepare Transmittal (hours / transmittal) | 60% | % | Average time spent in compiling documents for transmittal is reduced by 60%
Time to Log | 100% | % | Time spent logging documents In and Out is eliminated due to an electronic collaboration system.
Number of Sets Required | 100% | % | Number of sets required for documentation to be submitted to different role players on a project is eliminated due to an electronic collaboration system.
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 100% | % | Average cost for mailing documents/comments is eliminated due to the use of an electronic collaboration system.
Avg. Time Spent Filing Documents | 100% | %
Searching
Avg. QTO Time - Space and Equipment | 90% | % | Average time spent performing quantity take-off of space and equipment shown on plan drawings is reduced by 90%
Avg. Time Spent Revising | 90% | % | Average Time spent by Contractor recreating Submittal Items is reduced by 90% dut to use of a standard, structured data format.
Avg. Time Spent Searching | 90% | % | Average Time spent by Architect in searching for product data is reduced by 90% due to the ability to electronically compare information
Avg. Number of Re-Submit Cycles | 100% | % | Number of times submitted documents are re-submitted is eliminated due to the use of a standard, structured data format for moving information.
Reformatting
Average Time Spent Organizing Equipment (product) Type information (hours / submittal item) | 60% | % | Average Time spent by asst. project manager in producing submittal packages by organizing equipment type information is reduced by 60% due to the adoption of a single,open standard data format.
Avg. Time Spent Developing Equipment (product) Type Template | 70% | % | Avg. time spent by Architect in developing specifications for equipment types required for the project is reduced by 70% due to the use of a standard, structured data format.
Avg. Time Spent Developing Equipment Detailed (product) Type Candidate | 90% | % | Average time spent by Architect in preparing a detailed specifications for equipment types required for the project is reduced by 90% due to the use of a standard, structured data format.
Avg. Time Spent Reformatting | 100% | % | Average time spent reformatting information at different stages of a project is eliminated due to use of a single, open standard data format for information relating to managed assets.
Recreating
Avg. Percentage of errors | 90% | % | Average percentage of errors is eliminated due to the use of a standard, structured data format from the onset of a project.
Avg. Time Spent Recreating | 100% | % | Average time spent recreating information at different stages of a project is eliminated due to use of a standard, structured data format for moving space and equipment information.

## Current Assumptions
Inputs Red text indicates variables populated based on Scaling Variables found in Short Form Variables Tab | Value
| Short Form Value | Override Value | Final Value | Unit | Definitions | Tab Reference
Owner Project / Program Variables
Avg. Number of Pages in Facility Criteria | 2 | N/A | 2 | pages | Estimated number of pages in Owners initial analysis of Project need and Scope. | 10
Avg. Number of Pages in Discipline Specification | 52 | N/A | 52 | pages | Estimated number of pages in Equipment performance requirements during planning | 20
Avg. Number of Pages in Project Definition | 2 | N/A | 2 | pages | Estimated number of pages in Project Definition document. The Project Definition defines the project scope, budget requirements, site details, economic analysis and facility planning data | 40,70,80
Avg. Number of Pages in Front Matter | 10 | N/A | 10 | pages | Estimated number of pages that precede the technical content of the RFP for Design Services and Construction Services. | 70, 120
Project Variables
Number of Space Types per Project | 18 | N/A | 18 | space types / project | Average number of space types found in building. | 50,80
Number of Unique Product Types (Types / project) | 43 | N/A | 43 | Product Types / project | Number of different equipment types that will be installed. | 60,80,90,100,110,180,190, 250
Number of Tagged Components (components / project) | 23200 | N/A | 23200 | components / project | Total number of pieces of equipment that will have asset tags and will be managed by the owner | 210
Time to Log (hours / transmittal) | 0.25 | N/A | 0.25 | hours / transmittal | Time spent logging documents In and Out | 30,50,60,70,80,90,100,110,120,130,150,180,190,210,230,250
Pre-Design Variables
Avg. Number of Options | 3 | N/A | 3 | count | Average number of pre-design options created by the planner for early analysis of concepts. | 30
Avg. Number of Pre-Design Submittal Sets Reqd. (sets / submittal) | 4 | N/A | 4 | sets / submittal | Average number of pre-design drawing sets required for each submittal. | 30,50,60,70
Avg. Number of Sheets per Option | 3 | N/A | 3 | sheets | Average number of drawing sheets included in each option. | 30
Avg. Number of Letter-Sized Pages in Pre-Design Narrative per Option | 10 | N/A | 10 | pages | Average number of pages included in the pre-design narrative per option. | 30
Avg. Number of Pages in Space Program | 5.94 | N/A | 5.94 | pages | Average number of pages in Owner’s space program document. | 50,70,80
Avg. Number of Pages in Product Program | 14.19 | N/A | 14.19 | pages | Average number of pages in Product Program that documents Owners equipment specifications and performance | 60,70,80
Design Variables
Number of Design Submittal Sets Reqd. (sets / submittal) | 6 | N/A | 6 | sets / submittal | Number of Design Phase drawing sets required | 80,90,100,110
Avg. Number of Sheets in Design Early Drawings | 37.3333 | N/A | 37.3333 | drawings | Average number of Design Early (Schematic Design) drawings. | 80
Avg. Number of Letter-Sized Pages in Design Early Narrative | 10 | N/A | 10 | pages | Average number of letter-sized pages in the Design Early narrative. | 80
Avg. Number of Sheets in Design Schematic Drawings | 44.8 | N/A | 44.8 | drawings | Average number of Design Schematic (Design Development) drawings | 90
Avg. Number of Letter Sized Pages in Design Schematic Narrative | 20 | N/A | 20 | pages | Average number of letter-sized pages in the Design Schematic narrative | 90
Avg. Number of Letter Sized Pages in a Design Schematic Specification | 2 | N/A | 2 | pages | Average number of letter-sized pages in the Design Schematic (Design Development) specifications. | 90
Avg. Number of Sheets in Design Coordinated Drawings | 53.3333 | N/A | 53.3333 | drawings | Average number of Design Coordinated drawings | 100
Avg. Number of Letter Sized Pages in a Design Coordinated Narrative | 20 | N/A | 20 | pages | Average number of letter-sized pages in the Design Coordinated narrative. | 100
Avg. Number of Letter Sized Pages in a Design Coordinated Specification | 50 | N/A | 50 | pages | Average number of letter-sized pages in the Design Coordinated specifications. | 100
Avg. Number of Sheets in Design Final Drawings | 56 | N/A | 56 | drawings | Average number of Design Final drawings. | 110,120
Avg. Number of Letter Sized 'Pages in Design Final Narrative | 20 | N/A | 20 | pages | Average number of letter-sized pages in the Design Final narrative. | 110,120
Avg. Number of Letter Sized Pages in Design Final Specification | 50 | N/A | 50 | pages | Average number of letter-sized pages in the Design Final specifications. | 110,120
Estimating Process Variables
Avg QTO Time for Equipment Components (hours / plan drawing) | 0.08 | N/A | 0.08 | hours / plan drawing | Average time spent performing quantity take-off of equipment shown on plan drawings. | 90,100,110
Avg QTO Time for Spaces in building (hours / plan drawing) | 0.16 | N/A | 0.16 | hours / plan drawing | Average time spent performing quantity take-off of spaces shown on plan drawings. | 90,100,110
Submittal Process Variables
Number of Submittal Sets Reqd. (sets / submittal) | 6 | N/A | 6 | sets / submittal | Number of construction phase submittal sets required | 180,190,250
Avg. Number of Submittal Items in a Product Submittal Package (submittal items/submittal package) | 3 | N/A | 3 | submittal items / submittal package | Average number of product Items per submittal package | 180,190
Avg. Number of Submittal Pages in a Submittal Item (pages/submittal item) | 18 | N/A | 18 | pages/submittal item | Average number of letter-sized pages per submittal item | 180,190
Avg. Number of Submittal Sheets in a Submittal Item (sheets/submittal item) | 1 | N/A | 1 | sheets/submittal item | Average number of drawings per submittal item | 180,190
Organizational Variables
Owner Administrative Rate ($ / hour) | 23.71 | N/A | 23.71 | $ / hour | Rate for activities that cover Handling of documents | 10,20,30,40,250
Owners Rep. Rate ($ / hour) | 62.2 | N/A | 62.2 | $ / hour | Rate for activities that include Validating of documents | 50,60,80,90,100
Owners Rep. Administrative Rate ($ / hour) | 16.88 | N/A | 16.88 | $ / hour | Rate for activities that cover Handling of documents | 50,60,70,80,90,100,110,120,130,150,180
Planner Rate ($ / hour) | 37.84 | N/A | 37.84 | $ / hour | Rate for professional assisting owner in Pre-design activities. | 50,60
Planner Administrative Rate ($ / hour) | 16.82 | N/A | 16.82 | $ / hour | Rate for activities that cover Handling of documents | 30,50,60
Licensed Professional Architect Rate ($ / hour) | 109.99 | N/A | 109.99 | $ / hour | Rate including Professional Services, Overhead and Profit | 80,90,100,110,190,230
Specifier | 109.99 | N/A | 109.99 | $ / hour | Rate including Professional Services, Overhead and Profit | 90100110
Architect Drafter Rate ($ / hour) | 70.7 | N/A | 70.7 | $ / hour | Rate including Professional Services, Overhead and Profit | 70,80,90,100,110,130,150,180,190,210,230
Architect Administrative Rate ($ / hour) | 45.96 | N/A | 45.96 | $ / hour | Rate for activities that cover Handling of documents
Construction Project Manager Rate ($ / hour) | 125.81 | N/A | 125.81 | $ / hour | Rate including Professional Services, Overhead and Profit | 180190200210250
Assistant (Construction) Project Manager Rate ($ / hour) | 70.53 | N/A | 70.53 | $ / hour | Rate including Professional Services, Overhead and Profit | 180190210250
Contractor Administrative Rate ($ / hour) | 44.19 | N/A | 44.19 | $ / hour | Rate for activities that cover Handling of documents | 130, 150, 180, 190, 210, 230, 250
General Repro/Postal Delivery Cost
Avg. Per Page Copy Cost ($ / page) | 0.15 | N/A | 0.15 | $ / sheet | - | 10,20,30,40,50,60,70,80,90,100,110,120,180,250
Avg. Per Sheet Copy Cost ($ / sheet) | 3 | N/A | 3 | $ / sheet | - | 30,70,80,90,100,110,120,180,250
Process Specific Variables
Facility Criteria
Avg. Number of Sets Required (sets / submittal) | 2 | N/A | 2 | sets / submittal | Average number of sets required
Avg. In-house Reproduction Time Per Set (hours/set) | 0.0013333 | N/A | 0.0013333 | hours/set | Average time spent in printing and making copies of Facility Criteria by Owner
Discipline Specification
Avg. Number of Sets Required (sets / submittal) | 2 | N/A | 2 | sets | Average number of sets required
Avg. In-house Reproduction Time Per Set (hours/set) | 0.034667 | N/A | 0.034667 | hours/set | Average time spent in printing and making copies of Discipline Specification by Owner
Feasibility Study
Avg. Number of Transmittals | 2 | N/A | 2 | Transmittals | Average number of times options / comments are exchanged between the Planner and Owner times the number of recipients for each exchange
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 0.015 | N/A | 0.015 | hours / submittal set | Average time spent in printing and making copies of feasibility study by Planner
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 18.8 | N/A | 18.8 | $ / Transmittal | Average cost for delivering documents/comments sent between Planner and Owner
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.5 | N/A | 0.5 | hours / transmittal | Average time spent in compiling documents for transmittal
Project Definition
Avg. Number of Sets Required (sets / submittal) | 2 | N/A | 2 | sets | Average number of sets required
Avg. In-house Reproduction Time Per Set (hours/set) | 0.0013333 | N/A | 0.0013333 | hours/set | Average time spent in printing and making copies of Project Definition by Owner
Space Program
Avg. Time Spent Searching for Space Program Criteria (hours/space) | 0.25 | N/A | 0.25 | hours / space | Average time spent by Planner searching for Spatial requirements
Avg. Time Spent Reformatting Space Program Criteria into Room Data Sheets (hours/space) | 0.08 | N/A | 0.08 | hours / space | Average time spent in evaluating information in Project Definition and identifying and creating a detailed spatial program in a usable format.
Avg. Time for Owners Rep to Validate Space Program (hours) | 0.72 | N/A | 0.72 | hours | Average time spent by Owners Rep in validating Space Program provided by planner
Avg. Percentage of errors in Space Program | 30% | N/A | 30% | % | Average percentage of errors found by Owners Rep in Space Program
Avg. Time Spent Re - Searching for Space Program Criteria (hours/space) | 0.25 | N/A | 0.25 | hours / space | Average time spent by Planner recreating Space Program
Avg. Number of Re-Submit Cycles | 1 | N/A | 1 | Cycles | Average number of times submitted documents are re-submitted.
Avg. Number of Transmittals | 2 | N/A | 2 | Transmittals | Average number of times Space Program / Comments are sent between the Planner and Owners Rep times the number of recipients for each exchange.
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 18.8 | N/A | 18.8 | $ / Transmittal | Average cost for delivering documents/comments sent between Planner and Owners Rep
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.17 | N/A | 0.17 | hours / transmittal | Average time spent in compiling documents for transmittal
Product Program
Avg. Time Spent Searching for Product Program Criteria (hours / product) | 0.08 | N/A | 0.08 | hours / product | Average time spent by Planner searching for Product Program Criteria
Avg. Time for Owners Rep to Validate Product Program (hours) | 2.15 | N/A | 2.15 | hour | Average time spent by Owners Rep in validating Product Program provided by Planner
Avg. Percentage of errors in Product Program | 30% | N/A | 30% | % | Average percentage of errors found by Owners Rep in Product Program
Avg. Time Spent Re - Searching for Product Program Criteria (hours / product) | 0.08 | N/A | 0.08 | hours / space | Average time spent by Planner recreating Product Program
Avg. Number of Re-Submit Cycles | 1 | N/A | 1 | Cycles | Average number of times submitted documents are re-submitted
Avg. Number of Transmittals | 2 | N/A | 2 | Transmittals | Average number of times Product Program / Comments are sent between the Planner and Owners Rep times the number of recipients for each exchange.
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 23.95 | N/A | 23.95 | $ / Transmittal | Average cost for mailing documents/comments sent between Planner and Owners Rep.
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.17 | N/A | 0.17 | hours / transmittal | Average time spent in compiling documents for transmittal.
Request for Proposal
Avg. Number of Letter Sized Pages in Proposal (pages / proposal) | 6 | N/A | 6 | pages / proposal | Average number of Letter-Sized Pages in Proposal
Avg. Number of Drawing Sheets in Proposal (sheets / proposal) | 2 | N/A | 2 | sheets / proposal | Average number of sheets included in the Proposal
Number of RFP copies Reqd. (sets / submittal) | 5 | N/A | 5 | sets / submittal | Number of RFP copies required
Avg. Number of Transmittals - Owners Rep documents to Bidders | 5 | N/A | 5 | Transmittals | Average number of times Proposal is sent from the Owners Rep to the Bidders times the number of recipients for each exchange.
Avg. Number of Transmittals - Architect to Owner | 1 | N/A | 1 | Transmittals | Average number of times Proposal is sent from the Architect to the Owners Rep times the number of recipients for each exchange.
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 0.0095556 | N/A | 0.0095556 | hours / submittal set | Average time spent in printing and making copies of Proposal by Architect
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Owners Rep documents to Bidders | 16.5 | N/A | 16.5 | $ / Transmittal | Average cost for mailing documents/comments sent between Owners Rep and Architect
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Architect to Owners Rep | 16.5 | N/A | 16.5 | $ / Transmittal | Average cost for mailing proposal between Architect and Owners Rep.
Avg. Time to Prepare Transmittal (hours / transmittal) - Owners Rep | 0.75 | N/A | 0.75 | hours / transmittal | Average time spent in compiling documents for transmittal / submission
Avg. Time to Prepare Transmittal (hours / transmittal) - Architect | 1 | N/A | 1 | hours / transmittal | Average time spent in compiling documents for transmittal / submission
Design Early
Avg. Time Spent Reformatting Space Program (hours / space) | 0.16 | N/A | 0.16 | hours / space | Average time spent by Architect in documenting spatial requirements in a usable format
Avg. Time Spent Reformatting Product Program (hours /product) | 0.25 | N/A | 0.25 | hours / product | Average Time spent by Architect documenting product type requirements in a usable format
Avg. Time Spent Evaluating Design Early Drawings against Design Requirements - Space and Equipment | 9.15 | N/A | 9.15 | hours | Average time spent by Architect in validating Design Early drawings against space and equipment requirements before submission to Owners Rep
Avg. Time spent making corrections due to non-conformance with Space or Product Program | 1.5189 | N/A | 1.5189 | hours | Average time spent by Architect making corrections to space and equipment documentation based on internal validation.
Avg Time to Review Design Early Drawings for conformance to Space and Product Program | 3.08 | N/A | 3.08 | hours | Average time spent by Owner’s Rep. in validating space and equipment documentation in Design Early Documents provided by Architect.
Avg. Number of Re-Submit Cycles | 1 | N/A | 1 | Cycles | Average number of times submitted documents are re-submitted
Percentage of Time Spent by Licensed Professional Architect | 90% | N/A | 90% | % | Percentage of time spent by Licensed Architect reformatting Space and Product Program, evaluating documents and making corrections where necessary.
Percentage of Time Spent by Architect Drafter | 10% | N/A | 10% | % | Percentage of time spent by Architect Drafter reformatting Space and Product Program, copying and sending documents.
Avg. Number of Transmittals | 1 | N/A | 1 | Transmittals | Average number of times drawings, narratives and comments are sent and received between the Architect / Planner and Owner times the number of recipients for each exchange
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 0.11037 | N/A | 0.11037 | hours / submittal set | Average time spent in printing and making copies of drawings and narratives by Architect / Planner
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Owners Rep to Architect | 16.5 | N/A | 16.5 | $ / Transmittal | Average cost for mailing documents/comments sent between Owners Rep and Architect
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Architect to Owners Rep | 21.6 | N/A | 21.6 | $ / Transmittal | Average cost for mailing documents/comments between Architect and Owners Rep.
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.5 | N/A | 0.5 | hours / transmittal | Average time spent compiling copies of drawings, narratives and comments for transmittal by Architect and Owners Rep.
Design Schematic
Avg. Number of Plan Drawings in Design Schematic Drawings | 11.2 | N/A | 11.2 | plans / drawing set | Average number of Plan Drawings
Avg. Time Spent Developing Equipment (product) Type Template (hours / product type) | 0.25 | N/A | 0.25 | hours / product type | Average time spent by Architect in developing specifications for equipment types required for the project
Avg. Time Spent Evaluating Design Schematic Drawings against Design Requirements - Space and Equipment | 24.4 | N/A | 24.4 | hours | Average time spent by Architect in validating Design Schematic drawings against space and equipment requirements before submission to Owners Rep
Avg. Time spent making corrections due to non-conformance with Space or Product Program | 2.2784 | N/A | 2.2784 | hours | Average time spent by Architect making corrections to space and Product Type Templates (Outline Specifications) documentation based on internal validation.
Avg Time to Review Design Schematic Drawings for conformance to Space and Product Program | 3.696 | N/A | 3.696 | hours | Average time spent by Owner’s Rep. in validating Space and Product Type Templates (Outline Specifications) in Schematic Documents provided by Architect.
Avg. Number of Re-Submit Cycles | 1 | N/A | 1 | Cycles | Average number of times submitted documents are re-submitted
Percentage of Time Spent by Licensed Professional Architect | 80% | N/A | 80% | % | Percentage of time spent by Licensed Architect to taking off all equipment pieces and calculating areas, developing equipment type templates, evaluating documents and making corrections where necessary.
Percentage of Time Spent by Architect Drafter | 20% | N/A | 20% | % | Percentage of time spent by Architect Drafter taking off all equipment pieces and calculating areas, copying and sending documents.
Avg. Number of Transmittals | 1 | N/A | 1 | Transmittals | Average number of times schematic drawings, narratives, specifications and comments are sent and received between the Architect / Planner and Owner times the number of recipients for each exchange
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 0.13911 | N/A | 0.13911 | hours/submittal set | Average time spent in printing and making copies of drawings, narratives and specifications by Architect / Planner
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Owners Rep to Architect | 16.5 | N/A | 16.5 | $ / Transmittal | Average cost for mailing documents/comments sent between Owners Rep and Architect
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Architect to Owners Rep | 25.8 | N/A | 25.8 | $ / Transmittal | Average cost for mailing documents/comments between Architect and Owners Rep.
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.5 | N/A | 0.5 | hours / transmittal | Average time spent compiling copies of schematic drawings, narratives, specifications and comments for transmittal by Architect and Owners Rep.
Design Coordinated
Avg. Number of Plan Drawings in Design Coordinate Drawings | 11.2 | N/A | 11.2 | plans / drawing set | Average number of Plan Drawings
Avg. Time Spent Developing Detailed Equipment (products) Type Template (hours / product) | 2 | N/A | 2 | hours / product | Average time spent by Architect in preparing a detailed specifications list based on equipment types
Avg. Time Searching for Product Literature for Candidates (Hours/product) | 1 | N/A | 1 | hours / product | Average time spent by Architect in searching for product data
Avg. Time Spent Evaluating Design Coordinated Drawings against Design Requirements - Space and Equipment | 28.06 | N/A | 28.06 | hours | Average time spent by Architect in validating Design Coordinated drawings against space and equipment requirements before submission to Owners Rep
Avg. Time Spent making Corrections due to Non-Conformance with Space Program | 1.2658 | N/A | 1.2658 | hours | Average time spent by Architect making corrections to space and equipment documentation based on internal validation.
Avg. Percent of Errors in Product Type Candidate | 15% | N/A | 15% | % | Percentage of errors in Product Type List
Avg Time to Review Design Coordinated Drawings for conformance to Space and Product Program | 4.4 | N/A | 4.4 | hours | Average time spent by Owner’s Rep. in validating Space and Product Type Candidates in Schematic Coordinated Drawings provided by Architect.
Avg. Number of Re-Submit Cycles | 1 | N/A | 1 | Cycles | Average number of times submitted documents are re-submitted
Percentage of Time Spent by Licensed Professional Architect | 80% | N/A | 80% | % | Percentage of time spent by Licensed Architect taking off all equipment pieces and calculating areas, developing equipment type templates, searching for product literature, evaluating documents and making corrections where necessary.
Percentage of Time Spent by Architect Drafter | 20% | N/A | 20% | % | Percentage of time spent by Architect Drafter to take off all equipment pieces and to calculate areas, copying and sending documents.
Avg. Number of Transmittals | 1 | N/A | 1 | Transmittals | Average number of times coordinated drawings, narratives, specifications and comments are sent and received between the Architect and Owners Rep times the number of recipients for each exchange
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 0.19481 | N/A | 0.19481 | hours / submittal set | Average time spent in printing and making copies of drawings, narratives and specifications by Architect
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Owners Rep to Architect | 16.5 | N/A | 16.5 | $ / Transmittal | Average cost for mailing documents/comments sent between Owners Rep and Architect
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Architect to Owners Rep | 28.95 | N/A | 28.95 | $ / Transmittal | Average cost for mailing documents between Architect and Owners Rep.
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.5 | N/A | 0.5 | hours / transmittal | Average time spent compiling copies of coordinated drawings, narratives, specifications and comments for transmittal by Architect and Owners Rep
Design Final
Avg. Number of Plan Drawings in Design Final Drawings | 11.2 | N/A | 11.2 | plans / drawing set | Average number of Plan Drawings
Avg. Time Spent Developing Detailed Equipment (products) Type Candidate (hours / product) | 1 | N/A | 1 | hours / product | Average time spent by Architect in preparing a detailed specifications list based on equipment types
Avg. Time Spent Evaluating Design Final Drawings against Design Requirements - Space and Equipment | 26.23 | N/A | 26.23 | hours | Average time spent by Architect in validating Design Final drawings before submission to Owners Rep
Avg. Time Spent making Corrections due to Non-Conformance with Space or Product Program | 0.5063 | N/A | 0.5063 | hours | Average time spent by Architect making corrections based on internal evaluation and feedback from Owners Rep.
Percentage of Time Spent by Licensed Professional Architect | 90% | N/A | 90% | % | Percentage of time spent by Licensed Architect taking off all equipment pieces and calculating areas, developing detailed equipment type candidates, evaluating documents and making corrections where necessary.
Percentage of Time Spent by Architect Drafter | 10% | N/A | 10% | % | Percentage of time spent by Architect Drafter taking off all equipment pieces and calculating areas, copying and sending documents.
Avg. Number of Transmittals | 1 | N/A | 1 | Transmittals | Average number of times final drawings, narratives, specifications and comments are sent and received between the Architect and Owners Rep times the number of recipients for each exchange.
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 0.20222 | N/A | 0.20222 | hours / submittal set | Average time spent in printing and making copies of drawings, narratives and specifications by Architect / Planner
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Owners Rep to Architect | 16.5 | N/A | 16.5 | $ / Transmittal | Average cost for mailing documents/comments sent between Owners Rep and Architect
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Architect to Owners Rep | 32.75 | N/A | 32.75 | $ / Transmittal | Average cost for mailing proposal between Architect and Owners Rep.
Avg. Time to Prepare Transmittal (hours / transmittal) | 1 | N/A | 1 | hours / transmittal | Average time spent compiling copies of final drawings, narratives, specifications for transmittal by Architect
Request for Proposal
Avg. Number of Transmittals | 5 | N/A | 5 | Transmittals | Average number of times RFP Package is sent from Owners Rep to Contractor times the number of recipients for purpose of bidding.
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 0.20889 | N/A | 0.20889 | hours / submittal set | Average time spent in printing and making copies of RFP Package by Owners Rep.
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 32.75 | N/A | 32.75 | $ / Transmittal | Average cost for mailing RFP by Owners Rep.
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.75 | N/A | 0.75 | hours / transmittal | Average time spent compiling documents, drawings or specifications for transmittal by Owners Rep.
Avg. Number of Request for Proposal Submittal Sets Reqd. | 1 | N/A | 1 | submittal sets | Average number of RFP sets required for submission
Inquiry Issue
Avg. Number of Transmittals | 3 | N/A | 3 | Transmittals | Average number of times Inquiry Issues and responses are sent and received between Owners Rep, Architect and Contractor times the number of recipients for each exchange
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 16.5 | N/A | 16.5 | $ / Transmittal | Average cost for mailing documents/comments sent between Owners Rep, Architect, and Contractor
Avg. Time to Prepare Transmittals for Inquiry Issues (hours / transmittal) - Contractor / Architect | 0.17 | N/A | 0.17 | hours / transmittal | Avergae time spent compiling documents, drawings or specifications for transmittal by Architect and Contractor
Avg. Time to Prepare Transmittals for Inquiry Issues (hours / transmittal) - Owners Rep | 0.083 | N/A | 0.083 | hours / transmittal | Average time spent compiling documents, drawings or specifications for transmittal by Owners Rep.
Pre-Construction Plan
Inquiry Issue (RFI)
Avg. Number of RFIs | 29 | N/A | 29 | Transmittals | Average number of formal questions (Request for Information) initiated by the Contractor related to Space and Equipment
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 16.5 | N/A | 16.5 | $ / Transmittal | Average cost for mailing documents/comments sent between Owners Rep, Architect, and Contractor
Avg. Time to Prepare Transmittals for Inquiry Issues (RFI) (hours / transmittal) - Contractor / Architect | 0.17 | N/A | 0.17 | hours / transmittal | Average Time spent compiling Inquiry Issues (RFI) for transmittal by Architect and Contractor
Avg. Time to Prepare Transmittals for Inquiry Issues (RFI) (hours / transmittal) - Owner | 0.03 | N/A | 0.03 | hours / transmittal | Average Time spent compiling Inquiry Issues (RFI) for transmittal by Owners Rep
Product Type Selection
System Layout
Submittal Package
Average Time Spent Organizing Equipment (product) Type information (hours / submittal item) | 0.17 | N/A | 0.17 | hours / submittal item | Average Time spent by asst. project manager in producing submittal packages by organizing equipment type information
Average Time Spent Evaluating Equipment (product) Type Submittal Items against Contract Documents (hours / submittal item) | 0.5 | N/A | 0.5 | hours / submittal item | Average Time spent evaluating submittal items
Avg. Time to Sign each Page (hours / page) | 0.083 | N/A | 0.083 | hours/page | Average time required by Contractor to sign pages of Submittal Package
Avg. Time to Stamp each Sheet (hours / sheet) | 0.083 | N/A | 0.083 | hours/sheet | Average time required by Contractor to stamp sheets of Submittal Package
Percentage of Submittals Items rejected | 20% | N/A | 20% | % | Percentage of items rejected
Percentage of Time Spent by Construction Project Manager | 10% | N/A | 10% | % | Percentage of time spent by Construction Project Manager in validating Submittal Information
Percentage of Time Spent by Assistant (Construction) Project Manager | 90% | N/A | 90% | % | Percentage of time spent by Assistant Construction Project Manager in validating Submittal Information
Avg. Number of Transmittals | 30 | N/A | 30 | Transmittals | The average number of product submittal items sent by the Sub-Contractors and vendors to the Contractor.
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 0.014778 | N/A | 0.014778 | hours / submittal set | Average time spent in printing and making copies of Submittal Package by Contractor
Average Mailing Costs per Transmittal ($) | 16.5 | N/A | 16.5 | $ / Transmittal | Average cost for Mailing documents/transmittals sent between Owners Rep and Contractor
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.5 | N/A | 0.5 | hours / transmittal | Average time spent compiling Submittal Package for transmittal by Architect / Contractor
Submittal Issue
Avg. Time Spent Evaluating Product Type Submittal Items against Contract Documents (hours / product type submittal item) | 1 | N/A | 1 | hours / submittal item | Avergae time spent by Architect evaluating each product type submittal against contract documents
Avg. Time Spent Revising one Product Type Submittal Item (hours / product type submittal item) | 0.5 | N/A | 0.5 | hours / product | Average time spent by Contractor revising each Submittal Item to meet contract requirements and resubmit.
Percentage of Product Submittals reviewed by Licensed Architect | 75% | N/A | 75% | % | Percentage of submittals reviewed by Architect
Percentage of Product Submittals rejected on first review | 43% | N/A | 43% | % | Percentage of submittals rejected upon review
Percentage of Product Submittals rejected on second review | 25% | N/A | 25% | % | Percentage of submittals rejected upon review
Percentage of Product Submittals rejected on third review | 0% | N/A | 0% | % | Percentage of submittals rejected upon review
Avg. Time Spent Transferring Comments per Page | 0.033 | N/A | 0.033 | hours / page | Avergae time spent by Architect in marking up submittal with comments
Avg. Time Spent Transferring Comments per Sheet | 0.083 | N/A | 0.083 | hours / sheet | Avergae time spent by Architect in marking up submittal with comments
Percentage of Time Spent by Construction Project Manager | 80% | N/A | 80% | % | Percentage of time spent by Construction Project Manager in recreating Submittal Package
Percentage of Time Spent by Assistant (Construction) Project Manager | 20% | N/A | 20% | % | Percentage of time spent by Assistant Construction Project Manager in recreating Submittal Package
Avg. Number of Transmittals | 3 | N/A | 3 | Transmittals | Average number of times Submittal Packages (pages and sheets) are sent and received between Architect and Contractor times the number of recipients for each exchange
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.083 | N/A | 0.083 | hours / transmittal | Average time spent compiling Submittal Package for transmittal by Architect
Avg. Mailing Cost per Transmittal | 16.5 | N/A | 16.5 | $ / Transmittal | Average cost for Mailing documents/transmittals between Architect / Planner and Contractor
Purchase Order
Product Installation
Avg. Time Spent Re-formatting Product Installation Report in Office (hours/ component) | 0.17 | N/A | 0.17 | hours / component | Average time spent by Contractor in the office re-formatting report
Avg. Number of Transmittals (Transmittals) | 2 | N/A | 2 | Transmittals | Average number of times Product Installation Reports are sent and received between Contractor and Architect / Owner times the number of recipients for each exchange
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 16.5 | N/A | 16.5 | $ / Transmittal | Average cost for mailing Product Installation Report by Contractor
Avg. Time to Prepare a Transmittal (hours/transmittal) | 0.083 | N/A | 0.083 | hours / transmittal | Average time spent compiling Product Installation for transmittal by Assistant Construction Manager
Start-Up
Product Inspection
Avg. Field Time Spent Documenting Report per Site Visit (hours / visit) | 1.5 | N/A | 1.5 | hours / visit | Average time spent in the field documenting data during site visits.
Avg. Number of Site Visits per month | 4 | N/A | 4 | visits / month | Average number of times site is visited in a month
Avg Number of Months of Construction | 12 | N/A | 12 | months | Average construction duration of a project
Total Time Spent in Office | 8 | N/A | 8 | hours / day | Total time spent in the office on a daily basis
Avg. Percentage of Office Time Spent Quantifying products in place | 25% | N/A | 25% | % | Average percentage of time spent in the office documenting data recorded from the field.
Avg. Number of Transmittals | 2 | N/A | 2 | Transmittals | Average number of times Inspection Reports are sent and received between Architect and Contractor times the number of recipients for each exchange
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 16.5 | N/A | 16.5 | $ / Transmittal | Average cost for mailing Inspection Reports by Architect
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.083 | N/A | 0.083 | hours / transmittal | Average time spent compiling Inspection Report for transmittal by Architect
Punch list Issue
Turnover Package
Avg. Time Spent Searching and Assembling Operations & Maintenance Manuals (hours / document) | 3 | N/A | 3 | hours / document | Time spent compiling O&M Manual
Avg. Time Spent Searching and Assembling Commissioning Report (hours / document) | 0.0008 | N/A | 0.0008 | hours / document | Time spent compiling Commissioning Report
Avg. Time Spent Searching and Assembling Record Specifications (hours / document) | 0.008 | N/A | 0.008 | hours / document | Time spent compiling Record Specifications
Avg. Time Spent Searching and Assembling Record (As-Built) Drawings (hours / sheet) | 0.008 | N/A | 0.008 | hours / sheet | Time spent compiling Record (As-Built) Drawings
Avg. Time Spent Searching and Assembling Final Approved Shop Drawings (hours / sheet) | 0.0083 | N/A | 0.0083 | hours / sheet | Time spent compiling Final Approved Shop Drawings
Avg. Number of Pages in Operations & Maintenance Manuals (pages / product) | 645 | N/A | 645 | pages / product | Number of Pages in Operations & Maintenance Manuals
Avg. Number of Pages in Commissioning Report | 10 | N/A | 10 | pages / component | Number of Pages in Commissioning Report
Avg. Number of Components & Systems to be Commissioned | 20 | N/A | 20 | components | Number of Components to be commissioned
Avg. Number of Pages in Record Specifications | 50 | N/A | 50 | pages | Number of Pages in Record Specifications
Avg. Number of Sheets in Record (As-Built) Drawings | 90 | N/A | 90 | sheets | Number of Sheets in Record (As-Built) Drawings
Avg. Number of Sheets in Final Approved Shop Drawings | 1 | N/A | 1 | sheets | Number of Sheets in Final Approved Shop Drawings
Avg. Time Spent Reviewing Operations & Maintenance Manuals (hours/page) | 0.0017 | N/A | 0.0017 | hours / page | Time Spent Reviewing Operations & Maintenance Manuals
Avg. Time Spent Reviewing Commissioning Report (hours / page) | 0.0083 | N/A | 0.0083 | hours / page | Time Spent Reviewing Commissioning Report
Avg. Time Spent Reviewing Record Specifications (hours / page) | 0.0017 | N/A | 0.0017 | hours / page | Time Spent Reviewing Record Specifications
Avg. Time Spent Reviewing Record (As-Built) Drawings (hours/ sheet) | 0.0083 | N/A | 0.0083 | hours / sheet | Time Spent Reviewing Record (As-Built) Drawings
Avg. Time Spent Reviewing Final Approved Shop Drawings (hours / sheet) | 0.0083 | N/A | 0.0083 | hours / sheet | Time Spent Reviewing Final Approved Shop Drawings
Avg. Time Spent Filing Operations & Maintenance Manuals (hours/document) | 0.083 | N/A | 0.083 | hours / document | Time Spent Filing Operations & Maintenance Manuals
Avg. Time Spent Filing Commissioning Report (hours/document) | 0.083 | N/A | 0.083 | hours / document | Time Spent Filing Commissioning Report
Avg. Time Spent Filing Record Specifications (hours/document) | 0.083 | N/A | 0.083 | hours / document | Time Spent Filing Record Specifications
Avg. Time Spent Filing Record (As-Built) Drawings (hours / sheet) | 0.0017 | N/A | 0.0017 | hours / sheet | Time Spent Filing Record (As-Built) Drawings
Avg. Time Spent Filing Final Approved Shop Drawings(hours / sheet) | 0.0017 | N/A | 0.0017 | hours / sheet | Time Spent Filing Final Approved Shop Drawings
Percentage of Time Spent by Construction Project Manager | 10% | N/A | 10% | % | Percentage of time spent by Construction Project Manager in compiling Turnover Package
Percentage of Time Spent by Assistant (Construction) Project Manager | 90% | N/A | 0.9 | % | Percentage of time spent by Assistant Construction Project Manager in compiling Turnover Package
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 0.72278 | N/A | 0.72278 | hours / submittal set | Average time spent in printing and making copies of Turnover Package by Contractor
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 42.5 | N/A | 42.5 | $ / Transmittal | Average cost for mailing Turnover Package by Contractor
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.5 | N/A | 0.5 | hours / transmittal | Average time spent compiling Turnover Package for transmittal by Contractor

## Expected Assumptions
Inputs NOTE: Red text indicates variables affected by the expected process. | Current Value | Unit | Reduction Factor | Expected Outcome | Definitions | Tab Reference
Owner Project / Program Variables
Avg. Number of Pages in Facility Criteria | 2 | pages |  | 2 | Estimated number of pages in Owners initial analysis of Project need and Scope. | 10
Avg. Number of Pages in Discipline Specification | 52 | pages |  | 52 | Estimated number of pages in Equipment performance requirements during planning | 20
Avg. Number of Pages in Project Definition | 2 | pages |  | 2 | Estimated number of pages in Project Definition document. The Project Definition defines the project scope, budget requirements, site details, economic analysis and facility planning data | 40,70,80
Avg. Number of Pages in Front Matter | 10 | pages |  | 10 | Estimated number of pages that precede the technical content of the RFP for Design Services and Construction Services. | 70, 120
Project Variables
Number of Space Types per Project | 18 | Space types / building |  | 18 | Average number of space types found in building. | 50,80
Number of Unique Product Types (Types / project) | 43 | Product Types / project |  | 43 | Number of different equipment types that will be installed. | 60,80,90,100,110,180,190, 250
Number of Tagged Components (components / project) | 23200 | components / project |  | 23200 | Total number of pieces of equipment that will have asset tags and will be managed by the owner | 210
Time to Log (hours / transmittal) | 0.25 | hours / transmittal | 100% | 0 | Time spent logging documents In and Out | 30,50,60,70,80,90,100,110,120,130,150,180,190,210,230,250
Pre-Design Variables
Avg. Number of Options | 3 | count |  | 3 | Average number of pre-design options created by the planner for early analysis of concepts. | 30
Avg. Number of Pre-Design Submittal Sets Reqd. (sets / submittal) | 4 | sets / submittal | 100% | 0 | Average number of pre-design drawing sets required for each submittal. | 30,50,60,70
Avg. Number of Sheets per Option | 3 | sheets |  | 3 | Average number of drawing sheets included in each option. | 30
Avg. Number of Letter-Sized Pages in Pre-Design Narrative per Option | 10 | pages |  | 10 | Average number of pages included in the pre-design narrative per option. | 30
Avg. Number of Pages in Space Program | 5.94 | pages |  | 5.94 | Average number of pages in Owner’s space program document. | 50,70,80
Avg. Number of Pages in Product Program | 14.19 | pages |  | 14.19 | Average number of pages in Product Program that documents Owners equipment specifications and performance | 60,70,80
Design Variables
Number of Design Submittal Sets Reqd. (sets / submittal) | 6 | sets / submittal | 100% | 0 | Number of Design Phase drawing sets required | 80,90,100,110
Avg. Number of Sheets in Design Early Drawings | 37.3333 | drawings |  | 37.3333 | Average number of Design Early (Schematic Design) drawings. | 80
Avg. Number of Letter-Sized Pages in Design Early Narrative | 10 | pages |  | 10 | Average number of letter-sized pages in the Design Early narrative. | 80
Avg. Number of Sheets in Design Schematic Drawings | 44.8 | drawings |  | 44.8 | Average number of Design Schematic (Design Development) drawings | 90
Avg. Number of Letter Sized Pages in Design Schematic Narrative | 20 | pages |  | 20 | Average number of letter-sized pages in the Design Schematic narrative | 90
Avg. Number of Letter Sized Pages in a Design Schematic Specification | 2 | pages |  | 2 | Average number of letter-sized pages in the Design Schematic (Design Development) specifications. | 90
Avg. Number of Sheets in Design Coordinated Drawings | 53.3333 | drawings |  | 53.3333 | Average number of Design Coordinated drawings | 100
Avg. Number of Letter Sized Pages in a Design Coordinated Narrative | 20 | pages |  | 20 | Average number of letter-sized pages in the Design Coordinated narrative. | 100
Avg. Number of Letter Sized Pages in a Design Coordinated Specification | 50 | pages |  | 50 | Average number of letter-sized pages in the Design Coordinated specifications. | 100
Avg. Number of Sheets in Design Final Drawings | 56 | drawings |  | 56 | Average number of Design Final drawings. | 110,120
Avg. Number of Letter Sized 'Pages in Design Final Narrative | 20 | pages |  | 20 | Average number of letter-sized pages in the Design Final narrative. | 110,120
Avg. Number of Letter Sized Pages in Design Final Specification | 50 | pages |  | 50 | Average number of letter-sized pages in the Design Final specifications. | 110,120
Estimating Process Variables
Avg QTO Time for Equipment Components (hours / plan drawing) | 0.08 | hours / plan drawing | 90% | 0.008 | Average time spent performing quantity take-off of equipment shown on plan drawings. | 90,100,110
Avg QTO Time for Spaces in building (hours / plan drawing) | 0.16 | hours / plan drawing | 90% | 0.016 | Average time spent performing quantity take-off of spaces shown on plan drawings. | 90,100,110
Submittal Process Variables
Number of Submittal Sets Reqd. (sets / submittal) | 6 | sets / submittal | 100% | 0 | Number of construction phase submittal sets required | 180,190,250
Avg. Number of Submittal Items in a Product Submittal Package (submittal items/submittal package) | 3 | submittal items / submittal package |  | 3 | Average number of product Items per submittal package | 180,190
Avg. Number of Submittal Pages in a Submittal Item (pages/submittal item) | 18 | pages/submittal item |  | 18 | Average number of letter-sized pages per submittal item | 180,190
Avg. Number of Submittal Sheets in a Submittal Item (sheets/submittal item) | 1 | sheets/submittal item |  | 1 | Average number of drawings per submittal item | 180,190
Organizational Variables
Owner Administrative Rate ($ / hour) | 23.71 | $ / hour |  | 23.71 | Rate for activities that cover Handling of documents | 10,20,30,40,250
Owners Rep. Rate ($ / hour) | 62.2 | $ / hour |  | 62.2 | Rate for activities that include Validating of documents | 50,60,80,90,100
Owners Rep. Administrative Rate ($ / hour) | 16.88 | $ / hour |  | 16.88 | Rate for activities that cover Handling of documents | 50,60,70,80,90,100,110,120,130,150,180
Planner Rate ($ / hour) | 37.84 | $ / hour |  | 37.84 | Rate for professional assisting owner in Pre-design activities. | 50,60
Planner Administrative Rate ($ / hour) | 16.82 | $ / hour |  | 16.82 | Rate for activities that cover Handling of documents | 30,50,60
Licensed Professional Architect Rate ($ / hour) | 109.99 | $ / hour |  | 109.99 | Rate including Professional Services, Overhead and Profit | 80,90,100,110,190,230
Specifier | 109.99 | $ / hour |  | 109.99 | Rate including Professional Services, Overhead and Profit | 90100110
Architect Drafter Rate ($ / hour) | 70.7 | $ / hour |  | 70.7 | Rate including Professional Services, Overhead and Profit | 70,80,90,100,110,130,150,180,190,210,230
Architect Administrative Rate ($ / hour) | 45.96 | $ / hour |  | 45.96 | Rate for activities that cover Handling of documents
Construction Project Manager Rate ($ / hour) | 125.81 | $ / hour |  | 125.81 | Rate including Professional Services, Overhead and Profit | 180190200210250
Assistant (Construction) Project Manager Rate ($ / hour) | 70.53 | $ / hour |  | 70.53 | Rate including Professional Services, Overhead and Profit | 180190210250
Contractor Administrative Rate ($ / hour) | 44.19 | $ / hour |  | 44.19 | Rate for activities that cover Handling of documents | 130, 150, 180, 190, 210, 230, 250
General Repro/Postal Delivery Cost
Avg. Per Page Copy Cost ($ / page) | 0.15 | $ / sheet | 100% | 0 | - | 10,20,30,40,50,60,70,80,90,100,110,120,180,250
Avg. Per Sheet Copy Cost ($ / sheet) | 3 | $ / sheet | 100% | 0 | - | 30,70,80,90,100,110,120,180,250
Process Specific Variables
Facility Criteria | Current Value |  | Reduction Factor | Expected Outcome
Avg. Number of Sets Required (sets / submittal) | 2 | sets / submittal | 100% | 0 | Average number of sets required
Avg. In-house Reproduction Time Per Set (hours/set) | 0.0013333 | hours/set | 100% | 0 | Average time spent in printing and making copies of Facility Criteria by Owner
Discipline Specification
Avg. Number of Sets Required (sets / submittal) | 2 | sets / submittal | 100% | 0 | Average number of sets required
Avg. In-house Reproduction Time Per Set (hours/set) | 0.034667 | hours/set | 100% | 0 | Average time spent in printing and making copies of Discipline Specification by Owner
Feasibility Study
Avg. Number of Transmittals | 2 | Transmittals | - | 2 | Average number of times options / comments are exchanged between the Planner and Owner times the number of recipients for each exchange
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 0.015 | hours / submittal set | 100% | 0 | Average time spent in printing and making copies of feasibility study by Planner
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 18.8 | $ / Transmittal | 100% | 0 | Average cost for delivering documents/comments sent between Planner and Owner
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.5 | hours / transmittal | 60% | 0.2 | Average time spent in compiling documents for transmittal
Project Definition
Avg. Number of Sets Required (sets / submittal) | 2 | sets | 100% | 0 | Average number of sets required
Avg. In-house Reproduction Time Per Set (hours/set) | 0.0013333 | hours/set | 100% | 0 | Average time spent in printing and making copies of Project Definition by Owner
Space Program
Avg. Time Spent Searching for Space Program Criteria (hours/space) | 0.25 | hours / space | 100% | 0 | Average time spent by Planner searching for Spatial requirements
Avg. Time Spent Reformatting Space Program Criteria into Room Data Sheets (hours/space) | 0.08 | hours | 100% | 0 | Average time spent in evaluating information in Project Definition and identifying and creating a detailed spatial program in a usable format.
Avg. Time for Owners Rep to Validate Space Program (hours) | 0.72 | hours | 90% | 0.072 | Average time spent by Owners Rep in validating Space Program provided by planner
Avg. Percentage of errors in Space Program | 30% | % | 90% | 0.03 | Average percentage of errors found by Owners Rep in Space Program
Avg. Time Spent Re - Searching for Space Program Criteria (hours/space) | 0.25 | hours / space | 100% | 0 | Average time spent by Planner recreating Space Program
Avg. Number of Re-Submit Cycles | 1 | Cycles | 100% | 0 | Average number of times submitted documents are re-submitted.
Avg. Number of Transmittals | 2 | Transmittals | - | 2 | Average number of times Space Program / Comments are sent between the Planner and Owners Rep times the number of recipients for each exchange.
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 18.8 | $ / Transmittal | 100% | 0 | Average cost for delivering documents/comments sent between Planner and Owners Rep
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.17 | hours / transmittal | 60% | 0.068 | Average time spent in compiling documents for transmittal
Product Program
Avg. Time Spent Searching for Product Program Criteria (hours / product) | 0.08 | hours / product | 100% | 0 | Average time spent by Planner searching for Product Program Criteria
Avg. Time for Owners Rep to Validate Product Program (hours) | 2.15 | hour | 90% | 0.215 | Average time spent by Owners Rep in validating Product Program provided by Planner
Avg. Percentage of errors in Product Program | 30% | % | 90% | 0.03 | Average percentage of errors found by Owners Rep in Product Program
Avg. Time Spent Re - Searching for Product Program Criteria (hours / product) | 0.08 | hours / product | 100% | 0 | Average time spent by Planner recreating Product Program
Avg. Number of Re-Submit Cycles | 1 | Cycles | 100% | 0 | Average number of times submitted documents are re-submitted
Avg. Number of Transmittals | 2 | Transmittals | - | 2 | Average number of times Product Program / Comments are sent between the Planner and Owners Rep times the number of recipients for each exchange.
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 23.95 | $ / Transmittal | 100% | 0 | Average cost for mailing documents/comments sent between Planner and Owners Rep.
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.17 | hours / transmittal | 60% | 0.068 | Average time spent in compiling documents for transmittal.
Request for Proposal
Avg. Number of Letter Sized Pages in Proposal (pages / proposal) | 6 | pages / proposal |  | 6 | Average number of Letter-Sized Pages in Proposal
Avg. Number of Drawing Sheets in Proposal (sheets / proposal) | 2 | sheets / proposal |  | 2 | Average number of sheets included in the Proposal
Number of RFP copies Reqd. (sets / submittal) | 5 | sets / submittal | 100% | 0 | Number of RFP copies required
Avg. Number of Transmittals - Owners Rep documents to Bidders | 5 | Transmittals | - | 5 | Average number of times Proposal is sent from the Owners Rep to the Bidders times the number of recipients for each exchange.
Avg. Number of Transmittals - Architect to Owner | 1 | Transmittals | - | 1 | Average number of times Proposal is sent from the Architect to the Owners Rep times the number of recipients for each exchange.
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 0.0095556 | hours / submittal set | 100% | 0 | Average time spent in printing and making copies of Proposal by Architect
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Owners Rep documents to Bidders | 16.5 | $ / Transmittal | 100% | 0 | Average cost for mailing documents/comments sent between Owners Rep and Architect
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Architect to Owners Rep | 16.5 | $ / Transmittal | 100% | 0 | Average cost for mailing proposal between Architect and Owners Rep.
Avg. Time to Prepare Transmittal (hours / transmittal) - Owners Rep | 0.75 | hours / transmittal | 60% | 0.3 | Average time spent in compiling documents for transmittal / submission
Avg. Time to Prepare Transmittal (hours / transmittal) - Architect | 1 | hours / transmittal | 60% | 0.4 | Average time spent in compiling documents for transmittal / submission
Design Early
Avg. Time Spent Reformatting Space Program (hours / space) | 0.16 | hours / space type | 100% | 0 | Average time spent by Architect in documenting spatial requirements in a usable format
Avg. Time Spent Reformatting Product Program (hours /product) | 0.25 | hours / product | 100% | 0 | Average Time spent by Architect documenting product type requirements in a usable format
Avg. Time Spent Evaluating Design Early Drawings against Design Requirements - Space and Equipment | 9.15 | hours | 90% | 0.915 | Average time spent by Architect in validating Design Early drawings against space and equipment requirements before submission to Owners Rep
Avg. Time spent making corrections due to non-conformance with Space or Product Program | 1.5189 | hours | 100% | 0 | Average time spent by Architect making corrections to space and equipment documentation based on internal validation.
Avg Time to Review Design Early Drawings for conformance to Space and Product Program | 3.08 | hours | 90% | 0.308 | Average time spent by Owner’s Rep. in validating space and equipment documentation in Design Early Documents provided by Architect.
Avg. Number of Re-Submit Cycles | 1 | Cycles | 100% | 0 | Average number of times submitted documents are re-submitted
Percentage of Time Spent by Licensed Professional Architect | 90% | % | - | 90% | Percentage of time spent by Licensed Architect reformatting Space and Product Program, evaluating documents and making corrections where necessary.
Percentage of Time Spent by Architect Drafter | 10% | % | - | 10% | Percentage of time spent by Architect Drafter reformatting Space and Product Program, copying and sending documents.
Avg. Number of Transmittals | 1 | Transmittals | - | 1 | Average number of times drawings, narratives and comments are sent and received between the Architect / Planner and Owner times the number of recipients for each exchange
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 0.11037 | hours / submittal set | 100% | 0 | Average time spent in printing and making copies of drawings and narratives by Architect / Planner
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Owners Rep to Architect | 16.5 | $ / Transmittal | 100% | 0 | Average cost for mailing documents/comments sent between Owners Rep and Architect
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Architect to Owners Rep | 21.6 | $ / Transmittal | 100% | 0 | Average cost for mailing documents/comments between Architect and Owners Rep.
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.5 | hours / transmittal | 60% | 0.2 | Average time spent compiling copies of drawings, narratives and comments for transmittal by Architect and Owners Rep.
Design Schematic
Avg. Number of Plan Drawings in Design Schematic Drawings | 11.2 | plans / drawing set | - | 11.2 | Average number of Plan Drawings
Avg. Time Spent Developing Equipment (product) Type Template (hours / product type) | 0.25 | hours / product type | 70% | 0.075 | Average time spent by Architect in developing specifications for equipment types required for the project
Avg. Time Spent Evaluating Design Schematic Drawings against Design Requirements - Space and Equipment | 24.4 | hours | 90% | 2.44 | Average time spent by Architect in validating Design Schematic drawings against space and equipment requirements before submission to Owners Rep
Avg. Time spent making corrections due to non-conformance with Space or Product Program | 2.2784 | hours | 100% | 0 | Average time spent by Architect making corrections to space and Product Type Templates (Outline Specifications) documentation based on internal validation.
Avg Time to Review Design Schematic Drawings for conformance to Space and Product Program | 3.696 | hours | 90% | 0.3696 | Average time spent by Owner’s Rep. in validating Space and Product Type Templates (Outline Specifications) in Schematic Documents provided by Architect.
Avg. Number of Re-Submit Cycles | 1 | Cycles | 100% | 0 | Average number of times submitted documents are re-submitted
Percentage of Time Spent by Licensed Professional Architect | 80% | % | - | 80% | Percentage of time spent by Licensed Architect to taking off all equipment pieces and calculating areas, developing equipment type templates, evaluating documents and making corrections where necessary.
Percentage of Time Spent by Architect Drafter | 20% | % | - | 20% | Percentage of time spent by Architect Drafter taking off all equipment pieces and calculating areas, copying and sending documents.
Avg. Number of Transmittals | 1 | Transmittals | - | 1 | Average number of times schematic drawings, narratives, specifications and comments are sent and received between the Architect / Planner and Owner times the number of recipients for each exchange
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 0.13911 | hours/submittal set | 100% | 0 | Average time spent in printing and making copies of drawings, narratives and specifications by Architect / Planner
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Owners Rep to Architect | 16.5 | $ / Transmittal | 100% | 0 | Average cost for mailing documents/comments sent between Owners Rep and Architect
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Architect to Owners Rep | 25.8 | $ / Transmittal | 100% | 0 | Average cost for mailing documents/comments between Architect and Owners Rep.
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.5 | hours / transmittal | 60% | 0.2 | Average time spent compiling copies of schematic drawings, narratives, specifications and comments for transmittal by Architect and Owners Rep.
Design Coordinated
Avg. Number of Plan Drawings in Design Coordinate Drawings | 11.2 | plans / drawing set | - | 11.2 | Average number of Plan Drawings
Avg. Time Spent Developing Detailed Equipment (products) Type Template (hours / product) | 2 | hours / product | 70% | 0.6 | Average time spent by Architect in preparing a detailed specifications list based on equipment types
Avg. Time Searching for Product Literature for Candidates (Hours/product) | 1 | hours / product | 90% | 0.1 | Average time spent by Architect in searching for product data
Avg. Time Spent Evaluating Design Coordinated Drawings against Design Requirements - Space and Equipment | 28.06 | hours | 90% | 2.806 | Average time spent by Architect in validating Design Coordinated drawings against space and equipment requirements before submission to Owners Rep
Avg. Time Spent making Corrections due to Non-Conformance with Space Program | 1.2658 | hours | 100% | 0 | Average time spent by Architect making corrections to space and equipment documentation based on internal validation.
Avg. Percent of Errors in Product Type Candidate | 15% | % | 90% | 0.015 | Percentage of errors in Product Type List
Avg Time to Review Design Coordinated Drawings for conformance to Space and Product Program | 4.4 | hours | 90% | 0.44 | Average time spent by Owner’s Rep. in validating Space and Product Type Candidates in Schematic Coordinated Drawings provided by Architect.
Avg. Number of Re-Submit Cycles | 1 | Cycles | 100% | 0 | Average number of times submitted documents are re-submitted
Percentage of Time Spent by Licensed Professional Architect | 80% | % | - | 80% | Percentage of time spent by Licensed Architect taking off all equipment pieces and calculating areas, developing equipment type templates, searching for product literature, evaluating documents and making corrections where necessary.
Percentage of Time Spent by Architect Drafter | 20% | % | - | 20% | Percentage of time spent by Architect Drafter to take off all equipment pieces and to calculate areas, copying and sending documents.
Avg. Number of Transmittals | 1 | Transmittals | - | 1 | Average number of times coordinated drawings, narratives, specifications and comments are sent and received between the Architect and Owners Rep times the number of recipients for each exchange
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 0.19481 | hours / submittal set | 100% | 0 | Average time spent in printing and making copies of drawings, narratives and specifications by Architect
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Owners Rep to Architect | 16.5 | $ / Transmittal | 100% | 0 | Average cost for mailing documents/comments sent between Owners Rep and Architect
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Architect to Owners Rep | 28.95 | $ / Transmittal | 100% | 0 | Average cost for mailing documents between Architect and Owners Rep.
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.5 | hours / transmittal | 60% | 0.2 | Average time spent compiling copies of coordinated drawings, narratives, specifications and comments for transmittal by Architect and Owners Rep
Design Final
Avg. Number of Plan Drawings in Design Final Drawings | 11.2 | plans / drawing set | - | 11.2 | Average number of Plan Drawings
Avg. Time Spent Developing Detailed Equipment (products) Type Candidate (hours / product) | 1 | hours / product | 90% | 0.1 | Average time spent by Architect in preparing a detailed specifications list based on equipment types
Avg. Time Spent Evaluating Design Final Drawings against Design Requirements - Space and Equipment | 26.23 | hours | 90% | 2.623 | Average time spent by Architect in validating Design Final drawings before submission to Owners Rep
Avg. Time Spent making Corrections due to Non-Conformance with Space or Product Program | 0.5063 | hours | 100% | 0 | Average time spent by Architect making corrections based on internal evaluation and feedback from Owners Rep.
Percentage of Time Spent by Licensed Professional Architect | 90% | % | - | 90% | Percentage of time spent by Licensed Architect taking off all equipment pieces and calculating areas, developing detailed equipment type candidates, evaluating documents and making corrections where necessary.
Percentage of Time Spent by Architect Drafter | 10% | % | - | 10% | Percentage of time spent by Architect Drafter taking off all equipment pieces and calculating areas, copying and sending documents.
Avg. Number of Transmittals | 1 | Transmittals | - | 1 | Average number of times final drawings, narratives, specifications and comments are sent and received between the Architect and Owners Rep times the number of recipients for each exchange.
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 0.20222 | hours / submittal set | 100% | 0 | Average time spent in printing and making copies of drawings, narratives and specifications by Architect / Planner
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Owners Rep to Architect | 16.5 | $ / Transmittal | 100% | 0 | Average cost for mailing documents/comments sent between Owners Rep and Architect
Avg. Mailing Cost per Transmittal ($ / Transmittal) - Architect to Owners Rep | 32.75 | $ / Transmittal | 100% | 0 | Average cost for mailing proposal between Architect and Owners Rep.
Avg. Time to Prepare Transmittal (hours / transmittal) | 1 | hours / transmittal | 60% | 0.4 | Average time spent compiling copies of final drawings, narratives, specifications for transmittal by Architect
Request for Proposal
Avg. Number of Transmittals | 5 | Transmittals | - | 5 | Average number of times RFP Package is sent from Owners Rep to Contractor times the number of recipients for purpose of bidding.
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 0.20889 | hours / submittal set | 100% | 0 | Average time spent in printing and making copies of RFP Package by Owners Rep.
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 32.75 | $ / Transmittal | 100% | 0 | Average cost for mailing RFP by Owners Rep.
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.75 | hours / transmittal | 60% | 0.3 | Average time spent compiling documents, drawings or specifications for transmittal by Owners Rep.
Avg. Number of Request for Proposal Submittal Sets Reqd. | 1 | submittal sets | 100% | 0 | Average number of RFP sets required for submission
Inquiry Issue
Avg. Number of Transmittals | 3 | Transmittals | - | 3 | Average number of times Inquiry Issues and responses are sent and received between Owners Rep, Architect and Contractor times the number of recipients for each exchange
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 16.5 | $ / Transmittal | 100% | 0 | Average cost for mailing documents/comments sent between Owners Rep, Architect, and Contractor
Avg. Time to Prepare Transmittals for Inquiry Issues (hours / transmittal) - Contractor / Architect | 0.17 | hours / transmittal | 60% | 0.068 | Avergae time spent compiling documents, drawings or specifications for transmittal by Architect and Contractor
Avg. Time to Prepare Transmittals for Inquiry Issues (hours / transmittal) - Owners Rep | 0.083 | hours / transmittal | 60% | 0.0332 | Average time spent compiling documents, drawings or specifications for transmittal by Owners Rep.
Pre-Construction Plan
Inquiry Issue (RFI)
Avg. Number of RFIs | 29 | Transmittals | 90% | 2.9 | Average number of formal questions (Request for Information) initiated by the Contractor related to Space and Equipment
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 16.5 | $ / Transmittal | 100% | 0 | Average cost for mailing documents/comments sent between Owners Rep, Architect, and Contractor
Avg. Time to Prepare Transmittals for Inquiry Issues (RFI) (hours / transmittal) - Contractor / Architect | 0.17 | hours / transmittal | 60% | 0.068 | Average Time spent compiling Inquiry Issues (RFI) for transmittal by Architect and Contractor
Avg. Time to Prepare Transmittals for Inquiry Issues (RFI) (hours / transmittal) - Owner | 0.03 | hours / transmittal | 60% | 0.012 | Average Time spent compiling Inquiry Issues (RFI) for transmittal by Owners Rep
Product Type Selection
System Layout
Submittal Package
Average Time Spent Organizing Equipment (product) Type information (hours / submittal item) | 0.17 | hours / submittal item | 60% | 0.068 | Average Time spent by asst. project manager in producing submittal packages by organizing equipment type information
Average Time Spent Evaluating Equipment (product) Type Submittal Items against Contract Documents (hours / submittal item) | 0.5 | hours / submittal item | 90% | 0.05 | Average Time spent evaluating submittal items
Avg. Time to Sign each Page (hours / page) | 0.083 | hours/page | 100% | 0 | Average time required by Contractor to sign pages of Submittal Package
Avg. Time to Stamp each Sheet (hours / sheet) | 0.083 | hours/sheet | 100% | 0 | Average time required by Contractor to stamp sheets of Submittal Package
Percentage of Submittals Items rejected | 20% | % | - | 20% | Percentage of items rejected
Percentage of Time Spent by Construction Project Manager | 10% | % | - | 10% | Percentage of time spent by Construction Project Manager in validating Submittal Information
Percentage of Time Spent by Assistant (Construction) Project Manager | 90% | % | - | 90% | Percentage of time spent by Assistant Construction Project Manager in validating Submittal Information
Avg. Number of Transmittals | 30 | Transmittals | - | 30 | The average number of product submittal items sent by the Sub-Contractors and vendors to the Contractor.
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 0.014778 | hours / submittal set | 100% | 0 | Average time spent in printing and making copies of Submittal Package by Contractor
Average Mailing Costs per Transmittal ($) | 16.5 | $ / Transmittal | 100% | 0 | Average cost for Mailing documents/transmittals sent between Owners Rep and Contractor
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.5 | hours / transmittal | 60% | 0.2 | Average time spent compiling Submittal Package for transmittal by Architect / Contractor
Submittal Issue
Avg. Time Spent Evaluating Product Type Submittal Items against Contract Documents (hours / product type submittal item) | 1 | hours / submittal item | 90% | 0.1 | Avergae time spent by Architect evaluating each product type submittal against contract documents
Avg. Time Spent Revising one Product Type Submittal Item (hours / product type submittal item) | 0.5 | hours / product | 90% | 0.05 | Average time spent by Contractor revising each Submittal Item to meet contract requirements and resubmit.
Percentage of Product Submittals reviewed by Licensed Architect | 75% | % | - | 75% | Percentage of submittals reviewed by Architect
Percentage of Product Submittals rejected on first review | 43% | % | 90% | 4.3% | Percentage of submittals rejected upon review
Percentage of Product Submittals rejected on second review | 25% | % | 100% | 0% | Percentage of submittals rejected upon review
Percentage of Product Submittals rejected on third review | 0% | % | 100% | 0% | Percentage of submittals rejected upon review
Avg. Time Spent Transferring Comments per Page | 0.033 | hours / submittal package | 100% | 0 | Avergae time spent by Architect in marking up submittal with comments
Avg. Time Spent Transferring Comments per Sheet | 0.083 | hours / submittal package | 100% | 0 | Avergae time spent by Architect in marking up submittal with comments
Percentage of Time Spent by Construction Project Manager | 80% | % | - | 80% | Percentage of time spent by Construction Project Manager in recreating Submittal Package
Percentage of Time Spent by Assistant (Construction) Project Manager | 20% | % | - | 20% | Percentage of time spent by Assistant Construction Project Manager in recreating Submittal Package
Avg. Number of Transmittals | 3 | Transmittals | - | 3 | Average number of times Submittal Packages (pages and sheets) are sent and received between Architect and Contractor times the number of recipients for each exchange
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.083 | hours / transmittal | 60% | 0.0332 | Average time spent compiling Submittal Package for transmittal by Architect
Avg. Mailing Cost per Transmittal | 16.5 | $ / Transmittal | 100% | 0 | Average cost for Mailing documents/transmittals between Architect / Planner and Contractor
Purchase Order
Product Installation
Avg. Time Spent Re-formatting Product Installation Report in Office (hours/ component) | 0.17 | hours / component | 100% | 0 | Average time spent by Contractor in the office re-formatting report
Avg. Number of Transmittals (Transmittals) | 2 | Transmittals | - | 2 | Average number of times Product Installation Reports are sent and received between Contractor and Architect / Owner times the number of recipients for each exchange
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 16.5 | $ / Transmittal | 100% | 0 | Average cost for mailing Product Installation Report by Contractor
Avg. Time to Prepare a Transmittal (hours/transmittal) | 0.083 | hours / transmittal | 60% | 0.0332 | Average time spent compiling Product Installation for transmittal by Assistant Construction Manager
Start-Up
Product Inspection
Avg. Field Time Spent Documenting Report per Site Visit (hours / visit) | 1.5 | hours / visit | 60% | 0.6 | Average time spent in the field documenting data during site visits.
Avg. Number of Site Visits per month | 4 | visits / month | - | 4 | Average number of times site is visited in a month
Avg Number of Months of Construction | 12 | months | - | 12 | Average construction duration of a project
Total Time Spent in Office | 8 | hours / day | - | 8 | Total time spent in the office on a daily basis
Avg. Percentage of Office Time Spent Quantifying products in place | 25% | % | 90% | 2.5% | Average percentage of time spent in the office documenting data recorded from the field.
Avg. Number of Transmittals | 2 | Transmittals | - | 2 | Average number of times Inspection Reports are sent and received between Architect and Contractor times the number of recipients for each exchange
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 16.5 | $ / Transmittal | 100% | 0 | Average cost for mailing Inspection Reports by Architect
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.083 | hours / transmittal | 60% | 0.0332 | Average time spent compiling Inspection Report for transmittal by Architect
Punch list Issue
Turnover Package
Avg. Time Spent Searching and Assembling Operations & Maintenance Manuals (hours / document) | 3 | hours / document | 90% | 0.3 | Time spent compiling O&M Manual
Avg. Time Spent Searching and Assembling Commissioning Report (hours / document) | 0.0008 | hours / document | 90% | 8e-05 | Time spent compiling Commissioning Report
Avg. Time Spent Searching and Assembling Record Specifications (hours / document) | 0.008 | hours / document | 90% | 0.0008 | Time spent compiling Record Specifications
Avg. Time Spent Searching and Assembling Record (As-Built) Drawings (hours / sheet) | 0.008 | hours / sheet | 90% | 0.0008 | Time spent compiling Record (As-Built) Drawings
Avg. Time Spent Searching and Assembling Final Approved Shop Drawings (hours / sheet) | 0.0083 | hours / sheet | 90% | 0.00083 | Time spent compiling Final Approved Shop Drawings
Avg. Number of Pages in Operations & Maintenance Manuals (pages / product) | 645 | pages / product | - | 645 | Number of Pages in Operations & Maintenance Manuals
Avg. Number of Pages in Commissioning Report | 10 | pages / component | - | 10 | Number of Pages in Commissioning Report
Avg. Number of Components & Systems to be Commissioned | 20 | components | - | 20 | Number of Components to be commissioned
Avg. Number of Pages in Record Specifications | 50 | pages | - | 50 | Number of Pages in Record Specifications
Avg. Number of Sheets in Record (As-Built) Drawings | 90 | sheets | - | 90 | Number of Sheets in Record (As-Built) Drawings
Avg. Number of Sheets in Final Approved Shop Drawings | 1 | sheets | - | 1 | Number of Sheets in Final Approved Shop Drawings
Avg. Time Spent Reviewing Operations & Maintenance Manuals (hours/page) | 0.0017 | hours / page | 0% | 0.0017 | Time Spent Reviewing Operations & Maintenance Manuals
Avg. Time Spent Reviewing Commissioning Report (hours / page) | 0.0083 | hours / page | 0% | 0.0083 | Time Spent Reviewing Commissioning Report
Avg. Time Spent Reviewing Record Specifications (hours / page) | 0.0017 | hours / page | 100% | 0 | Time Spent Reviewing Record Specifications
Avg. Time Spent Reviewing Record (As-Built) Drawings (hours/ sheet) | 0.0083 | hours / sheet | 0% | 0.0083 | Time Spent Reviewing Record (As-Built) Drawings
Avg. Time Spent Reviewing Final Approved Shop Drawings (hours / sheet) | 0.0083 | hours / sheet | 100% | 0 | Time Spent Reviewing Final Approved Shop Drawings
Avg. Time Spent Filing Operations & Maintenance Manuals (hours/document) | 0.083 | hours / document | 100% | 0 | Time Spent Filing Operations & Maintenance Manuals
Avg. Time Spent Filing Commissioning Report (hours/document) | 0.083 | hours / document | 100% | 0 | Time Spent Filing Commissioning Report
Avg. Time Spent Filing Record Specifications (hours/document) | 0.083 | hours / document | 100% | 0 | Time Spent Filing Record Specifications
Avg. Time Spent Filing Record (As-Built) Drawings (hours / sheet) | 0.0017 | hours / sheet | 100% | 0 | Time Spent Filing Record (As-Built) Drawings
Avg. Time Spent Filing Final Approved Shop Drawings(hours / sheet) | 0.0017 | hours / sheet | 100% | 0 | Time Spent Filing Final Approved Shop Drawings
Percentage of Time Spent by Construction Project Manager | 10% | % | - | 10% | Percentage of time spent by Construction Project Manager in compiling Turnover Package
Percentage of Time Spent by Assistant (Construction) Project Manager | 90% | % | - | 90% | Percentage of time spent by Assistant Construction Project Manager in compiling Turnover Package
Avg. In-house Reproduction Time Per Submittal Set (hours/submittal set) | 0.72278 | hours / submittal set | 100% | 0 | Average time spent in printing and making copies of Turnover Package by Contractor
Avg. Mailing Cost per Transmittal ($ / Transmittal) | 42.5 | $ / Transmittal | 100% | 0 | Average cost for mailing Turnover Package by Contractor
Avg. Time to Prepare Transmittal (hours / transmittal) | 0.5 | hours / transmittal | 60% | 0.2 | Average time spent compiling Turnover Package for transmittal by Contractor

## Project Summary
PROJECT
Cost Summary
OmniClass Project Phase (Table31) | Current Process | Expected Process | Savings | % Savings
LCie 01 - Facility Criteria | 0 | 0 | 0 | 0%
LCie 02 - Design Specification | 20 | 0 | 20 | 100%
LCie 03 - Feasibility Study | 470 | 20 | 450 | 95.74%
LCie 04 - Project Definition | 0 | 0 | 0 | 0%
LCie 05 - Space Program | 510 | 10 | 500 | 98.04%
LCie 06 - Product Program | 540 | 20 | 520 | 96.3%
LCie 07 - Request for Proposal | 400 | 100 | 300 | 75%
LCie 08 - Design Early | 4900 | 100 | 4800 | 97.96%
LCie 09 - Design Schematic | 7100 | 700 | 6400 | 90.14%
LCie 10 -Design Coordinated | 21600 | 3700 | 17900 | 82.87%
LCie 11 - Design Final | 9200 | 800 | 8400 | 91.3%
LCie 12 - Request for Proposal | 410 | 30 | 380 | 92.68%
LCie 13 - Inquiry Issue | 1210 | 30 | 1180 | 97.52%
LCie 14 - Pre-Construction Plan | 0 | 0 | 0 | 0%
LCie 15 - Inquiry Issue (RFI) | 4700 | 0 | 4700 | 100%
LCie 16 - Product Type Selection | 0 | 0 | 0 | 0%
LCie 17 - System Layout | 0 | 0 | 0 | 0%
LCie 18 - Submittal Package | 12200 | 600 | 11600 | 95.08%
LCie 19 - Submittal Issue | 60500 | 400 | 60100 | 99.34%
LCie 20 - Purchase Order | 0 | 0 | 0 | 0%
LCie 21 - Product Installation | 278300 | 0 | 278300 | 100%
LCie 22 - Start-Up | 0 | 0 | 0 | 0%
LCie 23 - Product Inspection | 15900 | 600 | 15300 | 96.23%
LCie 24 - Punchlist Issue | 0 | 0 | 0 | 0%
LCie 25 - Turnover Package | 27400 | 100 | 27300 | 99.64%
Total | 445000 | 7000 | 438000 | 98.43%
Breakdown by Role
Owner / Owners Rep
OmniClass Project Phase | Current Process | Expected Process | Savings | % Savings by Role
LCie 01 - Facility Criteria | 0 | 0 | 0 | 0%
LCie 02 - Design Specification | 20 | 0 | 20 | 100%
LCie 03 - Feasibility Study | 90 | 10 | 80 | 88.89%
LCie 04 - Project Definition | 0 | 0 | 0 | 0%
LCie 05 - Space Program | 105 | 5 | 100 | 95.24%
LCie 06 - Product Program | 200 | 10 | 190 | 95%
LCie 07 - Request for Proposal | 270 | 30 | 240 | 88.89%
LCie 08 - Design Early | 500 | 0 | 500 | 100%
LCie 09 - Design Schematic | 500 | 0 | 500 | 100%
LCie 10 -Design Coordinated | 600 | 0 | 600 | 100%
LCie 11 - Design Final | 5 | 0 | 5 | 100%
LCie 12 - Request for Proposal | 410 | 30 | 380 | 92.68%
LCie 13 - Inquiry Issue | 150 | 0 | 150 | 100%
LCie 14 - Pre-Construction Plan | 0 | 0 | 0 | 0%
LCie 15 - Inquiry Issue (RFI) | 1480 | 0 | 1480 | 100%
LCie 16 - Product Type Selection | 0 | 0 | 0 | 0%
LCie 17 - System Layout | 0 | 0 | 0 | 0%
LCie 18 - Submittal Package | 1000 | 100 | 900 | 90%
LCie 19 - Submittal Issue | 0 | 0 | 0 | 0%
LCie 20 - Purchase Order | 0 | 0 | 0 | 0%
LCie 21 - Product Installation | 0 | 0 | 0 | 0%
LCie 22 - Start-Up | 0 | 0 | 0 | 0%
LCie 23 - Product Inspection | 0 | 0 | 0 | 0%
LCie 24 - Punchlist Issue | 0 | 0 | 0 | 0%
LCie 25 - Turnover Package | 60 | 50 | 10 | 16.67%
Total | 5000 | 200 | 5200 | 104%
Architect
OmniClass Project Phase | Current Process | Expected Process | Savings | % Savings by Role
LCie 01 - Facility Criteria | 0 | 0 | 0 | 0%
LCie 02 - Design Specification | 0 | 0 | 0 | 0%
LCie 03 - Feasibility Study | 390 | 10 | 380 | 97.44%
LCie 04 - Project Definition | 0 | 0 | 0 | 0%
LCie 05 - Space Program | 400 | 0 | 400 | 100%
LCie 06 - Product Program | 300 | 0 | 300 | 100%
LCie 07 - Request for Proposal | 140 | 30 | 110 | 78.57%
LCie 08 - Design Early | 4420 | 110 | 4310 | 97.51%
LCie 09 - Design Schematic | 6600 | 700 | 5900 | 89.39%
LCie 10 -Design Coordinated | 20800 | 3700 | 17100 | 82.21%
LCie 11 - Design Final | 9200 | 800 | 8400 | 91.3%
LCie 12 - Request for Proposal | 0 | 0 | 0 | 0%
LCie 13 - Inquiry Issue | 240 | 10 | 230 | 95.83%
LCie 14 - Pre-Construction Plan | 0 | 0 | 0 | 0%
LCie 15 - Inquiry Issue (RFI) | 1900 | 0 | 1900 | 100%
LCie 16 - Product Type Selection | 0 | 0 | 0 | 0%
LCie 17 - System Layout | 0 | 0 | 0 | 0%
LCie 18 - Submittal Package | 500 | 0 | 500 | 100%
LCie 19 - Submittal Issue | 58700 | 400 | 58300 | 99.32%
LCie 20 - Purchase Order | 0 | 0 | 0 | 0%
LCie 21 - Product Installation | 40 | 0 | 40 | 100%
LCie 22 - Start-Up | 0 | 0 | 0 | 0%
LCie 23 - Product Inspection | 15900 | 600 | 15300 | 96.23%
LCie 24 - Punchlist Issue | 0 | 0 | 0 | 0%
LCie 25 - Turnover Package | 0 | 0 | 0 | 0%
Total | 119500 | 6400 | 113200 | 94.73%
Contractor
OmniClass Project Phase | Current Process | Expected Process | Savings | % Savings by Role
LCie 01 - Facility Criteria | 0 | 0 | 0 | 0%
LCie 02 - Design Specification | 0 | 0 | 0 | 0%
LCie 03 - Feasibility Study | 0 | 0 | 0 | 0%
LCie 04 - Project Definition | 0 | 0 | 0 | 0%
LCie 05 - Space Program | 0 | 0 | 0 | 0%
LCie 06 - Product Program | 0 | 0 | 0 | 0%
LCie 07 - Request for Proposal | 0 | 0 | 0 | 0%
LCie 08 - Design Early | 0 | 0 | 0 | 0%
LCie 09 - Design Schematic | 0 | 0 | 0 | 0%
LCie 10 -Design Coordinated | 0 | 0 | 0 | 0%
LCie 11 - Design Final | 0 | 0 | 0 | 0%
LCie 12 - Request for Proposal | 0 | 0 | 0 | 0%
LCie 13 - Inquiry Issue | 820 | 10 | 810 | 98.78%
LCie 14 - Pre-Construction Plan | 0 | 0 | 0 | 0%
LCie 15 - Inquiry Issue (RFI) | 1300 | 0 | 1300 | 100%
LCie 16 - Product Type Selection | 0 | 0 | 0 | 0%
LCie 17 - System Layout | 0 | 0 | 0 | 0%
LCie 18 - Submittal Package | 10700 | 500 | 10200 | 95.33%
LCie 19 - Submittal Issue | 1780 | 10 | 1770 | 99.44%
LCie 20 - Purchase Order | 0 | 0 | 0 | 0%
LCie 21 - Product Installation | 278200 | 5 | 278195 | 100%
LCie 22 - Start-Up | 0 | 0 | 0 | 0%
LCie 23 - Product Inspection | 20 | 0 | 20 | 100%
LCie 24 - Punchlist Issue | 0 | 0 | 0 | 0%
LCie 25 - Turnover Package | 27380 | 40 | 27340 | 99.85%
Total | 320200 | 600 | 319600 | 99.81%

## 010_Facility_Criteria
| Process Name | Facility Criteria
| OmniClass Stage | 31-10 11 14 Project Description Phase
| OmniClass Role | 34-21 14 00 Owner
| Description | Standard facility information must be available in order to determine the basic requirements for a potential project. The owner indentifies the need and either develops technical criteria for the facility if none exist or utilizes existing technical criteria if available. If it does exist, this information must be checked for relevancy every five years to remain consistent with overall needs.
Information Attributes
|  |  | Total | Owner | Architect | Contractor
|  | Current process cost: | 0.66323 | 0.66323 | 0 | 0
|  | Expected process cost: | 0 | 0 | 0 | 0
|  | Process Cost Difference: | 0.66323 | 0.66323 | 0 | 0
Process
| Current Process | [7 empty] | Expected Process
| 010.01 | Identify Need | [6 empty] | 010.01 | Identify Need
| 010.02.10 | Review Existing Facility Criteria | [6 empty] | 010.02.10 | Review Existing Facility Criteria
| 010.02.30 | Produce Facility Criteria | [6 empty] | 010.02.30 | Produce Facility Criteria
COPYING/ ELEC.DOC. | 010.02.40 | Copy Facility Criteria (UFC Criteria) | [5 empty] | COPYING/ ELEC.DOC. | 010.02.40 | Copy Facility Criteria (UFC Criteria)
|  | 2 | Avg. Number of Pages in Facility Criteria | [6 empty] | 2 | Avg. Number of Pages in Facility Criteria
|  | 2 | Avg. Number of Sets Required (sets / submittal) | [6 empty] | 0 | Avg. Number of Sets Required (sets / submittal)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 0.0013333 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 23.71 | Owner Administrative Rate ($ / hour) |  |  | 0.063227 |  |  |  | 23.71 | Owner Administrative Rate ($ / hour) | 0
|  |  | Reproduction Costs |  |  | 0.6 |  |  |  |  | Reproduction Costs | 0
|  |  | SubTotal |  |  |  | 0.66323 |  |  |  | SubTotal |  | 0
[6 empty] | Current Process Total | 0.66323 |  |  |  |  | Expected Process Total | 0

## 020_Discipline_Specification
| Process Name | Discipline Specifications
OmniClass Stage
OmniClass Role
| Description | Specification information for equipment based on facility criteria is generated early in the planning process by the Owner. This information must be check for relevancy every five years to remain consistent with overall needs.
Information Attributes
|  |  | Total | Owner | Architect | Contractor
|  | Current process cost: | 17.2439 | 17.2439 | 0 | 0
|  | Expected process cost: | 0 | 0 | 0 | 0
|  | Process Cost Difference: | 17.2439 | 17.2439 | 0 | 0
Process
| Current Process | [7 empty] | Expected Process
| 020.01 | Identify Need | [6 empty] | 020.01 | Identify Need
| 020.02.10 | Review Existing Discipline Specification | [6 empty] | 020.02.10 | Review Existing Discipline Specification
| 020.02.30 | Produce Discipline Specification | [6 empty] | 020.02.30 | Produce Discipline Specification
COPYING/ ELEC.DOC. | 020.02.40 | Copy Discipline Specification | [5 empty] | COPYING/ ELEC.DOC. | 020.02.40 | Copy Discipline Specification
|  | 52 | Avg. Number of Pages in Discipline Specification | [6 empty] | 52 | Avg. Number of Pages in Discipline Specification
|  | 2 | Avg. Number of Sets Required (sets / submittal) | [6 empty] | 0 | Avg. Number of Sets Required (sets / submittal)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 0.034667 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 23.71 | Owner Administrative Rate ($ / hour) |  |  | 1.6439 |  |  |  | 23.71 | Owner Administrative Rate ($ / hour) | 0
|  |  | Reproduction Costs |  |  | 15.6 |  |  |  |  | Reproduction Costs | 0
|  |  | SubTotal |  |  |  | 17.2439 |  |  |  | SubTotal |  | 0
[6 empty] | Current Process Total | 17.2439 |  |  |  |  | Expected Process Total | 0

## 030_Feasibility_Study
| Process Name | Feasibility Study
OmniClass Stage
OmniClass Role
| Description | The Feasibility Study allows the Owner to evaluate different options (typically three) based on the identified requirements before finalizing specific information about the project. The Architect or Planner develops the study based on the information contained in the Facility Criteria and Discipline Specification information exchanges.
Information Attributes
|  |  | Total | Owner | Architect/ Planner | Contractor
|  | Current process cost: | 473.1084 | 85.02 | 388.0884 | 0
|  | Expected process cost: | 22.94 | 9.484 | 13.456 | 0
|  | Process Cost Difference: | 450.1684 | 75.536 | 374.6324 | 0
Process
| Current Process | [7 empty] | Expected Process
| 030.01 | Receive Facility Criteria and Discipline Specifications | [6 empty] | 030.01 | Receive Facility Criteria and Discipline Specifications
| 030.02 | Review Facility Criteria and Discipline Specifications Data | [6 empty] | 030.02 | Review Facility Criteria and Discipline Specifications Data
| 030.03 | Produce Feasibility Study | [6 empty] | 030.03 | Produce Feasibility Study
COPYING/ ELEC.DOC. | 030.04 | Copy Feasibility Study | [5 empty] | COPYING/ ELEC.DOC. | 030.04 | Copy Feasibility Study
|  | 3 | Avg. Number of Options | [6 empty] | 3 | Avg. Number of Options
|  | 3 | Avg. Number of Sheets per Option | [6 empty] | 3 | Avg. Number of Sheets per Option
|  | 10 | Avg. Number of Letter-Sized Pages in Pre-Design Narrative per Option | [6 empty] | 10 | Avg. Number of Letter-Sized Pages in Pre-Design Narrative per Option
|  | 4 | Avg. Number of Pre-Design Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Avg. Number of Pre-Design Submittal Sets Reqd. (sets / submittal)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 3 | Avg. Per Sheet Copy Cost ($ / sheet) | [6 empty] | 0 | Avg. Per Sheet Copy Cost ($ / sheet)
|  | 0.015 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 1.0092 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) | 0
|  |  | Reproduction Costs |  |  | 126 |  |  |  |  | Reproduction Costs | 0
|  |  | SubTotal |  |  |  | 127.0092 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 030.05 | Send Feasibility Study | [5 empty] | HANDLING/ ELEC.DOC. | 030.05 | Send Feasibility Study
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 18.8 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 16.82 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) | 6.728
|  |  | Mailing Costs |  |  | 37.6 |  |  |  |  | Mailing Costs | 0
|  |  | SubTotal |  |  |  | 54.42 |  |  |  | SubTotal |  | 6.728
HANDLING/ ELEC.DOC. | 030.06 | Log Transmittal of Feasibility Study | [5 empty] | HANDLING/ ELEC.DOC. | 030.06 | Log Transmittal of Feasibility Study
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 8.41 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 8.41 |  |  |  | SubTotal |  | 0
| 030.07 | Receive Feasibility Study | [6 empty] | 030.07 | Receive Feasibility Study
HANDLING/ ELEC.DOC. | 030.08 | Log Receipt of Feasibility Study | [5 empty] | HANDLING/ ELEC.DOC. | 030.08 | Log Receipt of Feasibility Study
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 23.71 | Owner Administrative Rate ($ / hour) |  |  | 11.855 |  |  |  | 23.71 | Owner Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 11.855 |  |  |  | SubTotal |  | 0
| 030.09 | Review Feasibility Study | [6 empty] | 030.09 | Review Feasibility Study
HANDLING/ ELEC.DOC. | 030.10.20 | Send Comments to Planner | [5 empty] | HANDLING/ ELEC.DOC. | 030.10.20 | Send Comments to Planner
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 18.8 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 23.71 | Owner Administrative Rate ($ / hour) |  |  | 23.71 |  |  |  | 23.71 | Owner Administrative Rate ($ / hour) | 9.484
|  |  | Mailing Costs |  |  | 37.6 |  |  |  |  | Mailing Costs | 0
|  |  | SubTotal |  |  |  | 61.31 |  |  |  | SubTotal |  | 9.484
HANDLING/ ELEC.DOC. | 030.10.21 | Log Transmittal of Feasibility Study Comments | [5 empty] | HANDLING/ ELEC.DOC. | 030.10.21 | Log Transmittal of Feasibility Study Comments
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 23.71 | Owner Administrative Rate ($ / hour) |  |  | 11.855 |  |  |  | 23.71 | Owner Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 11.855 |  |  |  | SubTotal |  | 0
| 030.11 | Receive Feasibility Review Comments | [6 empty] | 030.11 | Receive Feasibility Review Comments
HANDLING/ ELEC.DOC. | 030.12 | Log Receipt of Review Comments | [5 empty] | HANDLING/ ELEC.DOC. | 030.12 | Log Receipt of Review Comments
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 8.41 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 8.41 |  |  |  | SubTotal |  | 0
| 030.13 | Revise Feasibility Study | [6 empty] | 030.13 | Revise Feasibility Study
COPYING/ ELEC.DOC. | 030.14 | Copy Revised Feasibility Study | [5 empty] | COPYING/ ELEC.DOC. | 030.14 | Copy Revised Feasibility Study
|  | 3 | Avg. Number of Options | [6 empty] | 3 | Avg. Number of Options
|  | 3 | Avg. Number of Sheets per Option | [6 empty] | 3 | Avg. Number of Sheets per Option
|  | 10 | Avg. Number of Letter-Sized Pages in Pre-Design Narrative per Option | [6 empty] | 10 | Avg. Number of Letter-Sized Pages in Pre-Design Narrative per Option
|  | 4 | Avg. Number of Pre-Design Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Avg. Number of Pre-Design Submittal Sets Reqd. (sets / submittal)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 3 | Avg. Per Sheet Copy Cost ($ / sheet) | [6 empty] | 0 | Avg. Per Sheet Copy Cost ($ / sheet)
|  | 0.015 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 1.0092 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) | 0
|  |  | Reproduction Costs |  |  | 126 |  |  |  |  | Reproduction Costs | 0
|  |  | SubTotal |  |  |  | 127.0092 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 030.15 | Send Revised Feasibility Study | [5 empty] | HANDLING/ ELEC.DOC. | 030.15 | Send Revised Feasibility Study
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 18.8 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 16.82 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) | 6.728
|  |  | Mailing Costs |  |  | 37.6 |  |  |  |  | Mailing Costs | 0
|  |  | SubTotal |  |  |  | 54.42 |  |  |  | SubTotal |  | 6.728
HANDLING/ ELEC.DOC. | 030.16 | Log Transmittal of Revised Feasibility Study | [5 empty] | HANDLING/ ELEC.DOC. | 030.16 | Log Transmittal of Revised Feasibility Study
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 8.41 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 8.41 |  |  |  | SubTotal |  | 0
[6 empty] | Current Process Total | 473.1084 |  |  |  |  | Expected Process Total | 22.94

## 040_Project_Definition
| Process Name | Project Definition
| OmniClass Stage | 31-10 11 14 Project Description Phase
| OmniClass Role | 34-21 14 00 Owner
| Description | Initial criteria about a project must be established in order to evaluate the project feasibility. The Owner evaluates the Facility Criteria, Discipline Specification, and Feasibility Study to determine whether or not to move forward with the project.
Information Attributes
|  |  | Total | Owner | Architect/ Planner | Contractor
|  | Current process cost: | 0.66323 | 0.66323 | 0 | 0
|  | Expected process cost: | 0 | 0 | 0 | 0
|  | Process Cost Difference: | 0.66323 | 0.66323 | 0 | 0
Process
| Current Process | [7 empty] | Expected Process
| 040.01 | Review Information for Facility Criteria, Discipline Specifications, and Feasibility Study | [6 empty] | 040.01 | Review Information for Facility Criteria, Discipline Specifications, and Feasibility Study
| 040.02 | Evaluate Total Risk | [6 empty] | 040.02 | Evaluate Total Risk
| 040.03.10 | Produce Project Definition | [6 empty] | 040.03.10 | Produce Project Definition
COPYING/ ELEC.DOC. | 040.03.30 | Copy Project definition | [5 empty] | COPYING/ ELEC.DOC. | 040.03.30 | Copy Project definition
|  | 2 | Avg. Number of Pages in Project Definition | [6 empty] | 2 | Avg. Number of Pages in Project Definition
|  | 2 | Avg. Number of Sets Required (sets / submittal) | [6 empty] | 0 | Avg. Number of Sets Required (sets / submittal)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 0.0013333 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 23.71 | Owner Administrative Rate ($ / hour) |  |  | 0.063227 |  |  |  | 23.71 | Owner Administrative Rate ($ / hour) | 0
|  |  | Reproduction Costs |  |  | 0.6 |  |  |  |  | Reproduction Costs | 0
|  |  | SubTotal |  |  |  | 0.66323 |  |  |  | SubTotal |  | 0
[6 empty] | Current Process Total | 0.66323 |  |  |  |  | Expected Process Total | 0

## 050_Space_Program
| Process Name | Space Program
| OmniClass Stage | 31-10 14 21 Project Programming Phase
| OmniClass Role | 34-21 17 00 Planner
| Description | Once the Project Definition has been established and approved, further development of the project requirements can occur. The Architect or Planner evaluates information contained in the Project Definition information exchange to identify space needs based on the facility type. If no standard facility space criteria exist, it must be created by referencing similar facility types.
Information Attributes
|  |  | Total | Owner | Planner/ Architect | Contractor
|  | Current process cost: | 506.9804 | 105.0032 | 401.9772 | 0
|  | Expected process cost: | 6.7659 | 4.4784 | 2.2875 | 0
|  | Process Cost Difference: | 500.2145 | 100.5248 | 399.6897 | 0
Process
| Current Process | [7 empty] | Expected Process
| 050.01 | Utilize Project Definition to Develop Space Program Criteria | [6 empty] | 050.01 | Utilize Project Definition to Develop Space Program Criteria
| 050.02 | Evaluate Space Program Information | [6 empty] | 050.02 | Evaluate Space Program Information
RECREATING/ COBie | 050.03 | Search for Space Program Criteria as Necessary | [5 empty] | RECREATING/ COBie | 050.03 | Search for Space Program Criteria as Necessary
|  | 18 | Number of Space Types per Project | [6 empty] | 18 | Number of Space Types per Project
|  | 0.25 | Avg. Time Spent Searching for Space Program Criteria (hours /space) | [6 empty] | 0 | Avg. Time Spent Recreating Space Program Criteria (hours /space)
|  | 37.84 | Planner Rate ($ / hour) |  |  | 170.28 |  |  |  | 37.84 | Planner Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 170.28 |  |  |  | SubTotal |  | 0
REFORMATTING/ COBie | 050.04 | Reformat Space Program Criteria into Room Data Sheets | [5 empty] | REFORMATTING/ COBie | 050.04 | Reformat Space Program Criteria into Room Data Sheets
|  | 18 | Number of Space Types per Project | [6 empty] | 18 | Number of Space Types per Project
|  | 0.08 | Avg. Time Spent Reformatting Space Program Criteria into Room Data Sheets (hours/space) | [6 empty] | 0 | Avg. Time Spent Reformatting Space Program Criteria into Room Data Sheets (hours/space)
|  | 37.84 | Planner Rate ($ / hour) |  |  | 54.4896 |  |  |  | 37.84 | Planner Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 54.4896 |  |  |  | SubTotal |  | 0
COPYING & HANDLING/ ELEC.DOC. | 050.05 | Send Copies of Space Program | [5 empty] | COPYING & HANDLING/ ELEC.DOC. | 050.05 | Send Copies of Space Program
|  | 5.94 | Avg. Number of Pages in Space Program | [6 empty] | 5.94 | Avg. Number of Pages in Space Program
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 18.8 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 4 | Avg. Number of Pre-Design Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Avg. Number of Pre-Design Submittal Sets Reqd. (sets / submittal)
|  | 0.17 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.068 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 5.7188 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) | 2.2875
|  |  | Copying Costs |  |  | 7.128 |  |  |  |  | Copying Costs | 0
|  |  | Mailing Costs |  |  | 37.6 |  |  |  |  | Mailing Costs | 0
|  |  | SubTotal |  |  |  | 50.4468 |  |  |  | SubTotal |  | 2.2875
HANDLING/ ELEC.DOC. | 050.06 | Log Transmittal of Space Program | [5 empty] | HANDLING/ ELEC.DOC. | 050.06 | Log Transmittal of Space Program
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 8.41 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 8.41 |  |  |  | SubTotal |  | 0
| 050.07 | Receive Space Program | [6 empty] | 050.07 | Receive Space Program
HANDLING/ ELEC.DOC. | 050.08 | Log Receipt of Space Program | [5 empty] | HANDLING/ ELEC.DOC. | 050.08 | Log Receipt of Space Program
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 8.44 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 8.44 |  |  |  | SubTotal |  | 0
VALIDATING/ COBie | 050.09 | Validate Space Program | [5 empty] | VALIDATING/ COBie | 050.09 | Validate Space Program
|  | 0.72 | Avg. Time for Owners Rep to Validate Space Program (hours) | [6 empty] | 0.072 | Avg. Time for Owners Rep to Validate Space Program (hours)
|  | 62.2 | Owners Rep. Rate ($ / hour) |  |  | 44.784 |  |  |  | 62.2 | Owners Rep. Rate ($ / hour) | 4.4784
|  |  | SubTotal |  |  |  | 44.784 |  |  |  | SubTotal |  | 4.4784
HANDLING/ ELEC.DOC. | 050.10.10 | Send Comments | [5 empty] | HANDLING/ ELEC.DOC. | 050.10.10 | Send Comments
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 18.8 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.17 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.068 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 5.7392 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | Mailing Costs |  |  | 37.6 |  |  |  |  | Mailing Costs | 0
|  |  | SubTotal |  |  |  | 43.3392 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 050.10.20 | Log Transmittal of Space Program Comments | [5 empty] | HANDLING/ ELEC.DOC. | 050.10.20 | Log Transmittal of Space Program Comments
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 8.44 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 8.44 |  |  |  | SubTotal |  | 0
| 050.11 | Receive Comments | [6 empty] | 050.11 | Receive Comments
HANDLING/ ELEC.DOC. | 050.12 | Log Receipt of Space Program | [5 empty] | HANDLING/ ELEC.DOC. | 050.12 | Log Receipt of Space Program
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 8.41 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 8.41 |  |  |  | SubTotal |  | 0
RECREATING/ COBie | 050.13 | Re - Search for Space Program Criteria as Necessary | [5 empty] | RECREATING/ COBie | 050.13 | Re - Search for Space Program Criteria as Necessary
|  | 30% | Avg. Percentage of errors in Space Program | [6 empty] | 3% | Avg. Percentage of errors in Space Program
|  | 18 | Number of Space Types per Project | [6 empty] | 18 | Number of Space Types per Project
|  | 0.25 | Avg. Time Spent Re - Searching for Space Program Criteria (hours /space) | [6 empty] | 0 | Avg. Time Spent Re - Searching for Space Program Criteria (hours /space)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 37.84 | Planner Rate ($ / hour) |  |  | 51.084 |  |  |  | 37.84 | Planner Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 51.084 |  |  |  | SubTotal |  | 0
COPYING & HANDLING/ ELEC.DOC. | 050.14 | Send Revised Copies of Space Program | [5 empty] | COPYING & HANDLING/ ELEC.DOC. | 050.14 | Send Revised Copies of Space Program
|  | 5.94 | Avg. Number of Pages in Space Program | [6 empty] | 5.94 | Avg. Number of Pages in Space Program
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 18.8 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 4 | Avg. Number of Pre-Design Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Avg. Number of Pre-Design Submittal Sets Reqd. (sets / submittal)
|  | 0.17 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.068 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 5.7188 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) | 0
|  |  | Copying Costs |  |  | 7.128 |  |  |  |  | Copying Costs | 0
|  |  | Mailing Costs |  |  | 37.6 |  |  |  |  | Mailing Costs | 0
|  |  | SubTotal |  |  |  | 50.4468 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 050.15 | Log Transmittal of Revised Space Program | [5 empty] | HANDLING/ ELEC.DOC. | 050.15 | Log Transmittal of Revised Space Program
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 8.41 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 8.41 |  |  |  | SubTotal |  | 0
[6 empty] | Current Process Total | 506.9804 |  |  |  |  | Expected Process Total | 6.7659

## 060_Product_Program
| Process Name | Product Program
| OmniClass Stage | 31-10 14 21 Project Programming Phase
| OmniClass Role | 34-21 17 00 Planner
| Description | The Architect or Planner evaluates information contained in the Project Definition information exchange to identify product needs based on the facility type. If no standard facility product criteria exist, it must be created by referencing similar facility types.
Information Attributes
|  |  | Total | Owner | Planner/ Architect | Contractor
|  | Current process cost: | 539.9933 | 204.2492 | 335.7441 | 0
|  | Expected process cost: | 15.6605 | 13.373 | 2.2875 | 0
|  | Process Cost Difference: | 524.3328 | 190.8762 | 333.4566 | 0
Process
| Current Process | [7 empty] | Expected Process
| 060.01 | Utilize Project Definition & Space Requirements to Determine Product Program | [6 empty] | 060.01 | Utilize Project Definition & Space Requirements to Determine Product Program
| 060.02 | Evaluate Product Program Information | [6 empty] | 060.02 | Evaluate Product Program Information
RECREATING/ COBie | 060.03 | Search for Product Program Criteria as Necessary | [5 empty] | RECREATING/ COBie | 060.03 | Search for Product Program Criteria as Necessary
|  | 43 | Number of Unique Product Types (Types / project) | [6 empty] | 43 | Number of Unique Product Types (Types / project)
|  | 0.08 | Avg. Time Spent Searching for Product Program Criteria (hours / product) | [6 empty] | 0 | Avg. Time Spent Searching for Product Program Criteria (hours / product)
|  | 37.84 | Planner Rate ($ / hour) |  |  | 130.1696 |  |  |  | 37.84 | Planner Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 130.1696 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 060.04 | Send Copies of Product Program to Owner for Review | [5 empty] | HANDLING/ ELEC.DOC. | 060.04 | Send Copies of Product Program to Owner for Review
|  | 14.19 | Avg. Number of Pages in Product Program | [6 empty] | 14.19 | Avg. Number of Pages in Product Program
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 23.95 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 4 | Avg. Number of Pre-Design Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Avg. Number of Pre-Design Submittal Sets Reqd. (sets / submittal)
|  | 0.17 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.068 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 5.7188 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) | 2.2875
|  |  | Copying Costs |  |  | 17.028 |  |  |  |  | Copying Costs | 0
|  |  | Mailing Costs |  |  | 47.9 |  |  |  |  | Mailing Costs | 0
|  |  | SubTotal |  |  |  | 70.6468 |  |  |  | SubTotal |  | 2.2875
HANDLING/ ELEC.DOC. | 060.05 | Log Transmittal of Product Program | [5 empty] | HANDLING/ ELEC.DOC. | 060.05 | Log Transmittal of Product Program
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 8.41 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 8.41 |  |  |  | SubTotal |  | 0
| 060.06 | Receive Product Program | [6 empty] | 060.06 | Receive Product Program
HANDLING/ ELEC.DOC. | 060.07 | Log Receipt of Product Program | [5 empty] | HANDLING/ ELEC.DOC. | 060.07 | Log Receipt of Product Program
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 8.44 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 8.44 |  |  |  | SubTotal |  | 0
VALIDATING/ COBie | 060.08 | Validate Product Program | [5 empty] | VALIDATING/ COBie | 060.08 | Validate Product Program
|  | 2.15 | Avg. Time for Owners Rep to Validate Product Program (hours) | [6 empty] | 0.215 | Avg. Time for Owners Rep to Validate Product Program (hours)
|  | 62.2 | Owners Rep. Rate ($ / hour) |  |  | 133.73 |  |  |  | 62.2 | Owners Rep. Rate ($ / hour) | 13.373
|  |  | SubTotal |  |  |  | 133.73 |  |  |  | SubTotal |  | 13.373
HANDLING/ ELEC.DOC. | 060.09.10 | Send Comments | [5 empty] | HANDLING/ ELEC.DOC. | 060.09.10 | Send Comments
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 23.95 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.17 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.068 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 5.7392 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | Mailing Costs |  |  | 47.9 |  |  |  |  | Mailing Costs | 0
|  |  | SubTotal |  |  |  | 53.6392 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 060.09.20 | Log Transmittal of Product Program Comments | [5 empty] | HANDLING/ ELEC.DOC. | 060.09.20 | Log Transmittal of Product Program Comments
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 8.44 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 8.44 |  |  |  | SubTotal |  | 0
| 060.10 | Receive Comments | [6 empty] | 060.10 | Receive Comments
HANDLING/ ELEC.DOC. | 060.11 | Log Receipt of Product Program Comments | [5 empty] | HANDLING/ ELEC.DOC. | 060.11 | Log Receipt of Product Program Comments
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 8.41 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 8.41 |  |  |  | SubTotal |  | 0
RECREATING/ COBie | 060.12 | Re - Search for Product Program Criteria as Necessary | [5 empty] | RECREATING/ COBie | 060.12 | Re - Search for Product Program Criteria as Necessary
|  | 30% | Avg. Percent of errors in Product Program | [6 empty] | 3% | Avg. Percent of errors in Product Program
|  | 43 | Number of Unique Product Types (Types / project) | [6 empty] | 43 | Number of Unique Product Types (Types / project)
|  | 0.08 | Avg. Time Spent Re - Searching for Product Program Criteria (hours / product) | [6 empty] | 0 | Avg. Time Spent Re - Searching for Product Program Criteria (hours / product)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 37.84 | Planner Rate ($ / hour) |  |  | 39.0509 |  |  |  | 37.84 | Planner Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 39.0509 |  |  |  | SubTotal |  | 0
COPYING & HANDLING/ ELEC.DOC. | 060.13 | Send Revised Copies of Product Program | [5 empty] | COPYING & HANDLING/ ELEC.DOC. | 060.13 | Send Revised Copies of Product Program
|  | 14.19 | Avg. Number of Pages in Product Program | [6 empty] | 14.19 | Avg. Number of Pages in Product Program
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 23.95 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 4 | Avg. Number of Pre-Design Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Avg. Number of Pre-Design Submittal Sets Reqd. (sets / submittal)
|  | 0.17 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.068 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 5.7188 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) | 0
|  |  | Copying Costs |  |  | 17.028 |  |  |  |  | Copying Costs | 0
|  |  | Mailing Costs |  |  | 47.9 |  |  |  |  | Mailing Costs | 0
|  |  | SubTotal |  |  |  | 70.6468 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 060.14 | Log Transmittal of Revised Product Program | [5 empty] | HANDLING/ ELEC.DOC. | 060.14 | Log Transmittal of Revised Product Program
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 16.82 | Planner Administrative Rate ($ / hour) |  |  | 8.41 |  |  |  | 16.82 | Planner Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 8.41 |  |  |  | SubTotal |  | 0
[6 empty] | Current Process Total | 539.9933 |  |  |  |  | Expected Process Total | 15.6605

## 070_Request_For_Proposal
| Process Name | Request For Proposal
| OmniClass Stage | 31-10 14 21 Project Programming Phase
| OmniClass Role | 34-21 17 00 Planner
| Description | Once the major criteria have been determined, the Owner prepares and distributes a Request for Proposal (RFP).
Information Attributes
|  |  | Total | Owner | Architect | Contractor
|  | Current process cost: | 401.4648 | 266.2875 | 135.1773 | 0
|  | Expected process cost: | 53.6 | 25.32 | 28.28 | 0
|  | Process Cost Difference: | 347.8648 | 240.9675 | 106.8973 | 0
Process
| Current Process | [7 empty] | Expected Process
| 070.01 | Produce Request for Proposal Documents | [6 empty] | 070.01 | Produce Request for Proposal Documents
COPYING & HANDLING/ ELEC.DOC. | 070.02 | Send Copies of Request for Proposal (RFP) Package | [5 empty] | COPYING & HANDLING/ ELEC.DOC. | 070.02 | Send Copies of Request for Proposal (RFP) Package
|  | 5.94 | Avg. Number of Pages in Space Program | [6 empty] | 5.94 | Avg. Number of Pages in Space Program
|  | 14.19 | Avg. Number of Pages in Product Program | [6 empty] | 14.19 | Avg. Number of Pages in Product Program
|  | 2 | Avg. Number of Pages in Project Definition | [6 empty] | 2 | Avg. Number of Pages in Project Definition
|  | 10 | Avg. Number of Pages in Front Matter | [6 empty] | 10 | Avg. Number of Pages in Front Matter
|  | 5 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 5 | Avg. Number of Transmittals (Transmittals)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 5 | Number of RFP Submittal sets Reqd. | [6 empty] | 0 | Number of RFP Submittal sets Reqd.
|  | 0.75 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.3 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 63.3 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 25.32
|  |  | Copying Cost |  |  | 120.4875 |  |  |  |  | Copying Cost | 0
|  |  | Mailing Cost |  |  | 82.5 |  |  |  |  | Mailing Cost | 0
|  |  | SubTotal |  |  |  | 266.2875 |  |  |  | SubTotal |  | 25.32
| 070.03 | Receive Request for Proposal (RFP) Package | [6 empty] | 070.03 | Receive Request for Proposal (RFP) Package
HANDLING/ ELEC.DOC. | 070.04 | Log Receipt of Request for Proposal (RFP) Package | [5 empty] | HANDLING/ ELEC.DOC. | 070.04 | Log Receipt of Request for Proposal (RFP) Package
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 17.675 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 17.675 |  |  |  | SubTotal |  | 0
| 070.05 | Review Request for Proposal (RFP) Package | [6 empty] | 070.05 | Review Request for Proposal (RFP) Package
| 070.06 | Produce Proposal | [6 empty] | 070.06 | Produce Proposal
COPYING/ ELEC.DOC. | 070.07 | Copy Proposal | [5 empty] | COPYING/ ELEC.DOC. | 070.07 | Copy Proposal
|  | 6 | Avg. Number of Letter Sized Pages in Proposal | [6 empty] | 6 | Avg. Number of Letter Sized Pages in Proposal
|  | 2 | Avg. Number of Drawing Sheets in Proposal | [6 empty] | 2 | Avg. Number of Drawing Sheets in Proposal
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 3 | Avg. Per Sheet Copy Cost ($ / sheet) | [6 empty] | 0 | Avg. Per Sheet Copy Cost ($ / sheet)
|  | 4 | Avg. Number of Pre-Design Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Avg. Number of Pre-Design Submittal Sets Reqd. (sets / submittal)
|  | 0.0095556 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 2.7023 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | Reproduction Costs |  |  | 27.6 |  |  |  |  | Reproduction Costs | 0
|  |  | SubTotal |  |  |  | 30.3023 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 070.08 | Send Proposal | [5 empty] | HANDLING/ ELEC.DOC. | 070.08 | Send Proposal
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 1 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.4 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 70.7 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 28.28
|  |  | Mailing Costs |  |  | 16.5 |  |  |  |  | Mailing Costs | 0
|  |  | SubTotal |  |  |  | 87.2 |  |  |  | SubTotal |  | 28.28
[6 empty] | Current Process Total | 401.4648 |  |  |  |  | Expected Process Total | 53.6

## 080_Design_Early
| Process Name | Design Early
| OmniClass Stage | 31-20 10 14 Conceptual Design Phase
| OmniClass Role | 34-25 21 00 Architect
| Description | The Architect utilizes the specific information produced during pre-design to develop a solution that reflects the requirements stated in the Project Definition, Space Program, and Product Program. The Architect performs a QA/QC check before submitting to the owner. After receiving the submission, the Owner's Representative reviews and provides comments to the Architect. The Architect and Consultants are then required to update the documents based on the comments. After revisions are made, the Architect resubmits.
Information Attributes
|  |  | Total | Owner | Architect | Contractor
|  | Current process cost: | 4902.9573 | 482.3915 | 4420.5658 | 0
|  | Expected process cost: | 137.3144 | 22.5336 | 114.7808 | 0
|  | Process Cost Difference: | 4765.6428 | 459.8579 | 4305.7849 | 0
Process
| Current Process | [7 empty] | Expected Process
| 080.01 | Receive NTP | [6 empty] | 080.01 | Receive NTP
| 080.02 | Request Design Requirements | [6 empty] | 080.02 | Request Design Requirements
HANDLING/ ELEC.DOC. | 080.03 | Send Copies of Design Requirements | [5 empty] | HANDLING/ ELEC.DOC. | 080.03 | Send Copies of Design Requirements
|  | 5.94 | Avg. Number of Pages in Space Program | [6 empty] | 5.94 | Avg. Number of Pages in Space Program
|  | 14.19 | Avg. Number of Pages in Product Program | [6 empty] | 14.19 | Avg. Number of Pages in Product Program
|  | 2 | Avg. Number of Pages in Project Definition | [6 empty] | 2 | Avg. Number of Pages in Project Definition
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 8.44 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 3.376
|  |  | Copying Cost |  |  | 3.3195 |  |  |  |  | Copying Cost | 0
|  |  | Mailing Cost |  |  | 16.5 |  |  |  |  | Mailing Cost | 0
|  |  | SubTotal |  |  |  | 28.2595 |  |  |  | SubTotal |  | 3.376
HANDLING/ ELEC.DOC. | 080.04 | Log Transmittal of Design Requirements | [5 empty] | HANDLING/ ELEC.DOC. | 080.04 | Log Transmittal of Design Requirements
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 4.22 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 4.22 |  |  |  | SubTotal |  | 0
| 080.05 | Receive Design Requirements | [6 empty] | 080.05 | Receive Design Requirements
HANDLING/ ELEC.DOC. | 080.06 | Log Receipt of Design Requirements | [5 empty] | HANDLING/ ELEC.DOC. | 080.06 | Log Receipt of Design Requirements
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 17.675 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 17.675 |  |  |  | SubTotal |  | 0
| 080.07 | Review Design Requirements | [6 empty] | 080.07 | Review Design Requirements
REFORMATTING/ COBie | 080.08 | Reformat Design Requirements | [5 empty] | REFORMATTING/ COBie | 080.08 | Reformat Design Requirements
|  | 18 | Number of Space Types per Project | [6 empty] | 18 | Number of Space Types per Project
|  | 0.16 | Avg. Time Spent Reformatting Space Program (hours / space) | [6 empty] | 0 | Avg. Time Spent Reformatting Space Program (hours / space)
|  | 43 | Number of Unique Product Types (Types / project) | [6 empty] | 43 | Number of Unique Product Types (Types / project)
|  | 0.25 | Avg. Time Spent Reformatting Product Program (hours /product) | [6 empty] | 0 | Avg. Time Spent Reformatting Product Program (hours /product)
|  | 90% | Percentage of Time Spent by Licensed Professional Architect | [6 empty] | 90% | Percentage of Time Spent by Licensed Professional Architect
|  | 10% | Percentage of Time Spent by Architect Drafter | [6 empty] | 10% | Percentage of Time Spent by Architect Drafter
|  | 109.99 | Licensed Professional Architect Rate ($ / hour) |  |  | 1349.2473 |  |  |  | 109.99 | Licensed Professional Architect Rate ($ / hour) | 0
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 96.3641 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 1445.6114 |  |  |  | SubTotal |  | 0
| 080.09 | Produce Design Early Documents | [6 empty] | 080.09 | Produce Design Early Documents
| 080.10 | Receive Consultant's Early Design Documents | [6 empty] | 080.10 | Receive Consultant's Early Design Documents
| 080.11 | Produce Checkset of Design Early Documents | [6 empty] | 080.11 | Produce Checkset of Design Early Documents
VALIDATING/ COBie | 080.12 | Validate Checkset before Submission through manual QA/QC Process – Space and Equipment | [5 empty] | VALIDATING/ COBie | 080.12 | Validate Checkset before Submission through manual QA/QC Process – Space and Equipment
|  | 9.15 | Avg. Time Spent Evaluating Design Early Drawings against Design Requirements - Space and Equipment | [6 empty] | 0.915 | Avg. Time Spent Evaluating Design Early Drawings against Design Requirements - Space and Equipment
|  | 109.99 | Licensed Professional Architect Rate ($ / hour) |  |  | 1006.4085 |  |  |  | 109.99 | Licensed Professional Architect Rate ($ / hour) | 100.6408
|  |  | SubTotal |  |  |  | 1006.4085 |  |  |  | SubTotal |  | 100.6408
RECREATING/ COBie | 080.13.10 | Make Corrections (Architect and/or Consultants) | [5 empty] | RECREATING/ COBie | 080.13.10 | Make Corrections (Architect and/or Consultants)
|  | 1.5189 | Avg. Time spent making corrections due to non-conformance with Space or Product Program | [6 empty] | 0 | Avg. Time spent making corrections due to non-conformance with Space or Product Program
|  | 109.99 | Licensed Professional Architect Rate ($ / hour) |  |  | 167.0638 |  |  |  | 109.99 | Licensed Professional Architect Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 167.0638 |  |  |  | SubTotal |  | 0
COPYING/ ELEC.DOC. | 080.13.20 | Copy Design Early Documents | [5 empty] | COPYING/ ELEC.DOC. | 080.13.20 | Copy Design Early Documents
|  | 37.3333 | Avg. Number of Sheets in Design Early Drawings | [6 empty] | 37.3333 | Avg. Number of Sheets in Design Early Drawings
|  | 10 | Avg. Number of Letter-Sized Pages in Design Early Narrative | [6 empty] | 10 | Avg. Number of Letter-Sized Pages in Design Early Narrative
|  | 6 | Number of Design Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Number of Design Submittal Sets Reqd. (sets / submittal)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 3 | Avg. Per Sheet Copy Cost ($ / sheet) | [6 empty] | 0 | Avg. Per Sheet Copy Cost ($ / sheet)
|  | 0.11037 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 46.8191 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | Copying Cost |  |  | 681 |  |  |  |  | Copying Cost | 0
|  |  | SubTotal |  |  |  | 727.8191 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 080.13.30 | Send Design Early Documents | [5 empty] | HANDLING/ ELEC.DOC. | 080.13.30 | Send Design Early Documents
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 21.6 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 35.35 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 14.14
|  |  | Mailing Cost |  |  | 21.6 |  |  |  |  | Mailing Cost | 0
|  |  | SubTotal |  |  |  | 56.95 |  |  |  | SubTotal |  | 14.14
HANDLING/ ELEC.DOC. | 080.13.40 | Log Transmittal of Design Early Documents | [5 empty] | HANDLING/ ELEC.DOC. | 080.13.40 | Log Transmittal of Design Early Documents
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 17.675 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 17.675 |  |  |  | SubTotal |  | 0
| 080.14 | Receive Design Early Documents | [6 empty] | 080.14 | Receive Design Early Documents
HANDLING/ ELEC.DOC. | 080.15 | Log Receipt of Design Early Documents | [5 empty] | HANDLING/ ELEC.DOC. | 080.15 | Log Receipt of Design Early Documents
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 4.22 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 4.22 |  |  |  | SubTotal |  | 0
VALIDATING/ COBie | 080.16 | Validate Design Early Documents - Space and Equipment | [5 empty] | VALIDATING/ COBie | 080.16 | Validate Design Early Documents - Space and Equipment
|  | 3.08 | Avg Time to Review Design Early Drawings for conformance to Space and Product Program | [6 empty] | 0.308 | Avg Time to Review Design Early Drawings for conformance to Space and Product Program
|  | 62.2 | Owners Rep. Rate ($ / hour) |  |  | 191.576 |  |  |  | 62.2 | Owners Rep. Rate ($ / hour) | 19.1576
|  |  | SubTotal |  |  |  | 191.576 |  |  |  | SubTotal |  | 19.1576
HANDLING/ ELEC.DOC. | 080.17.20 | Send Comments to Design Team | [5 empty] | HANDLING/ ELEC.DOC. | 080.17.20 | Send Comments to Design Team
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 8.44 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | Mailing Cost |  |  | 16.5 |  |  |  |  | Mailing Cost | 0
|  |  | SubTotal |  |  |  | 24.94 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 080.17.30 | Log Transmittal of Comments | [5 empty] | HANDLING/ ELEC.DOC. | 080.17.30 | Log Transmittal of Comments
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 4.22 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 4.22 |  |  |  | SubTotal |  | 0
| 080.18 | Receive Review Comments | [6 empty] | 080.18 | Receive Review Comments
HANDLING/ ELEC.DOC. | 080.19 | Log Receipt of Comments | [5 empty] | HANDLING/ ELEC.DOC. | 080.19 | Log Receipt of Comments
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 17.675 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 17.675 |  |  |  | SubTotal |  | 0
RECREATING/ COBie | 080.20 | Make Corrections (Architect and/or Consultants) | [5 empty] | RECREATING/ COBie | 080.20 | Make Corrections (Architect and/or Consultants)
|  | 1.5189 | Avg. Time spent making corrections due to non-conformance with Space or Product Program | [6 empty] | 0 | Avg. Time spent making corrections due to non-conformance with Space or Product Program
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 109.99 | Licensed Professional Architect Rate ($ / hour) |  |  | 167.0638 |  |  |  | 109.99 | Licensed Professional Architect Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 167.0638 |  |  |  | SubTotal |  | 0
COPYING/ ELEC.DOC. | 080.21 | Copy Revised Design Early Documents | [5 empty] | COPYING/ ELEC.DOC. | 080.21 | Copy Revised Design Early Documents
|  | 37.3333 | Avg. Number of Sheets in Design Early Drawings | [6 empty] | 37.3333 | Avg. Number of Sheets in Design Early Drawings
|  | 10 | Avg. Number of Letter-Sized Pages in Design Early Narrative | [6 empty] | 10 | Avg. Number of Letter-Sized Pages in Design Early Narrative
|  | 6 | Number of Design Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Number of Design Submittal Sets Reqd. (sets / submittal)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 3 | Avg. Per Sheet Copy Cost ($ / sheet) | [6 empty] | 0 | Avg. Per Sheet Copy Cost ($ / sheet)
|  | 0.11037 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 46.8191 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | Copying Cost |  |  | 681 |  |  |  |  | Copying Cost | 0
|  |  | SubTotal |  |  |  | 727.8191 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 080.22 | Send Revised Design Early Documents | [5 empty] | HANDLING/ ELEC.DOC. | 080.22 | Send Revised Design Early Documents
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 21.6 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 23.71 | Architect Drafter Rate ($ / hour) |  |  | 11.855 |  |  |  | 23.71 | Architect Drafter Rate ($ / hour) | 0
|  |  | Mailing Cost |  |  | 21.6 |  |  |  |  | Mailing Cost | 0
|  |  | SubTotal |  |  |  | 33.455 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 080.23 | Log Transmittal of Revised Design Early Documents | [5 empty] | HANDLING/ ELEC.DOC. | 080.23 | Log Transmittal of Revised Design Early Documents
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 17.675 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 17.675 |  |  |  | SubTotal |  | 0
| 080.24 | Receive Design Early Documents | [6 empty] | 080.24 | Receive Design Early Documents
HANDLING/ ELEC.DOC. | 080.25 | Log Receipt of Revised Design Early Documents | [5 empty] | HANDLING/ ELEC.DOC. | 080.25 | Log Receipt of Revised Design Early Documents
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 4.22 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 4.22 |  |  |  | SubTotal |  | 0
VALIDATING/ COBie | 080.26 | Validate Revised Design Early Documents - Space and Equipment | [5 empty] | VALIDATING/ COBie | 080.26 | Validate Revised Design Early Documents - Space and Equipment
|  | 3.08 | Avg Time to Review Design Early Drawings for conformance to Space and Product Program | [6 empty] | 0.308 | Avg Time to Review Design Early Drawings for conformance to Space and Product Program
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 62.2 | Owners Rep. Rate ($ / hour) |  |  | 191.576 |  |  |  | 62.2 | Owners Rep. Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 191.576 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 080.27 | Send Comments to Design Team | [5 empty] | HANDLING/ ELEC.DOC. | 080.27 | Send Comments to Design Team
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 8.44 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | Mailing Cost |  |  | 16.5 |  |  |  |  | Mailing Cost | 0
|  |  | SubTotal |  |  |  | 24.94 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 080.28 | Log Transmittal of Comments | [5 empty] | HANDLING/ ELEC.DOC. | 080.28 | Log Transmittal of Comments
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 4.22 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 4.22 |  |  |  | SubTotal |  | 0
| 080.29 | Receive Review Comments | [6 empty] | 080.29 | Receive Review Comments
HANDLING/ ELEC.DOC. | 080.30 | Log Receipt of Comments | [5 empty] | HANDLING/ ELEC.DOC. | 080.30 | Log Receipt of Comments
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 17.675 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 17.675 |  |  |  | SubTotal |  | 0
[6 empty] | Current Process Total | 4902.9573 |  |  |  |  | Expected Process Total | 137.3144

## 090_Design_Schematic
| Process Name | Design Schematic, Product Type Template, & Product Type Candidate
| OmniClass Stage | 31-20 10 17 Schematic Design Phase
| OmniClass Role | 34-25 21 00 Architect
| Description | The Architect further develops the approved Design Early deliverable documents to produce the Design Schematic documents. The Architect performs a QA/QC check before submitting to the Owner. After receiving the submission, the Owner's Representative reviews and provides comments to the Architect. The Architect and Consultants are then required to update the documents based on the comments. After revisions are made the Architect resubmits.
Information Attributes
|  |  | Total | Owner | Architect | Contractor
|  | Current process cost: | 7131.835 | 526.5424 | 6605.2926 | 0
|  | Expected process cost: | 687.6756 | 22.9891 | 664.6864 | 0
|  | Process Cost Difference: | 6444.1595 | 503.5533 | 5940.6062 | 0
Process
| Current Process | [7 empty] | Expected Process
| 090.01 | Receive Design Early Approval Document from Owner's Rep | [6 empty] | 090.01 | Receive Design Early Approval Document from Owner's Rep
RECREATING/ COBie | 090.02.10 | Produce Design Schematic Documents | [5 empty] | RECREATING/ COBie | 090.02.10 | Produce Design Schematic Documents
|  | 11.2 | Avg. Number of Plan Drawings in Design Schematic Drawings | [6 empty] | 11.2 | Avg. Number of Plan Drawings in Design Schematic Drawings
|  | 0.08 | Avg QTO Time for Equipment Components (hours / plan drawing) | [6 empty] | 0.008 | Avg QTO Time for Equipment Components (hours / plan drawing)
|  | 0.16 | Avg QTO Time for Spaces in building (hours / plan drawing) | [6 empty] | 0.016 | Avg QTO Time for Spaces in building (hours / plan drawing)
|  | 80% | Percentage of Time Spent by Licensed Professional Architect | [6 empty] | 80% | Percentage of Time Spent by Licensed Professional Architect
|  | 20% | Percentage of Time Spent by Architect Drafter | [6 empty] | 20% | Percentage of Time Spent by Architect Drafter
|  | 109.99 | Licensed Professional Architect Rate ($ / hour) |  |  | 236.5225 |  |  |  | 109.99 | Licensed Professional Architect Rate ($ / hour) | 23.6522
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 38.0083 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 3.8008
|  |  | SubTotal |  |  |  | 274.5308 |  |  |  | SubTotal |  | 27.4531
REFORMATTING/COBie | 090.02.20 | Produce Outline Specification / Product Types Template | [5 empty] | REFORMATTING/COBie | 090.02.20 | Produce Outline Specification / Product Types Template
|  | 43 | Number of Unique Product Types (Types / project) | [6 empty] | 43 | Number of Unique Product Types (Types / project)
|  | 0.25 | Avg. Time Spent Developing Equipment (product) Type Template (hours / product type) | [6 empty] | 0.075 | Avg. Time Spent Developing Equipment (product) Type Template (hours / product type)
|  | 109.99 | Specifier |  |  | 1182.3925 |  |  |  | 109.99 | Specifier | 354.7178
|  |  | SubTotal |  |  |  | 1182.3925 |  |  |  | SubTotal |  | 354.7178
| 090.03 | Receive Consultant's Design Schematic Documents | [6 empty] | 090.03 | Receive Consultant's Design Schematic Documents
| 090.04 | Produce Checkset of Design Schematic Documents | [6 empty] | 090.04 | Produce Checkset of Design Schematic Documents
VALIDATING/ COBie | 090.05 | Validate Checkset before Submission through manual QA/QC Process - Space and Equipment | [5 empty] | VALIDATING/ COBie | 090.05 | Validate Checkset before Submission through manual QA/QC Process - Space and Equipment
|  | 24.4 | Avg. Time Spent Evaluating Design Schematic Drawings against Design Requirements - Space and Equipment | [6 empty] | 2.44 | Avg. Time Spent Evaluating Design Schematic Drawings against Design Requirements - Space and Equipment
|  | 109.99 | Licensed Professional Architect Rate ($ / hour) |  |  | 2683.756 |  |  |  | 109.99 | Licensed Professional Architect Rate ($ / hour) | 268.3756
|  |  | SubTotal |  |  |  | 2683.756 |  |  |  | SubTotal |  | 268.3756
RECREATING/ COBie | 090.06.10 | Make Corrections (Architect and/or Consultants) | [5 empty] | RECREATING/ COBie | 090.06.10 | Make Corrections (Architect and/or Consultants)
|  | 2.2784 | Avg. Time spent making corrections due to non-conformance with Space or Product Program | [6 empty] | 0 | Avg. Time spent making corrections due to non-conformance with Space or Product Program
|  | 109.99 | Licensed Professional Architect Rate ($ / hour) |  |  | 250.5957 |  |  |  | 109.99 | Licensed Professional Architect Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 250.5957 |  |  |  | SubTotal |  | 0
COPYING/ ELEC.DOC. | 090.06.20 | Copy Design Schematic & Product Type Template Documents | [5 empty] | COPYING/ ELEC.DOC. | 090.06.20 | Copy Design Schematic & Product Type Template Documents
|  | 44.8 | Avg. Number of Sheets in Design Schematic Drawings | [6 empty] | 44.8 | Avg. Number of Sheets in Design Schematic Drawings
|  | 20 | Avg. Number of Letter Sized Pages in Design Schematic Narrative | [6 empty] | 20 | Avg. Number of Letter Sized Pages in Design Schematic Narrative
|  | 2 | Avg. Number of Letter Sized Pages in a Design Schematic Specification | [6 empty] | 2 | Avg. Number of Letter Sized Pages in a Design Schematic Specification
|  | 6 | Number of Design Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Number of Design Submittal Sets Reqd. (sets / submittal)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 3 | Avg. Per Sheet Copy Cost ($ / sheet) | [6 empty] | 0 | Avg. Per Sheet Copy Cost ($ / sheet)
|  | 0.13911 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 59.0109 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | Copying Cost |  |  | 826.2 |  |  |  |  | Copying Cost | 0
|  |  | SubTotal |  |  |  | 885.2109 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 090.06.30 | Send Design Schematic & Product Type Template Documents | [5 empty] | HANDLING/ ELEC.DOC. | 090.06.30 | Send Design Schematic & Product Type Template Documents
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 25.8 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 35.35 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 14.14
|  |  | Mailing Cost |  |  | 25.8 |  |  |  |  | Mailing Cost | 0
|  |  | SubTotal |  |  |  | 61.15 |  |  |  | SubTotal |  | 14.14
HANDLING/ ELEC.DOC. | 090.06.40 | Log Transmittal of Design Schematic & Product Type Template Documents | [5 empty] | HANDLING/ ELEC.DOC. | 090.06.40 | Log Transmittal of Design Schematic & Product Type Template Documents
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 17.675 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 17.675 |  |  |  | SubTotal |  | 0
| 090.07 | Receive Design Schematic & Product Type Template | [6 empty] | 090.07 | Receive Design Schematic & Product Type Template
HANDLING/ ELEC.DOC. | 090.08 | Log Receipt of Design Schematic & Product Type Template Documents | [5 empty] | HANDLING/ ELEC.DOC. | 090.08 | Log Receipt of Design Schematic & Product Type Template Documents
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 4.22 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 4.22 |  |  |  | SubTotal |  | 0
VALIDATING/ COBie | 090.09 | Validate Design Schematic Space & Product Type Template Documents | [5 empty] | VALIDATING/ COBie | 090.09 | Validate Design Schematic Space & Product Type Template Documents
|  | 3.696 | Avg Time to Review Design Schematic Drawings for conformance to Space and Product Program | [6 empty] | 0.3696 | Avg Time to Review Design Schematic Drawings for conformance to Space and Product Program
|  | 62.2 | Owners Rep. Rate ($ / hour) |  |  | 229.8912 |  |  |  | 62.2 | Owners Rep. Rate ($ / hour) | 22.9891
|  |  | SubTotal |  |  |  | 229.8912 |  |  |  | SubTotal |  | 22.9891
HANDLING/ ELEC.DOC. | 090.10.20 | Send Comments to Design Team | [5 empty] | HANDLING/ ELEC.DOC. | 090.10.20 | Send Comments to Design Team
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 8.44 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | Mailing Cost |  |  | 16.5 |  |  |  |  | Mailing Cost | 0
|  |  | SubTotal |  |  |  | 24.94 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 090.10.30 | Log Transmittal of Comments | [5 empty] | HANDLING/ ELEC.DOC. | 090.10.30 | Log Transmittal of Comments
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 4.22 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 4.22 |  |  |  | SubTotal |  | 0
| 090.11 | Receive Review Comments | [6 empty] | 090.11 | Receive Review Comments
HANDLING/ ELEC.DOC. | 090.12 | Log Receipt of Comments | [5 empty] | HANDLING/ ELEC.DOC. | 090.12 | Log Receipt of Comments
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 17.675 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 17.675 |  |  |  | SubTotal |  | 0
RECREATING/ COBie | 090.13 | Make Corrections (Architect and/or Consultants) | [5 empty] | RECREATING/ COBie | 090.13 | Make Corrections (Architect and/or Consultants)
|  | 2.2784 | Avg. Time spent making corrections due to non-conformance with Space or Product Program | [6 empty] | 0 | Avg. Time spent making corrections due to non-conformance with Space or Product Program
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 109.99 | Licensed Professional Architect Rate ($ / hour) |  |  | 250.5957 |  |  |  | 109.99 | Licensed Professional Architect Rate ($ / hour) | 0
[7 empty] | 250.5957 | [5 empty] | 0
COPYING/ ELEC.DOC. | 090.14 | Copy Revised Design Schematic & Product Type Template Documents | [5 empty] | COPYING/ ELEC.DOC. | 090.14 | Copy Revised Design Schematic & Product Type Template Documents
|  | 44.8 | Avg. Number of Sheets in Design Schematic Drawings | [6 empty] | 44.8 | Avg. Number of Sheets in Design Schematic Drawings
|  | 20 | Avg. Number of Letter Sized Pages in Design Schematic Narrative | [6 empty] | 20 | Avg. Number of Letter Sized Pages in Design Schematic Narrative
|  | 2 | Avg. Number of Letter Sized Pages in a Design Schematic Specification | [6 empty] | 2 | Avg. Number of Letter Sized Pages in a Design Schematic Specification
|  | 6 | Number of Design Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Number of Design Submittal Sets Reqd. (sets / submittal)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 3 | Avg. Per Sheet Copy Cost ($ / sheet) | [6 empty] | 0 | Avg. Per Sheet Copy Cost ($ / sheet)
|  | 0.13911 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 59.0109 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | Copying Cost |  |  | 826.2 |  |  |  |  | Copying Cost | 0
|  |  | SubTotal |  |  |  | 885.2109 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 090.15 | Send Revised Design Schematic & Product Type Template Documents | [5 empty] | HANDLING/ ELEC.DOC. | 090.15 | Send Revised Design Schematic & Product Type Template Documents
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 25.8 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 35.35 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | Mailing Cost |  |  | 25.8 |  |  |  |  | Mailing Cost | 0
|  |  | SubTotal |  |  |  | 61.15 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 090.16 | Log Transmittal of Revised Design Schematic & Product Type Template Documents | [5 empty] | HANDLING/ ELEC.DOC. | 090.16 | Log Transmittal of Revised Design Schematic & Product Type Template Documents
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 17.675 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 17.675 |  |  |  | SubTotal |  | 0
| 090.17 | Receive Revised Design Schematic & Product Type Template Documents | [6 empty] | 090.17 | Receive Revised Design Schematic & Product Type Template Documents
HANDLING/ ELEC.DOC. | 090.18 | Log Receipt of Revised Design Schematic & Product Type Template Documents | [5 empty] | HANDLING/ ELEC.DOC. | 090.18 | Log Receipt of Revised Design Schematic & Product Type Template Documents
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 4.22 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 4.22 |  |  |  | SubTotal |  | 0
VALIDATING/ COBie | 090.19 | Validate Revised Design Schematic Space & Product Type Template Documents | [5 empty] | VALIDATING/ COBie | 090.19 | Validate Revised Design Schematic Space & Product Type Template Documents
|  | 3.696 | Avg Time to Review Design Schematic Drawings for conformance to Space and Product Program | [6 empty] | 0.3696 | Avg Time to Review Design Schematic Drawings for conformance to Space and Product Program
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 62.2 | Owners Rep. Rate ($ / hour) |  |  | 229.8912 |  |  |  | 62.2 | Owners Rep. Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 229.8912 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 090.20 | Send Comments to Design Team | [5 empty] | HANDLING/ ELEC.DOC. | 090.20 | Send Comments to Design Team
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 8.44 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | Mailing Cost |  |  | 16.5 |  |  |  |  | Mailing Cost | 0
|  |  | SubTotal |  |  |  | 24.94 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 090.21 | Log Transmittal of Comments | [5 empty] | HANDLING/ ELEC.DOC. | 090.21 | Log Transmittal of Comments
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 4.22 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 4.22 |  |  |  | SubTotal |  | 0
| 090.22 | Receive Review Comments | [6 empty] | 090.22 | Receive Review Comments
HANDLING/ ELEC.DOC. | 090.23 | Log Receipt of Comments | [5 empty] | HANDLING/ ELEC.DOC. | 090.23 | Log Receipt of Comments
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 17.675 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 17.675 |  |  |  | SubTotal |  | 0
[6 empty] | Current Process Total | 7131.835 |  |  |  |  | Expected Process Total | 687.6756
Note on C47: Naila Crawford: Add - for the production of the specification or some of the assets in the COBie format
Note on L47: Naila Crawford: Add - for the production of the specification or some of the assets in the COBie format
Note on C55: Naila Crawford: add for COBie
Note on L55: Naila Crawford: add for COBie
Note on C106: Naila Crawford: Add back costs
Note on L106: Naila Crawford: Add back costs

## 100_Design_Coordinated
| Process Name | Design Coordinated & Product Type Candidate
| OmniClass Stage | 31-20 20 11 Detailed Design Phase
| OmniClass Role | 34-25 21 00 Architect
| Description | The Architect further develops the approved Design Schematic deliverable documents to produce the Design Coordinated documents. In addition, the building systems are coordinated to eliminate spatial interferences. This is a major coordination submittal before the final delivery package. The Architect performs a QA/QC check before distributing to the Owner's Representative. After receiving the submission, the Owner's Representative reviews and provides comments to the Architect. The Architect and Consultants are then required to update the documents based on the comments. After revisions are made, the Architect resubmits.
Information Attributes
|  |  | Total | Owner | Architect | Contractor
|  | Current process cost: | 21562.1363 | 614.12 | 20808.7964 | 0
|  | Expected process cost: | 3695.3864 | 27.368 | 3668.0184 | 0
|  | Process Cost Difference: | 17866.7499 | 586.752 | 17140.7781 | 0
Process
| Current Process | [7 empty] | Expected Process
| 100.01 | Receive Design Schematic Approval Document from Owner | [6 empty] | 100.01 | Receive Design Schematic Approval Document from Owner
RECREATING/ COBie | 100.02.10 | Produce Design Coordinated Documents | [5 empty] | RECREATING/ COBie | 100.02.10 | Produce Design Coordinated Documents
|  | 11.2 | Avg. Number of Plan Drawings in Design Coordinated Drawings | [6 empty] | 11.2 | Avg. Number of Plan Drawings in Design Coordinated Drawings
|  | 0.08 | Avg QTO Time for Equipment Components (hours / plan drawing) | [6 empty] | 0.008 | Avg QTO Time for Equipment Components (hours / plan drawing)
|  | 0.16 | Avg QTO Time for Spaces in building (hours / plan drawing) | [6 empty] | 0.016 | Avg QTO Time for Spaces in building (hours / plan drawing)
|  | 80% | Percentage of Time Spent by Licensed Professional Architect | [6 empty] | 80% | Percentage of Time Spent by Licensed Professional Architect
|  | 20% | Percentage of Time Spent by Architect Drafter | [6 empty] | 20% | Percentage of Time Spent by Architect Drafter
|  | 109.99 | Licensed Professional Architect Rate ($ / hour) |  |  | 236.5225 |  |  |  | 109.99 | Licensed Professional Architect Rate ($ / hour) | 23.6522
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 38.0083 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 3.8008
|  |  | SubTotal |  |  |  | 274.5308 |  |  |  | SubTotal |  | 27.4531
REFORMATTING/ COBie | 100.02.20 | Produce Detailed Specification / Product Type Templates | [5 empty] | REFORMATTING/ COBie | 100.02.20 | Produce Detailed Specification / Product Type Templates
|  | 43 | Number of Unique Product Types (Types / project) | [6 empty] | 43 | Number of Unique Product Types (Types / project)
|  | 2 | Avg. Time Spent Developing Detailed Equipment (products) Type Template (hours / product) | [6 empty] | 0.6 | Avg. Time Spent Developing Detailed Equipment (products) Type Template (hours / product)
|  | 109.99 | Specifier |  |  | 9459.14 |  |  |  | 109.99 | Specifier | 2837.742
|  |  | SubTotal |  |  |  | 9459.14 |  |  |  | SubTotal |  | 2837.742
SEARCHING/ COBie | 100.03 | Search for Product Type Candidates | [5 empty] | SEARCHING/ COBie | 100.03 | Search for Product Type Candidates
|  | 43 | Number of Unique Product Types (Types / project) | [6 empty] | 43 | Number of Unique Product Types (Types / project)
|  | 1 | Avg. Time Searching for Product Literature for Candidates (Hours/product) | [6 empty] | 0.1 | Avg. Time Searching for Product Literature for Candidates (Hours/product)
|  | 109.99 | Licensed Professional Architect Rate ($ / hour) |  |  | 4729.57 |  |  |  | 109.99 | Licensed Professional Architect Rate ($ / hour) | 472.957
|  |  | SubTotal |  |  |  | 4729.57 |  |  |  | SubTotal |  | 472.957
| 100.04 | Receive Consultant's Design Coordinated Documents | [6 empty] | 100.04 | Receive Consultant's Design Coordinated Documents
| 100.05 | Produce Checkset of Design Coordinated Documents | [6 empty] | 100.05 | Produce Checkset of Design Coordinated Documents
VALIDATING/ COBie | 100.06 | Validate Checkset before Submission through manual QA/QC Process - Space and Equipment | [5 empty] | VALIDATING/ COBie | 100.06 | Validate Checkset before Submission through manual QA/QC Process - Space and Equipment
|  | 28.06 | Avg. Time Spent Evaluating Design Coordinated Drawings against Design Requirements - Space and Equipment | [6 empty] | 2.806 | Avg. Time Spent Evaluating Design Coordinated Drawings against Design Requirements - Space and Equipment
|  | 109.99 | Licensed Professional Architect Rate ($ / hour) |  |  | 3086.3194 |  |  |  | 109.99 | Licensed Professional Architect Rate ($ / hour) | 308.6319
|  |  | SubTotal |  |  |  | 3086.3194 |  |  |  | SubTotal |  | 308.6319
RECREATING/ COBie | 100.07.05 | Make Corrections (Architect and/or Consultants) | [5 empty] | RECREATING/ COBie | 100.07.05 | Make Corrections (Architect and/or Consultants)
|  | 1.2658 | Avg. Time spent making corrections due to non-conformance with Space Program | [6 empty] | 0 | Avg. Time spent making corrections due to non-conformance with Space Program
|  | 109.99 | Licensed Professional Architect Rate ($ / hour) |  |  | 139.2198 |  |  |  | 109.99 | Licensed Professional Architect Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 139.2198 |  |  |  | SubTotal |  | 0
SEARCHING & RECREATING/ COBie | 100.07.10 | Re- Search and Recreate Product Type Candidates and Detailed Specifications based on QA/QC Results | [5 empty] | SEARCHING & RECREATING/ COBie | 100.07.10 | Re- Search and Recreate Product Type Candidates and Detailed Specifications based on QA/QC Results
|  | 15% | Avg. Percent of Errors in Product Type Candidate | [6 empty] | 1.5% | Avg. Percent of Errors in Product Type Candidate
|  | 43 | Number of Unique Product Types (Types / project) | [6 empty] | 43 | Number of Unique Product Types (Types / project)
|  | 1 | Avg. Time Searching for Product Literature for Candidates (Hours/product) | [6 empty] | 0.1 | Avg. Time Searching for Product Literature for Candidates (Hours/product)
|  | 109.99 | Licensed Professional Architect Rate ($ / hour) |  |  | 709.4355 |  |  |  | 109.99 | Licensed Professional Architect Rate ($ / hour) | 7.0944
|  |  | SubTotal |  |  |  | 709.4355 |  |  |  | SubTotal |  | 7.0944
COPYING/ ELEC.DOC. | 100.07.20 | Copy Design Coordinated & Product Type Candidate Documents | [5 empty] | COPYING/ ELEC.DOC. | 100.07.20 | Copy Design Coordinated & Product Type Candidate Documents
|  | 53.3333 | Avg. Number of Sheets in Design Coordinated Drawings | [6 empty] | 53.3333 | Avg. Number of Sheets in Design Coordinated Drawings
|  | 20 | Avg. Number of Letter Sized Pages in a Design Coordinated Narrative | [6 empty] | 20 | Avg. Number of Letter Sized Pages in a Design Coordinated Narrative
|  | 50 | Avg. Number of Letter Sized Pages in a Design Coordinated Specification | [6 empty] | 50 | Avg. Number of Letter Sized Pages in a Design Coordinated Specification
|  | 6 | Number of Design Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Number of Design Submittal Sets Reqd. (sets / submittal)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 3 | Avg. Per Sheet Copy Cost ($ / sheet) | [6 empty] | 0 | Avg. Per Sheet Copy Cost ($ / sheet)
|  | 0.19481 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 82.6404 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | Copying Cost |  |  | 1023 |  |  |  |  | Copying Cost | 0
|  |  | SubTotal |  |  |  | 1105.6404 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 100.07.30 | Send Design Coordinated & Product Type Candidate Documents | [5 empty] | HANDLING/ ELEC.DOC. | 100.07.30 | Send Design Coordinated & Product Type Candidate Documents
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 28.95 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 35.35 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 14.14
|  |  | Mailing Cost |  |  | 28.95 |  |  |  |  | Mailing Cost | 0
|  |  | SubTotal |  |  |  | 64.3 |  |  |  | SubTotal |  | 14.14
HANDLING/ ELEC.DOC. | 100.07.40 | Log Transmittal of Design Coordinated & Product Type Candidate Documents | [5 empty] | HANDLING/ ELEC.DOC. | 100.07.40 | Log Transmittal of Design Coordinated Documents
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 17.675 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 17.675 |  |  |  | SubTotal |  | 0
| 100.08 | Receive Design Coordinated & Product Type Candidate Documents | [6 empty] | 100.08 | Receive Design Coordinated & Product Type Candidate Documents
HANDLING/ ELEC.DOC. | 100.09 | Log Receipt of Design Coordinated & Product Type Candidate Documents | [5 empty] | HANDLING/ ELEC.DOC. | 100.09 | Log Receipt of Design Coordinated & Product Type Candidate Documents
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 4.22 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 4.22 |  |  |  | SubTotal |  | 0
VALIDATING/ COBie | 100.1 | Validate Design Coordinated Space & Product Type Candidate Documents | [5 empty] | VALIDATING/ COBie | 100.1 | Validate Design Coordinated Space & Product Type Candidate Documents
|  | 4.4 | Avg. Time to Review Design Coordinated Drawings for conformance to Space and Product Program | [6 empty] | 0.44 | Avg Time to Review Design Coordinated Drawings for conformance to Space and Product Program
|  | 62.2 | Owners Rep. Rate ($ / hour) |  |  | 273.68 |  |  |  | 62.2 | Owners Rep. Rate ($ / hour) | 27.368
|  |  | SubTotal |  |  |  | 273.68 |  |  |  | SubTotal |  | 27.368
HANDLING/ ELEC.DOC. | 100.11.20 | Send Comments to Design Team | [5 empty] | HANDLING/ ELEC.DOC. | 100.11.20 | Send Comments to Design Team
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 8.44 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | Mailing Costs |  |  | 16.5 |  |  |  |  | Mailing Costs | 0
|  |  | SubTotal |  |  |  | 24.94 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 100.11.30 | Log Transmittal of Comments | [5 empty] | HANDLING/ ELEC.DOC. | 100.11.30 | Log Transmittal of Comments
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 4.22 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 4.22 |  |  |  | SubTotal |  | 0
| 100.12 | Receive Review Comments | [6 empty] | 100.12 | Receive Review Comments
HANDLING/ ELEC.DOC. | 100.13 | Log Receipt of Comments | [5 empty] | HANDLING/ ELEC.DOC. | 100.13 | Log Receipt of Comments
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 17.675 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 17.675 |  |  |  | SubTotal |  | 0
RECREATING/ COBie | 100.14 | Make Corrections (Architect and/or Consultants) | [5 empty] | RECREATING/ COBie | 100.14 | Make Corrections (Architect and/or Consultants)
|  | 1.2658 | Avg. Time spent making corrections due to non-conformance with Space Program | [6 empty] | 0 | Avg. Time spent making corrections due to non-conformance with Space Program
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 109.99 | Licensed Professional Architect Rate ($ / hour) |  |  | 139.2198 |  |  |  | 109.99 | Licensed Professional Architect Rate ($ / hour) | 0
[7 empty] | 139.2198 | [5 empty] | 0
COPYING/ ELEC.DOC. | 100.15 | Copy Revised Design Coordinated & Product Type Candidate Documents | [5 empty] | COPYING/ ELEC.DOC. | 100.15 | Copy Revised Design Coordinated & Product Type Candidate Documents
|  | 53.3333 | Avg. Number of Sheets in Design Coordinated Drawings | [6 empty] | 53.3333 | Avg. Number of Sheets in Design Coordinated Drawings
|  | 20 | Avg. Number of Letter Sized Pages in a Design Coordinated Narrative | [6 empty] | 20 | Avg. Number of Letter Sized Pages in a Design Coordinated Narrative
|  | 50 | Avg. Number of Letter Sized Pages in a Design Coordinated Specification | [6 empty] | 50 | Avg. Number of Letter Sized Pages in a Design Coordinated Specification
|  | 6 | Number of Design Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Number of Design Submittal Sets Reqd. (sets / submittal)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 3 | Avg. Per Sheet Copy Cost ($ / sheet) | [6 empty] | 0 | Avg. Per Sheet Copy Cost ($ / sheet)
|  | 0.19481 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 82.6404 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | Copying Cost |  |  | 1023 |  |  |  |  | Copying Cost | 0
|  |  | SubTotal |  |  |  | 1105.6404 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 100.16 | Send Revised Design Coordinated & Product Type Candidate Documents | [5 empty] | HANDLING/ ELEC.DOC. | 100.16 | Send Revised Design Coordinated & Product Type Candidate Documents
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 28.95 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 35.35 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | Mailing Cost |  |  | 28.95 |  |  |  |  | Mailing Cost | 0
|  |  | SubTotal |  |  |  | 64.3 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 100.17 | Log Transmittal of Revised Design Coordinated & Product Type Candidate Documents | [5 empty] | HANDLING/ ELEC.DOC. | 100.17 | Log Transmittal of Revised Design Coordinated & Product Type Candidate Documents
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 17.675 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 17.675 |  |  |  | SubTotal |  | 0
| 100.18 | Receive Design Coordinated & Product Type Candidate Documents | [6 empty] | 100.18 | Receive Design Coordinated & Product Type Candidate Documents
HANDLING/ ELEC.DOC. | 100.19 | Log Receipt of Revised Design Coordinated & Product Type Candidate Documents | [5 empty] | HANDLING/ ELEC.DOC. | 100.19 | Log Receipt of Revised Design Coordinated & Product Type Candidate Documents
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 4.22 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 4.22 |  |  |  | SubTotal |  | 0
VALIDATING/ COBie | 100.20 | Validate Revised Design Coordinated Space & Product Type Candidate Documents | [5 empty] | VALIDATING/ COBie | 100.20 | Validate Revised Design Coordinated Space & Product Type Candidate Documents
|  | 4.4 | Avg Time to Review Design Coordinated Drawings for conformance to Space and Product Program | [6 empty] | 0.44 | Avg Time to Review Design Coordinated Drawings for conformance to Space and Product Program
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 62.2 | Owners Rep. Rate ($ / hour) |  |  | 273.68 |  |  |  | 62.2 | Owners Rep. Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 273.68 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 100.21 | Send Comments to Design Team | [5 empty] | HANDLING/ ELEC.DOC. | 100.21 | Send Comments to Design Team
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 8.44 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | Mailing Cost |  |  | 16.5 |  |  |  |  | Mailing Cost | 0
|  |  | SubTotal |  |  |  | 24.94 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 100.22 | Log Transmittal of Comments | [5 empty] | HANDLING/ ELEC.DOC. | 100.22 | Log Transmittal of Comments
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 4.22 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 4.22 |  |  |  | SubTotal |  | 0
| 100.23 | Receive Review Comments | [6 empty] | 100.23 | Receive Review Comments
HANDLING/ ELEC.DOC. | 100.24 | Log Receipt of Comments | [5 empty] | HANDLING/ ELEC.DOC. | 100.24 | Log Receipt of Comments
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 1 | Avg. Number of Re-Submit Cycles | [6 empty] | 0 | Avg. Number of Re-Submit Cycles
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 17.675 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 17.675 |  |  |  | SubTotal |  | 0
[6 empty] | Current Process Total | 21562.1363 |  |  |  |  | Expected Process Total | 3695.3864
Note on C63: Naila Crawford: add for COBie
Note on L63: Naila Crawford: add for COBie

## 110_Design_Final
| Process Name | Design Final & Product Type Template
| OmniClass Stage | 31-20 20 24 Product Selection Phase
31-20 20 27 Material Selection Phase
31-20 20 31 Equipment Selection Phase
| OmniClass Role | 34-25 41 00 Specifier
| Description | The Design Final package is the final set of contract documents ready for bid solicitation by the Government. This final design deliverable does not require another review by the Owner's Representative.
Information Attributes
|  |  | Total | Owner | Architect | Contractor
|  | Current process cost: | 9237.5153 | 4.22 | 9177.6073 | 0
|  | Expected process cost: | 818.25 | 0 | 818.25 | 0
|  | Process Cost Difference: | 8419.2653 | 4.22 | 8359.3574 | 0
Process
| Current Process | [7 empty] | Expected Process
| 110.01 | Receive Design Coordinated Documents Approval from Owner | [6 empty] | 110.01 | Receive Design Coordinated Documents Approval from Owner
RECREATING/ COBie | 110.02.10 | Produce Design Final Documents | [5 empty] | RECREATING/ COBie | 110.02.10 | Produce Design Final Documents
|  | 11.2 | Avg. Number of Plan Drawings in Design Final Drawings | [6 empty] | 11.2 | Avg. Number of Plan Drawings in Design Final Drawings
|  | 0.08 | Avg QTO Time for Equipment Components (hours / plan drawing) | [6 empty] | 0.008 | Avg QTO Time for Equipment Components (hours / plan drawing)
|  | 0.16 | Avg QTO Time for Spaces in building (hours / plan drawing) | [6 empty] | 0.016 | Avg QTO Time for Spaces in building (hours / plan drawing)
|  | 90% | Percentage of Time Spent by Licensed Professional Architect | [6 empty] | 90% | Percentage of Time Spent by Licensed Professional Architect
|  | 10% | Percentage of Time Spent by Architect Drafter | [6 empty] | 10% | Percentage of Time Spent by Architect Drafter
|  | 109.99 | Licensed Professional Architect Rate ($ / hour) |  |  | 266.0878 |  |  |  | 109.99 | Licensed Professional Architect Rate ($ / hour) |  | 26.6088
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 19.0042 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) |  | 1.9004
|  |  | SubTotal |  |  |  | 285.092 |  |  |  | SubTotal |  |  | 28.5092
REFORMATTING/ COBie | 110.02.20 | Produce Detailed Specification / Product Type Candidates | [5 empty] | REFORMATTING/ COBie | 110.02.20 | Produce Detailed Specification / Product Type Candidates
|  | 43 | Number of Unique Product Types (Types / project) | [6 empty] | 43 | Number of Unique Product Types (Types / project)
|  | 1 | Avg. Time Spent Developing Detailed Equipment (products) Type Candidate (hours / product) | [6 empty] | 0.1 | Avg. Time Spent Developing Detailed Equipment (products) Type Candidate (hours / product)
|  | 109.99 | Specifier |  |  | 4729.57 |  |  |  | 109.99 | Specifier |  | 472.957
|  |  | SubTotal |  |  |  | 4729.57 |  |  |  | SubTotal |  |  | 472.957
| 110.03 | Receive Consultant's Design Final Documents | [6 empty] | 110.03 | Receive Consultant's Design Final Documents
| 110.04 | Produce Check Set of Design Final Documents | [6 empty] | 110.04 | Produce Check Set of Design Final Documents
VALIDATING/ COBie | 110.05 | Validate Checkset before Submission through manual QA/QC Process - Space and Equipment | [5 empty] | VALIDATING/ COBie | 110.05 | Validate Checkset before Submission through manual QA/QC Process - Space and Equipment
|  | 26.23 | Avg. Time Spent Evaluating Design Final Drawings against Design Requirements - Space and Equipment | [6 empty] | 2.623 | Avg. Time Spent Evaluating Design Final Drawings against Design Requirements - Space and Equipment
|  | 109.99 | Licensed Professional Architect Rate ($ / hour) |  |  | 2885.0377 |  |  |  | 109.99 | Licensed Professional Architect Rate ($ / hour) |  | 288.5038
|  |  | SubTotal |  |  |  | 2885.0377 |  |  |  | SubTotal |  |  | 288.5038
RECREATING/ COBie | 110.06.10 | Make Corrections (Architect and/or Consultants) | [5 empty] | RECREATING/ COBie | 110.06.10 | Make Corrections (Architect and/or Consultants)
|  | 0.5063 | Avg. Time spent making corrections due to non-conformance with Space Program | [6 empty] | 0 | Avg. Time spent making corrections due to non-conformance with Space Program
|  | 109.99 | Licensed Professional Architect Rate ($ / hour) |  |  | 55.6879 |  |  |  | 109.99 | Licensed Professional Architect Rate ($ / hour) |  |  | 0
|  |  | SubTotal |  |  |  | 55.6879 |  |  |  |  | SubTotal |  |  | 0
COPYING/ ELEC.DOC. | 110.06.20 | Copy Design Final Documents | [5 empty] | COPYING/ ELEC.DOC. | 110.06.20 | Copy Design Final Documents
|  | 56 | Avg. Number of Sheets in Design Final Drawings | [6 empty] | 56 | Avg. Number of Sheets in Design Final Drawings
|  | 20 | Avg. Number of Letter Sized 'Pages in Design Final Narrative | [6 empty] | 20 | Avg. Number of Letter Sized 'Pages in Design Final Narrative
|  | 50 | Avg. Number of Letter Sized Pages in Design Final Specification | [6 empty] | 50 | Avg. Number of Letter Sized Pages in Design Final Specification
|  | 6 | Number of Design Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Number of Design Submittal Sets Reqd. (sets / submittal)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 3 | Avg. Per Sheet Copy Cost ($ / sheet) | [6 empty] | 0 | Avg. Per Sheet Copy Cost ($ / sheet)
|  | 0.20222 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 85.7827 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | Copying Cost |  |  | 1071 |  |  |  |  | Copying Cost |  | 0
|  |  | SubTotal |  |  |  | 1156.7827 |  |  |  | SubTotal |  |  | 0
HANDLING/ ELEC.DOC. | 110.06.30 | Send Design Final Documents | [5 empty] | HANDLING/ ELEC.DOC. | 110.06.30 | Send Design Final Documents
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 32.75 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 1 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.4 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 70.7 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) |  | 28.28
|  |  | Mailing Cost |  |  | 32.75 |  |  |  |  | Mailing Cost |  | 0
|  |  | SubTotal |  |  |  | 103.45 |  |  |  | SubTotal |  |  | 28.28
HANDLING/ ELEC.DOC. | 110.06.40 | Log Transmittal of Design Final Documents | [5 empty] | HANDLING/ ELEC.DOC. | 110.06.40 | Log Transmittal of Design Final Documents
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 17.675 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 17.675 |  |  |  | SubTotal |  |  | 0
| 110.07 | Receive Design Final and Product Type Candidate Documents | [6 empty] | 110.07 | Receive Design Final and Product Type Candidate Documents
HANDLING/ ELEC.DOC. | 110.08 | Log Receipt of Design Final Documents for Bidding Process | [5 empty] | HANDLING/ ELEC.DOC. | 110.08 | Log Receipt of Design Final Documents for Bidding Process
|  | 1 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 1 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 4.22 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 4.22 |  |  |  | SubTotal |  |  | 0
| 110.09 | Produce Design Final Documents for Bidding Process | [6 empty] | 110.09 | Produce Design Final Documents for Bidding Process
[6 empty] | Current Process Total | 9237.5153 | [5 empty] | Expected Process Total | 818.25
Note on C56: Naila Crawford: add for COBie
Note on L56: Naila Crawford: add for COBie

## 120_Request_For_Proposal
| Process Name | Request For Proposal
| OmniClass Stage | 31-20 20 24 Product Selection Phase
31-20 20 27 Material Selection Phase
31-20 20 31 Equipment Selection Phase
| OmniClass Role | 34-25 41 00 Specifier
| Description | Once the design is complete, the Owner packages the Design Final Documents information together with the owner-supplied information (e.g., contractual terms) and creates a Request for Proposals (RFP). This becomes the official bid set.
Information Attributes
|  |  | Total | Owner | Architect | Contractor
|  | Current process cost: | 414.796 | 414.796 | 0 | 0
|  | Expected process cost: | 25.32 | 25.32 | 0 | 0
|  | Process Cost Difference: | 389.476 | 389.476 | 0 | 0
Process
| Current Process | [7 empty] | Expected Process
HANDLING/ ELEC.DOC. | 120.01 | Receive Information from A/E to Develop Bid Documents | [5 empty] | HANDLING/ ELEC.DOC. | 120.01 | Receive Information from A/E to Develop Bid Documents
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 4.22 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 4.22 |  |  |  | SubTotal |  | 0
| 120.02 | Produce RFP Front Matter | [6 empty] | 120.02 | Produce RFP Front Matter
COPYING/ ELEC.DOC. | 120.03 | Copy Request for Proposal (RFP) Package | [5 empty] | COPYING/ ELEC.DOC. | 120.03 | Copy Request for Proposal (RFP) Package
|  | 10 | Avg. Number of Pages in Front Matter | [6 empty] | 10 | Avg. Number of Pages in Front Matter
|  | 56 | Avg. Number of Sheets in Design Final Drawings | [6 empty] | 56 | Avg. Number of Sheets in Design Final Drawings
|  | 20 | Avg. Number of Letter Sized 'Pages in Design Final Narrative | [6 empty] | 20 | Avg. Number of Letter Sized 'Pages in Design Final Narrative
|  | 50 | Avg. Number of Letter Sized Pages in Design Final Specification | [6 empty] | 50 | Avg. Number of Letter Sized Pages in Design Final Specification
|  | 1 | Avg. Number of Request for Proposal Submittal Sets Reqd. | [6 empty] | 0 | Avg. Number of Request for Proposal Submittal Sets Reqd.
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 3 | Avg. Per Sheet Copy Cost ($ / sheet) | [6 empty] | 0 | Avg. Per Sheet Copy Cost ($ / sheet)
|  | 0.20889 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 3.526 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | Copying Cost |  |  | 180 |  |  |  |  | Copying Cost | 0
|  |  | SubTotal |  |  |  | 183.526 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 120.04 | Send Request for Proposal (RFP) Package | [5 empty] | HANDLING/ ELEC.DOC. | 120.04 | Send Request for Proposal (RFP) Package
|  | 5 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 5 | Avg. Number of Transmittals (Transmittals)
|  | 32.75 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.75 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.3 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 63.3 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 25.32
|  |  | Mailing Cost |  |  | 163.75 |  |  |  |  | Mailing Cost | 0
|  |  | SubTotal |  |  |  | 227.05 |  |  |  | SubTotal |  | 25.32
| 120.05 | Receive RFP Package | [6 empty] | 120.05 | Receive RFP Package
[6 empty] | Current Process Total | 414.796 |  |  |  |  | Expected Process Total | 25.32

## 130_Inquiry_Issue
| Process Name | Inquiry Issue (Clarification)
| OmniClass Stage | 31-20 20 24 Product Selection Phase
31-20 20 27 Material Selection Phase
31-20 20 31 Equipment Selection Phase
| OmniClass Role | 34-25 41 00 Specifier
| Description | Before finalizing a bid proposal, the Contractor typically request additional information or clarification of some bid documents.
Information Attributes
|  |  | Total | Owner | Architect | Contractor
|  | Current process cost: | 1207.9751 | 145.3862 | 244.632 | 817.9569
|  | Expected process cost: | 26.8001 | 3.3625 | 14.4228 | 9.0148
|  | Process Cost Difference: | 1181.1751 | 142.0237 | 230.2092 | 808.9421
Process
| Current Process | [7 empty] | Expected Process
| 130.01 | Acquire/Review Bidding Documents | [6 empty] | 130.01 | Acquire/Review Bidding Documents
| 130.02 | Define Inquiry Issue (Clarification) | [6 empty] | 130.02 | Define Inquiry Issue (Clarification)
| 130.03 | Produce Inquiry Issues | [6 empty] | 130.03 | Produce Inquiry Issues
HANDLING/ ELEC.DOC. | 130.04 | Send Inquiry Issue (Clarification) | [5 empty] | HANDLING/ ELEC.DOC. | 130.04 | Send Inquiry Issue (Clarification)
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.17 | Avg. Time to Prepare Transmittals for Inquiry Issues (hours / transmittal) | [6 empty] | 0.068 | Avg. Time to Prepare Transmittals for Inquiry Issues (hours / transmittal)
|  | 44.19 | Contractor Administrative Rate ($ / hour) |  |  | 22.5369 |  |  |  | 44.19 | Contractor Administrative Rate ($ / hour) | 9.0148
|  |  | Mailing Costs |  |  | 729.135 |  |  |  |  | Mailing Costs | 0
|  |  | SubTotal |  |  |  | 751.6719 |  |  |  | SubTotal |  | 9.0148
HANDLING/ ELEC.DOC. | 130.05 | Log Transmittal of Inquiry Issue (Clarification) | [5 empty] | HANDLING/ ELEC.DOC. | 130.05 | Log Transmittal of Inquiry Issue (Clarification)
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 44.19 | Contractor Administrative Rate ($ / hour) |  |  | 33.1425 |  |  |  | 44.19 | Contractor Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 33.1425 |  |  |  | SubTotal |  | 0
| 130.06 | Receive Inquiry Issue (Clarification) from Contractor | [6 empty] | 130.06 | Receive Inquiry Issue (Clarification) from Contractor
HANDLING/ ELEC.DOC. | 130.07 | Log Receipt of Inquiry Issue (Clarification) | [5 empty] | HANDLING/ ELEC.DOC. | 130.07 | Log Receipt of Inquiry Issue (Clarification)
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 12.66 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 12.66 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 130.08 | Send Inquiry Issue (Clarification) to Architect | [5 empty] | HANDLING/ ELEC.DOC. | 130.08 | Send Inquiry Issue (Clarification) to Architect
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.083 | Avg. Time to Prepare Transmittals for Inquiry Issues (hours / transmittal) | [6 empty] | 0.0332 | Avg. Time to Prepare Transmittals for Inquiry Issues (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 4.2031 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 1.6812
|  |  | Mailing Costs |  |  | 49.5 |  |  |  |  | Mailing Costs | 0
|  |  | SubTotal |  |  |  | 53.7031 |  |  |  | SubTotal |  | 1.6812
HANDLING/ ELEC.DOC. | 130.09 | Log Transmittal of Inquiry Issue (Clarification) | [5 empty] | HANDLING/ ELEC.DOC. | 130.09 | Log Transmittal of Inquiry Issue (Clarification)
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 12.66 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 12.66 |  |  |  | SubTotal |  | 0
| 130.10 | Receive Inquiry Issue (Clarification) | [6 empty] | 130.10 | Receive Inquiry Issue (Clarification)
HANDLING/ ELEC.DOC. | 130.11 | Log Receipt of Inquiry Issue (Clarification) | [5 empty] | HANDLING/ ELEC.DOC. | 130.11 | Log Receipt of Inquiry Issue (Clarification)
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 53.025 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 53.025 |  |  |  | SubTotal |  | 0
| 130.12 | Review Inquiry Issue (Clarification) | [6 empty] | 130.12 | Review Inquiry Issue (Clarification)
HANDLING/ ELEC.DOC. | 130.13 | Send Inquiry Issue (Clarification) Response | [5 empty] | HANDLING/ ELEC.DOC. | 130.13 | Send Inquiry Issue (Clarification) Response
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.17 | Avg. Time to Prepare Transmittals for Inquiry Issues (hours / transmittal) | [6 empty] | 0.068 | Avg. Time to Prepare Transmittals for Inquiry Issues (hours / transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 36.057 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 14.4228
|  |  | Mailing Costs |  |  | 49.5 |  |  |  |  | Mailing Costs | 0
|  |  | SubTotal |  |  |  | 85.557 |  |  |  | SubTotal |  | 14.4228
HANDLING/ ELEC.DOC. | 130.14 | Log Transmittal of Inquiry Issue (Clarification) Response | [5 empty] | HANDLING/ ELEC.DOC. | 130.14 | Log Transmittal of Inquiry Issue (Clarification) Response
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 53.025 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 53.025 |  |  |  | SubTotal |  | 0
| 130.15 | Receive Response to Inquiry Issue (Clarification) from Architect | [6 empty] | 130.15 | Receive Response to Inquiry Issue (Clarification) from Architect
HANDLING/ ELEC.DOC. | 130.16 | Log Receipt of Inquiry Issue (Clarification) Response | [5 empty] | HANDLING/ ELEC.DOC. | 130.16 | Log Receipt of Inquiry Issue (Clarification) Response
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 53.025 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 53.025 |  |  |  | SubTotal |  | 0
| 130.17 | Review Responses to Inquiry Issue (Clarification) | [6 empty] | 130.17 | Review Responses to Inquiry Issue (Clarification)
HANDLING/ ELEC.DOC. | 130.18 | Send Inquiry Issue (Clarification) Response to Contractor | [5 empty] | HANDLING/ ELEC.DOC. | 130.18 | Send Inquiry Issue (Clarification) Response to Contractor
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.083 | Avg. Time to Prepare Transmittals for Inquiry Issues (hours / transmittal) | [6 empty] | 0.0332 | Avg. Time to Prepare Transmittals for Inquiry Issues (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 4.2031 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 1.6812
|  |  | Mailing Costs |  |  | 49.5 |  |  |  |  | Mailing Costs | 0
|  |  | SubTotal |  |  |  | 53.7031 |  |  |  | SubTotal |  | 1.6812
HANDLING/ ELEC.DOC. | 130.19 | Log Transmittal of Inquiry Issue (Clarification) Response | [5 empty] | HANDLING/ ELEC.DOC. | 130.19 | Log Transmittal of Inquiry Issue (Clarification) Response
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 12.66 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 12.66 |  |  |  | SubTotal |  | 0
| 130.20 | Receive Inquiry Issue (Clarification) Response | [6 empty] | 130.20 | Receive Inquiry Issue (Clarification) Response
HANDLING/ ELEC.DOC. | 130.21 | Log Receipt of Inquiry Issue (Clarification) Response | [5 empty] | HANDLING/ ELEC.DOC. | 130.21 | Log Receipt of Inquiry Issue (Clarification) Response
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 44.19 | Contractor Administrative Rate ($ / hour) |  |  | 33.1425 |  |  |  | 44.19 | Contractor Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 33.1425 |  |  |  | SubTotal |  | 0
[6 empty] | Current Process Total | 1207.9751 |  |  |  |  | Expected Process Total | 26.8001

## 140_PreConstruction_Plan
Process Name | Pre-Construction Plan
OmniClass Stage | 31-40 20 27 Submittal Processing Phase
OmniClass Role | 34-35 14 00 Contractor
Description | The Contractor is required to develop a Pre-Construction Plan that describes how the Contractor will provision and manage the construction of the facility. This is sent as a submittal package. Refer to the submittal Package exchange for detailed requirements related to transmitting and handling Pre-Construction Plan Submittals.
Information Attributes
|  | Total | Owner | Architect | Contractor
| Current process cost: | 0 | 0 | 0 | 0
| Expected process cost: | 0 | 0 | 0 | 0
| Process Cost Difference: | 0 | 0 | 0 | 0
Process
Current Process | [6 empty] | Expected Process
140.01 | Review Specification Requirements | [5 empty] | 140.01 | Review Specification Requirements
140.02 | Develop Pre-Construction Plan | [5 empty] | 140.02 | Develop Pre-Construction Plan
140.03 | Submittal Process | [5 empty] | 140.03 | Submittal Process
[5 empty] | Current Process Total | 0 |  |  | Expected Process Total | 0

## 150_Inquiry_Issue_(RFI)
| Process Name | Inquiry issue (RFI)
| OmniClass Stage | 31-40 20 27 Submittal Processing Phase
| OmniClass Role | 34-35 14 00 Contractor
| Description | The Contractor submits a Request for Information (RFI) to ask for clarification during the construction process. These questions may be due to ambiguities or contradictions in the drawings or to site conditions.
Information Attributes
|  |  | Total | Owner | Architect | Contractor
|  | Current process cost: | 4665.2039 | 1475.8912 | 1852.201 | 1337.1117
|  | Expected process cost: | 23.8312 | 1.1748 | 13.942 | 8.7143
|  | Process Cost Difference: | 4641.3727 | 1474.7164 | 1838.259 | 1328.3974
Process
| Current Process | [7 empty] | Expected Process
| 150.01 | Acquire/Review Bidding Documents | [6 empty] | 150.01 | Acquire/Review Bidding Documents
| 150.02 | Define Inquiry Issue (RFI) | [6 empty] | 150.02 | Define Inquiry Issue (RFI)
| 150.03 | Produce Questions | [6 empty] | 150.03 | Produce Questions
HANDLING/ ELEC.DOC. | 150.04 | Send Inquiry Issue (RFI) | [5 empty] | HANDLING/ ELEC.DOC. | 150.04 | Send Inquiry Issue (RFI)
|  | 29 | Avg. Number of RFIs | [6 empty] | 2.9 | Avg. Number of RFIs
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.17 | Avg. Time to Prepare Transmittals for Inquiry Issues (RFI) (hours / transmittal) | [6 empty] | 0.068 | Avg. Time to Prepare Transmittals for Inquiry Issues (RFI) (hours / transmittal)
|  | 44.19 | Contractor Administrative Rate ($ / hour) |  |  | 217.8567 |  |  |  | 44.19 | Contractor Administrative Rate ($ / hour) | 8.7143
|  |  | Mailing Costs |  |  | 478.5 |  |  |  |  | Mailing Costs | 0
|  |  | SubTotal |  |  |  | 696.3567 |  |  |  | SubTotal |  | 8.7143
HANDLING/ ELEC.DOC. | 150.05 | Log Transmittal of Inquiry Issue (RFI) | [5 empty] | HANDLING/ ELEC.DOC. | 150.05 | Log Transmittal of Inquiry Issue (RFI)
|  | 29 | Avg. Number of RFIs | [6 empty] | 2.9 | Avg. Number of RFIs
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 44.19 | Contractor Administrative Rate ($ / hour) |  |  | 320.3775 |  |  |  | 44.19 | Contractor Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 320.3775 |  |  |  | SubTotal |  | 0
| 150.06 | Receive Inquiry Issue (RFI) from Contractor | [6 empty] | 150.06 | Receive Inquiry Issue (RFI) from Contractor
HANDLING/ ELEC.DOC. | 150.07 | Log Receipt of Inquiry Issue (RFI) | [5 empty] | HANDLING/ ELEC.DOC. | 150.07 | Log Receipt of Inquiry Issue (RFI)
|  | 29 | Avg. Number of RFIs | [6 empty] | 2.9 | Avg. Number of RFIs
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 122.38 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 122.38 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 150.08 | Send Inquiry Issue (RFI) to Architect | [5 empty] | HANDLING/ ELEC.DOC. | 150.08 | Send Inquiry Issue (RFI) to Architect
|  | 29 | Avg. Number of RFIs | [6 empty] | 2.9 | Avg. Number of RFIs
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.03 | Avg. Time to Prepare Transmittals for Inquiry Issues (RFI) (hours / transmittal) | [6 empty] | 0.012 | Avg. Time to Prepare Transmittals for Inquiry Issues (RFI) (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 14.6856 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0.58742
|  |  | Mailing Costs |  |  | 478.5 |  |  |  |  | Mailing Costs | 0
|  |  | SubTotal |  |  |  | 493.1856 |  |  |  | SubTotal |  | 0.58742
HANDLING/ ELEC.DOC. | 150.09 | Log Transmittal of Inquiry Issue (RFI) | [5 empty] | HANDLING/ ELEC.DOC. | 150.09 | Log Transmittal of Inquiry Issue (RFI)
|  | 29 | Avg. Number of RFIs | [6 empty] | 2.9 | Avg. Number of RFIs
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 122.38 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 122.38 |  |  |  | SubTotal |  | 0
| 150.10 | Receive Inquiry Issue (RFI) | [6 empty] | 150.10 | Receive Inquiry Issue (RFI)
HANDLING/ ELEC.DOC. | 150.11 | Log Receipt of Inquiry Issue (RFI) | [5 empty] | HANDLING/ ELEC.DOC. | 150.11 | Log Receipt of Inquiry Issue (RFI)
|  | 29 | Avg. Number of RFIs | [6 empty] | 2.9 | Avg. Number of RFIs
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 512.575 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 512.575 |  |  |  | SubTotal |  | 0
| 150.12 | Review Inquiry Issue (RFI) | [6 empty] | 150.12 | Review Inquiry Issue (RFI)
HANDLING/ ELEC.DOC. | 150.13 | Send Inquiry Issue (RFI) Response | [5 empty] | HANDLING/ ELEC.DOC. | 150.13 | Send Inquiry Issue (RFI) Response
|  | 29 | Avg. Number of RFIs | [6 empty] | 2.9 | Avg. Number of RFIs
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.17 | Avg. Time to Prepare Transmittals for Inquiry Issues (RFI) (hours / transmittal) | [6 empty] | 0.068 | Avg. Time to Prepare Transmittals for Inquiry Issues (RFI) (hours / transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 348.551 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 13.942
|  |  | Mailing Costs |  |  | 478.5 |  |  |  |  | Mailing Costs | 0
|  |  | SubTotal |  |  |  | 827.051 |  |  |  | SubTotal |  | 13.942
HANDLING/ ELEC.DOC. | 150.14 | Log Transmittal of Inquiry Issue (RFI) Response | [5 empty] | HANDLING/ ELEC.DOC. | 150.14 | Log Transmittal of Inquiry Issue (RFI) Response
|  | 29 | Avg. Number of RFIs | [6 empty] | 2.9 | Avg. Number of RFIs
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 512.575 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 512.575 |  |  |  | SubTotal |  | 0
| 150.15 | Receive Response to Inquiry Issue (RFI) from Architect | [6 empty] | 150.15 | Receive Response to Inquiry Issue (RFI) from Architect
HANDLING/ ELEC.DOC. | 150.16 | Log Receipt of Response of Inquiry Issue (RFI) | [5 empty] | HANDLING/ ELEC.DOC. | 150.16 | Log Receipt of Response of Inquiry Issue (RFI)
|  | 29 | Avg. Number of RFIs | [6 empty] | 2.9 | Avg. Number of RFIs
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 122.38 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 122.38 |  |  |  | SubTotal |  | 0
| 150.17 | Review Responses to Inquiry Issue (RFI) | [6 empty] | 150.17 | Review Responses to Inquiry Issue (RFI)
HANDLING/ ELEC.DOC. | 150.18 | Send Inquiry Issue (RFI) Response to Contractor | [5 empty] | HANDLING/ ELEC.DOC. | 150.18 | Send Inquiry Issue (RFI) Response to Contractor
|  | 29 | Avg. Number of RFIs | [6 empty] | 2.9 | Avg. Number of RFIs
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.03 | Avg. Time to Prepare Transmittals for Inquiry Issues (RFI) (hours / transmittal) | [6 empty] | 0.012 | Avg. Time to Prepare Transmittals for Inquiry Issues (RFI) (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 14.6856 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0.58742
|  |  | Mailing Costs |  |  | 478.5 |  |  |  |  | Mailing Costs | 0
|  |  | SubTotal |  |  |  | 493.1856 |  |  |  | SubTotal |  | 0.58742
HANDLING/ ELEC.DOC. | 150.19 | Log Transmittal of Inquiry Issue (RFI) Response | [5 empty] | HANDLING/ ELEC.DOC. | 150.19 | Log Transmittal of Inquiry Issue (RFI) Response
|  | 29 | Avg. Number of RFIs | [6 empty] | 2.9 | Avg. Number of RFIs
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 122.38 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 122.38 |  |  |  | SubTotal |  | 0
| 150.20 | Receive Inquiry Issue (RFI) from Owner | [6 empty] | 150.20 | Receive Inquiry Issue (RFI) from Owner
HANDLING/ ELEC.DOC. | [7 empty] | HANDLING/ ELEC.DOC.
| 150.21 | Log Receipt of Inquiry Issue (RFI) Response | [6 empty] | 150.21 | Log Receipt of Inquiry Issue (RFI) Response
|  | 29 | Avg. Number of RFIs | [6 empty] | 2.9 | Avg. Number of RFIs
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 44.19 | Contractor Administrative Rate ($ / hour) |  |  | 320.3775 |  |  |  | 44.19 | Contractor Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 320.3775 |  |  |  | SubTotal |  | 0
[6 empty] | Current Process Total | 4665.2039 |  |  |  |  | Expected Process Total | 23.8312

## 160Product Type_Selection
Process Name | Product Type Selection
OmniClass Stage | 31-40 20 27 Submittal Processing Phase
OmniClass Role | 34-35 14 00 Contractor
Description | The Contractor and Sub-Contractors gather information for products identified in the Design Final documents and prepare submittals. Refer to the Submittal Package exchange for detailed requirements related to transmitting and handling Product Type Selection submittals.
Information Attributes
|  | Total | Owner | Architect | Contractor
| Current process cost: | 0 | 0 | 0 | 0
| Expected process cost: | 0 | 0 | 0 | 0
| Process Cost Difference: | 0 | 0 | 0 | 0
Process
Current Process | [5 empty] | Expected Process
160.01 | Review Contract Documents |  |  |  |  | 160.01 | Review Contract Documents
160.02 | Validate Submittal Information |  |  |  |  | 160.02 | Validate Submittal Information
160.03 | Submittal Process |  |  |  |  | 160.03 | Submittal Process
|  |  |  | Current Process Total | 0 |  |  | Expected Process Total | 0

## 170_System_Layout
Process Name | System Layout
OmniClass Stage | 31-40 20 27 Submittal Processing Phase
OmniClass Role | 34-35 14 00 Contractor
Description | The Contractor and Sub-Contractors review information for products identified in the Design Final documents and prepare shop drawings. Refer to Submittal Package exchange for detailed requirements related to transmitting and handling System Layout submittals.
Information Attributes
|  | Total | Owner | Architect | Contractor
| Current process cost: | 0 | 0 | 0 | 0
| Expected process cost: | 0 | 0 | 0 | 0
| Process Cost Difference: | 0 | 0 | 0 | 0
Process
Current Process | [6 empty] | Expected Process
170.01 | Review Contract Drawings | [5 empty] | 170.01 | Review Contract Drawings
170.02 | Layout and Route Building System | [5 empty] | 170.02 | Layout and Route Building System
170.03 | Overlay System Layouts (Shop Drawings) | [5 empty] | 170.03 | Overlay System Layouts (Shop Drawings)
170.04 | Identify System Interferences | [5 empty] | 170.04 | Identify System Interferences
170.05 | Resolve System Interferences | [5 empty] | 170.05 | Resolve System Interferences
170.06 | Update System Layouts (Shop Drawings) | [5 empty] | 170.06 | Update System Layouts (Shop Drawings)
170.07.10 | Submittal Process | [5 empty] | 170.07.10 | Submittal Process
[5 empty] | Current Process Total | 0 |  |  | Expected Process Total | 0

## 180_Submittal_Package
| Process Name | Submittal Package
| OmniClass Stage | 31-40 20 27 Submittal Processing Phase
| OmniClass Role | 34-35 14 00 Contractor
| Description | The Contractor organizes the required submittal information and creates Submittal Packages to be reviewed by the Architect and/or Owner's Representative.
Information Attributes
|  |  | Total | Owner | Architect | Contractor
|  | Current process cost: | 12181.9345 | 1001.4 | 530.25 | 10650.2845
|  | Expected process cost: | 605.3547 | 101.28 | 0 | 504.0747
|  | Process Cost Difference: | 11576.5799 | 900.12 | 530.25 | 10146.2099
Process
| Current Process | [7 empty] | Expected Process
| 180.01 | Identify Submittal Dates on Submittal Register | [6 empty] | 180.01 | Identify Submittal Dates on Submittal Register
| 180.02.10 | Receive Submittal Information from Sub-Contractors and Vendors | [6 empty] | 180.02.10 | Receive Submittal Information from Sub-Contractors and Vendors
HANDLING/ ELEC.DOC. | 180.02.15 | Log Receipt of Submittal Package from Sub-Contractors and Vendors | [5 empty] | HANDLING/ ELEC.DOC. | 180.02.15 | Log Receipt of Submittal Package from Sub-Contractors and Vendors
|  | 30 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 30 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 44.19 | Contractor Administrative Rate ($ / hour) |  |  | 331.425 |  |  |  | 44.19 | Contractor Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 331.425 |  |  |  | SubTotal |  | 0
REFORMATTING/ COBie | 180.02.20 | Produce Submittal Information | [5 empty] | REFORMATTING/ COBie | 180.02.20 | Produce Submittal Information
|  | 43 | Number of Unique Product Types (Types / project) | [6 empty] | 43 | Number of Unique Product Types (Types / project)
|  | 0.17 | Avg. Time Spent Organizing Equipment (product) Type information (hours / submittal item) | [6 empty] | 0.068 | Avg. Time Spent Organizing Equipment (product) Type information (hours / submittal item)
|  | 70.53 | Assistant (Construction) Project Manager Rate ($ / hour) |  |  | 515.5743 |  |  |  | 70.53 | Assistant (Construction) Project Manager Rate ($ / hour) | 206.2297
|  |  | SubTotal |  |  |  | 515.5743 |  |  |  | SubTotal |  | 206.2297
VALIDATING/ COBie | 180.03 | Validate Submittal Information against Contract Documents | [5 empty] | VALIDATING/ COBie | 180.03 | Validate Submittal Information against Contract Documents
|  | 43 | Number of Unique Product Types (Types / project) | [6 empty] | 43 | Number of Unique Product Types (Types / project)
|  | 0.5 | Avg. Time Spent Evaluating Equipment (product) Type Submittal Items against Contract Documents (hours / submittal item) | [6 empty] | 0.05 | Avg. Time Spent Evaluating Equipment (product) Type Submittal Items against Contract Documents (hours / submittal item)
|  | 20% | Percentage of Submittals Items rejected | [6 empty] | 20% | Percentage of Submittals Items rejected
|  | 10% | Percentage of Time Spent by Construction Project Manager | [6 empty] | 10% | Percentage of Time Spent by Construction Project Manager
|  | 90% | Percentage of Time Spent by Assistant (Construction) Project Manager | [6 empty] | 90% | Percentage of Time Spent by Assistant (Construction) Project Manager
|  | 125.81 | Construction Project Manager Rate ($ / hour) |  |  | 54.0983 |  |  |  | 125.81 | Construction Project Manager Rate ($ / hour) | 5.4098
|  | 70.53 | Assistant (Construction) Project Manager Rate ($ / hour) |  |  | 272.9511 |  |  |  | 70.53 | Assistant (Construction) Project Manager Rate ($ / hour) | 27.2951
|  |  | SubTotal |  |  |  | 327.0494 |  |  |  | SubTotal |  | 32.7049
| 180.04 | Produce Submittal Package | [6 empty] | 180.04 | Produce Submittal Package
COPYING/ ELEC.DOC. | 180.05 | Copy Submittal Package | [5 empty] | COPYING/ ELEC.DOC. | 180.05 | Copy Submittal Package
|  | 18 | Avg. Number of Submittal Pages in a Submittal Item (pages/submittal item) | [6 empty] | 18 | Avg. Number of Submittal Pages in a Submittal Item (pages/submittal item)
|  | 1 | Avg. Number of Submittal Sheets in a Submittal Item (sheets/submittal item) | [6 empty] | 1 | Avg. Number of Submittal Sheets in a Submittal Item (sheets/submittal item)
|  | 3 | Avg. Number of Submittal Items in a Product Submittal Package (submittal items/submittal package) | [6 empty] | 3 | Avg. Number of Submittal Items in a Product Submittal Package (submittal items/submittal package)
|  | 43 | Number of Unique Product Types (Types / project) | [6 empty] | 43 | Number of Unique Product Types (Types / project)
|  | 6 | Number of Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Number of Submittal Sets Reqd. (sets / submittal)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 3 | Avg. Per Sheet Copy Cost ($ / sheet) | [6 empty] | 0 | Avg. Per Sheet Copy Cost ($ / sheet)
|  | 0.014778 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 44.19 | Contractor Administrative Rate ($ / hour) |  |  | 3.9182 |  |  |  | 44.19 | Contractor Administrative Rate ($ / hour) | 0
|  |  | Copying Cost |  |  | 4411.8 |  |  |  |  | Copying Cost | 0
|  |  | SubTotal |  |  |  | 4415.7182 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 180.06 | Stamp Submittal Package | [5 empty] | HANDLING/ ELEC.DOC. | 180.06 | Stamp Submittal Package
|  | 18 | Avg. Number of Submittal Pages in a Submittal Item (pages/submittal item) | [6 empty] | 18 | Avg. Number of Submittal Pages in a Submittal Item (pages/submittal item)
|  | 1 | Avg. Number of Submittal Sheets in a Submittal Item (sheets/submittal item) | [6 empty] | 1 | Avg. Number of Submittal Sheets in a Submittal Item (sheets/submittal item)
|  | 3 | Avg. Number of Submittal Items in a Product Submittal Package (submittal items/submittal package) | [6 empty] | 3 | Avg. Number of Submittal Items in a Product Submittal Package (submittal items/submittal package)
|  | 6 | Number of Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Number of Submittal Sets Reqd. (sets / submittal)
|  | 0.083 | Avg. Time to Sign each Page (hours/page) | [6 empty] | 0 | Avg. Time to Sign each Page (hours/page)
|  | 0.083 | Avg. Time to Stamp each Sheet (hours / sheet) | [6 empty] | 0 | Avg. Time to Stamp each Sheet (hours / sheet)
|  | 125.81 | Construction Project Manager Rate ($ / hour) |  |  | 3571.2427 |  |  |  | 125.81 | Construction Project Manager Rate ($ / hour) | 0
|  | 70.53 | Assistant (Construction) Project Manager Rate ($ / hour) |  |  | 2002.0646 |  |  |  | 70.53 | Assistant (Construction) Project Manager Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 3571.2427 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 180.07 | Send Submittal Package | [5 empty] | HANDLING/ ELEC.DOC. | 180.07 | Send Submittal Package
|  | 30 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 30 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 44.19 | Contractor Administrative Rate ($ / hour) |  |  | 662.85 |  |  |  | 44.19 | Contractor Administrative Rate ($ / hour) | 265.14
|  |  | Mailing Costs |  |  | 495 |  |  |  |  | Mailing Costs | 0
|  |  | SubTotal |  |  |  | 1157.85 |  |  |  | SubTotal |  | 265.14
HANDLING/ ELEC.DOC. | 180.08 | Log Transmittal of Submittal Package | [5 empty] | HANDLING/ ELEC.DOC. | 180.08 | Log Transmittal of Submittal Package
|  | 30 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 30 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 44.19 | Contractor Administrative Rate ($ / hour) |  |  | 331.425 |  |  |  | 44.19 | Contractor Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 331.425 |  |  |  | SubTotal |  | 0
| 180.09 | Receive Submittal Package | [6 empty] | 180.09 | Receive Submittal Package
HANDLING/ ELEC.DOC. | 180.10 | Log Receipt of Submittal Package | [5 empty] | HANDLING/ ELEC.DOC. | 180.10 | Log Receipt of Submittal Package
|  | 30 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 30 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 126.6 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 126.6 |  |  |  | SubTotal |  | 0
| 180.11 | Review Submittal Package | [6 empty] | 180.11 | Verify Submittal Package
HANDLING/ ELEC.DOC. | 180.12 | Send Submittal Package to Architect | [5 empty] | HANDLING/ ELEC.DOC. | 180.12 | Send Submittal Package to Architect
|  | 30 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 30 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 253.2 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 101.28
|  |  | Mailing Costs |  |  | 495 |  |  |  |  | Mailing Costs | 0
|  |  | SubTotal |  |  |  | 748.2 |  |  |  | SubTotal |  | 101.28
HANDLING/ ELEC.DOC. | 180.13 | Log Transmittal of Submittal Package | [5 empty] | HANDLING/ ELEC.DOC. | 180.13 | Log Transmittal of Submittal Package
|  | 30 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 30 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 16.88 | Owners Rep. Administrative Rate ($ / hour) |  |  | 126.6 |  |  |  | 16.88 | Owners Rep. Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 126.6 |  |  |  | SubTotal |  | 0
| 180.14 | Receive Submittal Package | [6 empty] | 180.14 | Receive Submittal Package
HANDLING/ ELEC.DOC. | 180.15 | Log Receipt of Submittal Package | [5 empty] | HANDLING/ ELEC.DOC. | 180.15 | Log Receipt of Submittal Package
|  | 30 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 30 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 530.25 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 530.25 |  |  |  | SubTotal |  | 0
| 180.16 | Submittal Issue | [6 empty] | 180.16 | Submittal Issue
[6 empty] | Current Process Total | 12181.9345 |  |  |  |  | Expected Process Total | 605.3547

## 190_Submittal_Issue
| Process Name | Submittal Issue
| OmniClass Stage | 31-40 20 27 Submittal Processing Phase
| OmniClass Role | 34-35 14 00 Contractor
| Description | The Owner's Representative and Architect review the submittals provided by the contractor and provide comments.
Information Attributes
|  |  | Total | Owner | Architect | Contractor
|  | Current process cost: | 60481.562 | 0 | 58704.431 | 1777.131
|  | COBie process cost: | 408.7465 | 0 | 398.1375 | 10.609
|  | Process Cost Difference: | 60072.8155 | 0 | 58306.2935 | 1766.522
| Current Process | [7 empty] | Expected Process
| 190.01 | Examine Submittal Package (Pre-Construction, Product Type Selection, System Layout) | [6 empty] | 190.01 | Examine Submittal Package (Pre-Construction, Product Type Selection, System Layout)
HANDLING/ ELEC.DOC. | 190.02.10 | Send Copies of Submittal Package (Product Type Selection, System Layout) to Sub-Consultants | [5 empty] | HANDLING/ ELEC.DOC. | 190.02.10 | Send Copies of Submittal Package (Product Type Selection, System Layout) to Sub-Consultants
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal | [6 empty] | 0 | Avg. Mailing Cost per Transmittal
|  | 0.083 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.0332 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 17.6043 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) |  | 7.0417
|  |  | Mailing Costs |  |  | 49.5 |  |  |  |  | Mailing Costs |  | 0
|  |  | SubTotal |  |  |  | 67.1043 |  |  |  | SubTotal |  |  | 7.0417
HANDLING/ ELEC.DOC. | 190.02.11 | Log Transmittal of Submittal Package (Product Type Selection, System Layout) | [5 empty] | HANDLING/ ELEC.DOC. | 190.02.11 | Log Transmittal of Submittal Package (Product Type Selection, System Layout)
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 53.025 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 53.025 |  |  |  | SubTotal |  |  | 0
| 190.02.12 | Receive Copies of Sub Consultant's Submittal Mark-ups/Comments | [6 empty] | 190.02.12 | Receive Copies of Sub Consultant's Submittal Mark-ups/Comments
HANDLING/ ELEC.DOC. | 190.02.13 | Log Receipt of Sub Consultant's Submittal Mark-ups/Comments | [5 empty] | HANDLING/ ELEC.DOC. | 190.02.13 | Log Receipt of Sub Consultant's Submittal Mark-ups/Comments
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 53.025 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 53.025 |  |  |  | SubTotal |  |  | 0
| 190.02.14 | Review Sub Consultant's Submittal Mark-ups/Comments | [6 empty] | 190.02.14 | Review Sub Consultant's Submittal Mark-ups/Comments
VALIDATING/ COBie | 190.02.20 | Validate Submittal Package not sent to Sub Consultants | [5 empty] | VALIDATING/ COBie | 190.02.20 | Validate Submittal Package not sent to Sub Consultants
|  | 43 | Number of Unique Product Types (Types / project) | [6 empty] | 43 | Number of Unique Product Types (Types / project)
|  | 1 | Avg. Time Spent Evaluating Product Type Submittal Items against Contract Documents (hours / product type submittal item) | [6 empty] | 0.1 | Avg. Time Spent Evaluating Product Type Submittal Items against Contract Documents (hours / product type submittal item)
|  | 75% | Percentage of Product Submittals reviewed by Licensed Architect | [6 empty] | 75% | Percentage of Product Submittals reviewed by Licensed Architect
|  | 109.99 | Licensed Professional Architect Rate ($ / hour) |  |  | 3547.1775 |  |  |  | 109.99 | Licensed Professional Architect Rate ($ / hour) |  | 354.7177
|  |  | SubTotal |  |  |  | 3547.1775 |  |  |  | SubTotal |  |  | 354.7177
HANDLING/ ELEC.DOC. | 190.02.21 | Mark-up Copies of Submittals with Comments | [5 empty] | HANDLING/ ELEC.DOC. | 190.02.21 | Mark-up Copies of Submittals with Comments
|  | 18 | Avg. Number of Submittal Pages in a Submittal Item (pages/submittal item) | [6 empty] | 18 | Avg. Number of Submittal Pages in a Submittal Item (pages/submittal item)
|  | 1 | Avg. Number of Submittal Sheets in a Submittal Item (sheets/submittal item) | [6 empty] | 1 | Avg. Number of Submittal Sheets in a Submittal Item (sheets/submittal item)
|  | 3 | Avg. Number of Submittal Items in a Product Submittal Package (submittal items/submittal package) | [6 empty] | 3 | Avg. Number of Submittal Items in a Product Submittal Package (submittal items/submittal package)
|  | 43 | Number of Unique Product Types (Types / project) | [6 empty] | 43 | Number of Unique Product Types (Types / project)
|  | 0.033 | Avg. Time Spent Transferring Comments per Page (hours / page) | [6 empty] | 0 | Avg. Time Spent Transferring Comments per Page (hours / page)
|  | 0.083 | Avg. Time Spent Transferring Comments per Sheet (hours / sheet) | [6 empty] | 0 | Avg. Time Spent Transferring Comments per Sheet (hours / sheet)
|  | 6 | Number of Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Number of Submittal Sets Reqd. (sets / submittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 30872.2155 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 30872.2155 |  |  |  | SubTotal |  |  | 0
HANDLING/ ELEC.DOC. | 190.03.10 | Send Copies of Submittal Issues | [5 empty] | HANDLING/ ELEC.DOC. | 190.03.10 | Send Copies of Submittal Issues
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal | [6 empty] | 0 | Avg. Mailing Cost per Transmittal
|  | 0.083 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.0332 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 17.6043 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) |  | 7.0417
|  |  | Mailing Cost |  |  | 49.5 |  |  |  |  | Mailing Cost |  | 0
|  |  | SubTotal |  |  |  | 67.1043 |  |  |  | SubTotal |  |  | 7.0417
HANDLING/ ELEC.DOC. | 190.03.20 | Log Transmittal of Submittal Issues | [5 empty] | HANDLING/ ELEC.DOC. | 190.03.20 | Log Transmittal of Submittal Issues
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 53.025 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 53.025 |  |  |  | SubTotal |  |  | 0
| 190.04 | Receive Submittal Issue | [6 empty] | 190.04 | Receive Submittal Issue
HANDLING/ ELEC.DOC. | 190.05 | Log Receipt of Submittal Issue | [5 empty] | HANDLING/ ELEC.DOC. | 190.05 | Log Receipt of Submittal Issue
|  | 3 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 3 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 44.19 | Contractor Administrative Rate ($ / hour) |  |  | 33.1425 |  |  |  | 44.19 | Contractor Administrative Rate ($ / hour) |  | 0
|  |  | SubTotal |  |  |  | 33.1425 |  |  |  | SubTotal |  |  | 0
| 190.06 | Review Submittal Package | [6 empty] | 190.06 | Review Submittal Package
[5 empty] | Subtotal (1st Review Total) |  | 34745.8191 |  |  |  |  | Subtotal (1st Review Total) |  | 368.8012
RECREATING/ COBie | 190.06.10 | Recreate Submittal Package (Product Type Selection, System Layout) | [5 empty] | RECREATING/ COBie | 190.06.10 | Recreate Submittal Package (Product Type Selection, System Layout)
|  | 43 | Number of Unique Product Types (Types / project) | [6 empty] | 43 | Number of Unique Product Types (Types / project)
|  | 0.5 | Avg. Time Spent Revising one Product Type Submittal Item (hours / product type submittal item) | [6 empty] | 0.05 | Avg. Time Spent Revising one Product Type Submittal Item (hours / product type submittal item)
|  | 80% | Percentage of Time Spent by Construction Project Manager | [6 empty] | 80% | Percentage of Time Spent by Construction Project Manager
|  | 20% | Percentage of Time Spent by Assistant (Construction) Project Manager | [6 empty] | 20% | Percentage of Time Spent by Assistant (Construction) Project Manager
|  | 125.81 | Construction Project Manager Rate ($ / hour) |  |  | 2163.932 |  |  |  | 125.81 | Construction Project Manager Rate ($ / hour) |  | 216.3932
|  | 70.53 | Assistant (Construction) Project Manager Rate ($ / hour) |  |  | 303.279 |  |  |  | 70.53 | Assistant (Construction) Project Manager Rate ($ / hour) |  | 30.3279
|  |  | SubTotal |  |  | 2467.211 |  |  |  |  | SubTotal |  | 246.7211
| 190.07 | 2nd Review Cycle of Submittal Package (Product Type Selection, System Layout) | [6 empty] | 190.07 | 2nd Review Cycle of Submittal Package (Product Type Selection, System Layout)
|  | 43% | Percentage of Product Submittals rejected on 2nd review | [6 empty] | 4.3% | Percentage of Product Submittals rejected on 2nd review
[5 empty] | Architect's Cost | 15093.6226 | [5 empty] | Architect's Cost | 29.3363
[5 empty] | Contractor's Cost | 1094.0432 | [5 empty] | Contractor's Cost | 10.609
[5 empty] | Subtotal (2nd Review Total) |  | 16187.6658 |  |  |  |  | Subtotal (2nd Review Total) |  | 39.9453
| 190.08 | 3rd Review Cycle of Submittal Package (Product Type Selection, System Layout) | [6 empty] | 190.08 | 3rd Review Cycle of Submittal Package (Product Type Selection, System Layout)
|  | 25% | Percentage of Product Submittals rejected on 3rd review | [6 empty] | 0% | Percentage of Product Submittals rejected on 3rd review
[5 empty] | Architect's Cost | 8898.1319 | [5 empty] | Architect's Cost | 0
[5 empty] | Contractor's Cost | 649.9452 | [5 empty] | Contractor's Cost | 0
[5 empty] | Subtotal (3rd Review Total) |  | 9548.0771 |  |  |  |  | Subtotal (3rd Review Total) |  | 0
| 190.09 | 4th Review Cycle of Submittal Package (Product Type Selection, System Layout) | [6 empty] | 190.09 | 4th Review Cycle of Submittal Package (Product Type Selection, System Layout)
|  | 0% | Percentage of Product Submittals rejected on 4th review | [6 empty] | 0% | Percentage of Product Submittals rejected on 4th review
[5 empty] | Architect's Cost | 0 | [5 empty] | Architect's Cost | 0
[5 empty] | Contractor's Cost | 0 | [5 empty] | Contractor's Cost | 0
[5 empty] | Subtotal (4th Review Total) |  | 0 |  |  |  |  | Subtotal (4th Review Total) |  | 0
[6 empty] | Current Process Total | 60481.562 | [5 empty] | Expected Process Total | 408.7465
[5 empty] | Elec. Doc Current process cost: | [6 empty] | Elec. Doc Expected process cost:
[5 empty] | 2nd review | [6 empty] | 2nd review
[5 empty] | Architect's Cost | 13568.3363 | [5 empty] | Architect's Cost | 14.0834
[5 empty] | Contractor's Cost | 33.1425 | [5 empty] | Contractor's Cost | 0
[5 empty] | 3rd review | [6 empty] | 3rd review
[5 empty] | Architect's Cost | 8011.3375 | [5 empty] | Architect's Cost | 0
[5 empty] | Contractor's Cost | 33.1425 | [5 empty] | Contractor's Cost | 0
[5 empty] | 4th review | [6 empty] | 4th review
[5 empty] | Architect's Cost | 0 | [5 empty] | Architect's Cost | 0
[5 empty] | Contractor's Cost | 0 | [5 empty] | Contractor's Cost | 0
[6 empty] | Architect's Sub Total | 21579.6737 | [5 empty] | Architect's Sub Total | 14.0834
[6 empty] | Contractor's Sub Total | 66.285 | [5 empty] | Contractor's Sub Total | 0
[5 empty] | COBie Current process cost: | [6 empty] | COBie Expected process cost:
[5 empty] | 2nd review | [6 empty] | 2nd review
[5 empty] | Architect's Cost | 1525.2863 | [5 empty] | Architect's Cost | 15.2529
[5 empty] | Contractor's Cost | 1060.9007 | [5 empty] | Contractor's Cost | 10.609
[5 empty] | 3rd review | [6 empty] | 3rd review
[5 empty] | Architect's Cost | 886.7944 | [5 empty] | Architect's Cost | 0
[5 empty] | Contractor's Cost | 616.8027 | [5 empty] | Contractor's Cost | 0
[5 empty] | 4th review | [6 empty] | 4th review
[5 empty] | Architect's Cost | 0 | [5 empty] | Architect's Cost | 0
[5 empty] | Contractor's Cost | 0 | [5 empty] | Contractor's Cost | 0
[6 empty] | Architect's Sub Total | 2412.0807 | [5 empty] | Architect's Sub Total | 15.2529
[6 empty] | Contractor's Sub Total | 1677.7035 | [5 empty] | Contractor's Sub Total | 10.609

## 200_Purchase_Order
Process Name | Purchase Order
OmniClass Stage | 31-40 20 27 Submittal Processing Phase
OmniClass Role | 34-35 14 00 Contractor
Description | The Contractor contacts a Supplier to order equipment and materials. The Supplier then provides a price quote to the Contractor for the equipment and/or materials. The Contractor verifies the specifications of the equipment and/or materials in the quote against approved submittal documentation and then submits a Purchase Order.
Information Attributes
|  | Total | Owner | Architect | Contractor
| Current process cost: | 0 | 0 | 0 | 0
| Expected process cost: | 0 | 0 | 0 | 0
| Process Cost Difference: | 0 | 0 | 0 | 0
Process
Current Process | [5 empty] | Expected Process
200.01 | Contact Supplier |  |  |  |  | 200.01 | Contact Supplier
200.02 | Request Quote and Technical Data |  |  |  |  | 200.02 | Request Quote and Technical Data
200.03 | Receive Quote and Technical Data |  |  |  |  | 200.03 | Receive Quote and Technical Data
200.04 | Submit Technical Data for Approval |  |  |  |  | 200.04 | Submit Technical Data for Approval
200.05 | Receive Approval |  |  |  |  | 200.05 | Receive Approval
200.06 | Issue Purchase Order |  |  |  |  | 200.06 | Issue Purchase Order
200.07 | Send Purchase Order and Approved Product Type Selection to Supplier |  |  |  |  | 200.07 | Send Purchase Order and Approved Product Type Selection to Supplier
|  |  |  | Current Process Total | 0 |  |  | Expected Process Total | 0

## 210_Product_Installation
| Process Name | Product Installation
| OmniClass Stage | 31-40 40 11 17 Installation Phase
| OmniClass Role | 34-35 14 00 Contractor
| Description | The Contractor installs the building equipment, materials, and systems using the design final drawings, approved shop drawings, product data and manufacturer's instructions.
Information Attributes
|  |  | Total | Owner | Architect | Contractor
|  | Current process cost: | 278268.1005 | 0 | 35.35 | 278232.7505
|  | Expected process cost: | 2.9342 | 0 | 0 | 2.9342
|  | Process Cost Difference: | 278265.1663 | 0 | 35.35 | 278229.8163
Process
| Current Process | [7 empty] | Expected Process
| 210.01 | Receive Equipment and Materials | [6 empty] | 210.01 | Receive Equipment and Materials
| 210.02 | Review Purchase Order | [6 empty] | 210.02 | Review Purchase Order
| 210.03.10 | Log Receipt of Equipment and Materials | [6 empty] | 210.03.10 | Log Receipt of Equipment and Materials
| 210.03.11 | Review Manufacturer's Installation Instructions | [6 empty] | 210.03.11 | Review Manufacturer's Installation Instructions
| 210.03.12 | Install Equipment, Materials and Building Systems - Recording Component Data | [6 empty] | 210.03.12 | Install Equipment, Materials and Building Systems - Recording Component Data
REFORMATTING/ COBie | 210.04 | Reformat Product Installation Report | [5 empty] | REFORMATTING/ COBie | 210.04 | Reformat Product Installation Report
|  | 23200 | Number of Tagged Components (components / project) | [6 empty] | 23200 | Number of Tagged Components (components / project)
|  | 0.17 | Avg. Time Spent Re-formatting Product Installation Report in Office (hours/ component) | [6 empty] | 0 | Avg. Time Spent Re-formatting Product Installation Report in Office (hours/ component)
|  | 70.53 | Assistant (Construction) Project Manager Rate ($ / hour) |  |  | 278170.32 |  |  |  | 70.53 | Assistant (Construction) Project Manager Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 278170.32 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 210.05 | Send Product Installation Report to Architect / Owners Rep | [5 empty] | HANDLING/ ELEC.DOC. | 210.05 | Send Product Installation Report to Architect / Owners Rep
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.083 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.0332 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 44.19 | Contractor Administrative Rate ($ / hour) |  |  | 7.3355 |  |  |  | 44.19 | Contractor Administrative Rate ($ / hour) | 2.9342
|  |  | Mailing Cost |  |  | 33 |  |  |  |  | Mailing Cost | 0
|  |  | SubTotal |  |  |  | 40.3355 |  |  |  | SubTotal |  | 2.9342
HANDLING/ ELEC.DOC. | 210.06 | Log Transmittal of Product Installation Report | [5 empty] | HANDLING/ ELEC.DOC. | 210.06 | Log Transmittal of Product Installation Report
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 44.19 | Contractor Administrative Rate ($ / hour) |  |  | 22.095 |  |  |  | 44.19 | Contractor Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 22.095 |  |  |  | SubTotal |  | 0
| 210.07 | Receive Product Installation Report | [6 empty] | 210.07 | Receive Product Installation Report
HANDLING/ ELEC.DOC. | 210.08 | Log Receipt of Product Installation Report | [5 empty] | HANDLING/ ELEC.DOC. | 210.08 | Log Receipt of Product Installation Report
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 35.35 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 35.35 |  |  |  | SubTotal |  | 0
[6 empty] | Current Process Total | 278268.1005 |  |  |  |  | Expected Process Total | 2.9342

## 220_Start-Up
Process Name | Start-Up
OmniClass Stage | 31-40 40 11 17 Installation Phase
OmniClass Role | 34-35 14 00 Contractor
Description | After the Contractor completes the installation process, the equipment/systems must be tested by activating the equipment. This testing must be completed with the Owner's Representative and Manufacturer's representative present.
Information Attributes
|  | Total | Owner | Architect | Contractor
| Current process cost: | 0 | 0 | 0 | 0
| Expected process cost: | 0 | 0 | 0 | 0
| Process Cost Difference: | 0 | 0 | 0 | 0
Process
Current Process | [6 empty] | Expected Process
220.01 | Send Start-Up Test Procedures and Recording Forms to Owner's Rep. | [5 empty] | 220.01 | Send Start-Up Test Procedures and Recording Forms to Owner's Rep.
220.02 | Schedule Start-Up Test with Owner's Rep. | [5 empty] | 220.02 | Schedule Start-Up Test with Owner's Rep.
220.03 | Review Manufacturer's Start-Up/Operation Instructions | [5 empty] | 220.03 | Review Manufacturer's Start-Up/Operation Instructions
220.04 | Conduct Start-Up/Test of Installed Equipment | [5 empty] | 220.04 | Conduct Start-Up/Test of Installed Equipment
220.05 | Record Test Results | [5 empty] | 220.05 | Record Test Results
[5 empty] | Current Process Total | 0 |  |  | Expected Process Total | 0

## 230_Product_Inspection
| Process Name | Product Inspection
| OmniClass Stage | 31-40 40 91 17 Evaluation Phase
| OmniClass Role | 34-35 14 00 Contractor
| Description | When the Contractor has completed installation of equipment or systems, a notification is sent to the Architect indicating the installed item is ready for inspection/observation. The Architect conducts regular inspections of the installed construction work. The findings of the inspections including any deficiencies are identified in the inspection report, the Contractor corrects them and requests a re-inspection.
Information Attributes
|  |  | Total | Owner | Architect | Contractor
|  | Current process cost: | 15940.7412 | 0 | 15918.6462 | 22.095
|  | COBie process cost: | 638.2369 | 0 | 638.2369 | 0
|  | Process Cost Difference: | 15302.5043 | 0 | 15280.4093 | 22.095
Process
| Current Process | [7 empty] | Expected Process
| 230.01 | Request Product Inspection | [6 empty] | 230.01 | Request Product Inspection
| 230.02 | Review Contract Drawings and Product Inspection Report | [6 empty] | 230.02 | Review Contract Drawings and Product Inspection Report
| 230.03 | Conduct Product Inspection | [6 empty] | 230.03 | Conduct Product Inspection
REFORMATTING/COBie | 230.04 | Reformat Product Inspection Report | [5 empty] | REFORMATTING/COBie | 230.04 | Reformat Product Inspection Report
|  | 1.5 | Avg. Field Time Spent Documenting Report per Site Visit (hours / visit) | [6 empty] | 0.6 | Avg. Field Time Spent Documenting Report per Site Visit (hours / visit)
|  | 4 | Avg. Number of Site Visits per month (visit / month) | [6 empty] | 4 | Avg. Number of Site Visits per month (visit / month)
|  | 12 | Avg. Number of Months of Construction (months) | [6 empty] | 12 | Avg Number of Months of Construction (months)
|  | 8 | Total Time Spent in Office (hours / day) | [6 empty] | 8 | Total Time Spent in Office (hours / day)
|  | 25% | Avg. Percentage of Office Time Spent Quantifying products-in-place | [6 empty] | 2.5% | Avg. Percentage of Office Time Spent Quantifying products-in-place
|  | 109.99 | Licensed Professional Architect Rate ($ / hour) |  |  | 15838.56 |  |  |  | 109.99 | Licensed Professional Architect Rate ($ / hour) | 633.5424
|  |  | SubTotal |  |  |  | 15838.56 |  |  |  | SubTotal |  | 633.5424
HANDLING/ ELEC.DOC. | 230.05 | Send Product Inspection Report to Contractor | [5 empty] | HANDLING/ ELEC.DOC. | 230.05 | Send Product Inspection Report to Contractor
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 16.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.083 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.0332 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 11.7362 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 4.6945
|  |  | Mailing Cost |  |  | 33 |  |  |  |  | Mailing Cost | 0
|  |  | SubTotal |  |  |  | 44.7362 |  |  |  | SubTotal |  | 4.6945
HANDLING/ ELEC.DOC. | 230.06 | Log Transmittal of Product Inspection Report | [5 empty] | HANDLING/ ELEC.DOC. | 230.06 | Log Transmittal of Product Inspection Report
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 70.7 | Architect Drafter Rate ($ / hour) |  |  | 35.35 |  |  |  | 70.7 | Architect Drafter Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 35.35 |  |  |  | SubTotal |  | 0
| 230.07 | Receive Product Inspection Report | [6 empty] | 230.07 | Receive Product Inspection Report
HANDLING/ ELEC.DOC. | 230.08 | Log Receipt of Product Inspection Report | [5 empty] | HANDLING/ ELEC.DOC. | 230.08 | Log Receipt of Product Inspection Report
|  | 2 | Avg. Number of Transmittals (Transmittals) | [6 empty] | 2 | Avg. Number of Transmittals (Transmittals)
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 44.19 | Contractor Administrative Rate ($ / hour) |  |  | 22.095 |  |  |  | 44.19 | Contractor Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 22.095 |  |  |  | SubTotal |  | 0
| 230.09 | Review Product Inspection Report | [6 empty] | 230.09 | Review Product Inspection Report
| 230.10 | Correct Deficiencies | [6 empty] | 230.10 | Correct Deficiencies
| 230.11 | Request Re-inspection | [6 empty] | 230.11 | Request Re-inspection
[6 empty] | Current Process Total | 15940.7412 |  |  |  |  | Expected Process Total | 638.2369

## 240_Punchlist_Issue
Process Name | Punchlist Issue
OmniClass Stage | 31-40 40 91 17 Evaluation Phase
OmniClass Role | 34-35 14 00 Contractor
Description | The Architect creates a final punchlist based upon a survey of the completed construction work. The Contractor corrects the deficiencies identified in the punchlist. The Architect verifies that the Contractor has corrected the deficiencies in the punchlist by performing a final walkthrough.
Information Attributes
|  | Total | Owner | Architect | Contractor
| Current process cost: | 0 | 0 | 0 | 0
| Expected process cost: | 0 | 0 | 0 | 0
| Process Cost Difference: | 0 | 0 | 0 | 0
Process
Current Process | [5 empty] | Expected Process
240.01 | Request Punchlist Issue Inspection |  |  |  |  | 240.01 | Request Punchlist Issue Inspection
240.02 | Review Contract Drawings |  |  |  |  | 240.02 | Review Contract Drawings
240.03 | Conduct Punchlist Issue Inspection |  |  |  |  | 240.03 | Conduct Punchlist Issue Inspection
240.04 | Reformat Punchlist Issue Report |  |  |  |  | 240.04 | Reformat Punchlist Issue Report
240.05 | Send Punchlist Issue Report to Contractor |  |  |  |  | 240.05 | Send Punchlist Issue Report to Contractor
240.06 | Log Transmittal of Punchlist Issue Report |  |  |  |  | 240.06 | Log Transmittal of Punchlist Issue Report
240.07 | Receive Punchlist Issue Report |  |  |  |  | 240.07 | Receive Punchlist Issue Report
240.08 | Log Receipt of Punchlist Issue Report |  |  |  |  | 240.08 | Log Receipt of Punchlist Issue Report
240.09 | Review Punchlist Issue Report |  |  |  |  | 240.09 | Review Punchlist Issue Report
240.10 | Correct Deficiencies |  |  |  |  | 240.10 | Correct Deficiencies
240.11 | Request Re-inspection |  |  |  |  | 240.11 | Request Re-inspection
|  |  |  | Current Process Total | 0 |  |  | Expected Process Total | 0

## 250_Turnover_Package
| Process Name | Turnover Package
| OmniClass Stage | 31-40 40 91 17 Evaluation Phase
| OmniClass Role | 34-35 14 00 Contractor
| Description | The Contractor gathers all the as-built information related to the project and forwards the information to the owner.
Information Attributes
|  |  | Total | Owner | Architect | Contractor
|  | Current process cost: | 27439.4048 | 63.3887 | 0 | 27376.0162
|  | Expected process cost: | 82.939 | 45.6773 | 0 | 37.2616
|  | Process Cost Difference: | 27356.4659 | 17.7114 | 0 | 27338.7545
Process
| Current Process | [7 empty] | Expected Process
SEARCHING/ ELEC.DOC. | 250.01 | Compile Turnover Package | [5 empty] | SEARCHING/ ELEC.DOC. | 250.01 | Compile Turnover Package
|  | 3 | Avg. Time Spent Searching and Assembling Operations & Maintenance Manuals (hours / document) | [6 empty] | 0.3 | Avg. Time Spent Searching and Assembling Operations & Maintenance Manuals (hours / document)
|  | 0.0008 | Avg. Time Spent Searching and Assembling Commissioning Report (hours / document) | [6 empty] | 8e-05 | Avg. Time Spent Searching and Assembling Commissioning Report (hours / document)
|  | 0.008 | Avg. Time Spent Searching and Assembling Record Specifications (hours / document) | [6 empty] | 0.0008 | Avg. Time Spent Searching and Assembling Record Specifications (hours / document)
|  | 90 | Avg. Number of Sheets in Record (As-Built) Drawings | [6 empty] | 90 | Avg. Number of Sheets in Record (As-Built) Drawings
|  | 0.008 | Avg. Time Spent Searching and Assembling Record (As-Built) Drawings (hours / sheet) | [6 empty] | 0.0008 | Avg. Time Spent Searching and Assembling Record (As-Built) Drawings (hours / sheet)
|  | 1 | Avg. Number of Sheets in Final Approved Shop Drawings | [6 empty] | 1 | Avg. Number of Sheets in Final Approved Shop Drawings
|  | 0.0083 | Avg. Time Spent Searching and Assembling Final Approved Shop Drawings (hours / sheet) | [6 empty] | 0.00083 | Avg. Time Spent Searching and Assembling Final Approved Shop Drawings (hours / sheet)
|  | 10% | Percentage of Time Spent by Construction Project Manager | [6 empty] | 10% | Percentage of Time Spent by Construction Project Manager
|  | 90% | Percentage of Time Spent by Assistant (Construction) Project Manager | [6 empty] | 90% | Percentage of Time Spent by Assistant (Construction) Project Manager
|  | 125.81 | Construction Project Manager Rate ($ / hour) |  |  | 47.0165 |  |  |  | 125.81 | Construction Project Manager Rate ($ / hour) | 4.7016
|  | 70.53 | Assistant (Construction) Project Manager Rate ($ / hour) |  |  | 237.2199 |  |  |  | 70.53 | Assistant (Construction) Project Manager Rate ($ / hour) | 23.722
|  |  | SubTotal |  |  |  | 284.2364 |  |  |  | SubTotal |  | 28.4236
COPYING/ ELEC.DOC. | 250.02 | Copy Turnover Package | [5 empty] | COPYING/ ELEC.DOC. | 250.02 | Copy Turnover Package
|  | 645 | Avg. Number of Pages in Operations & Maintenance Manuals (pages / product) | [6 empty] | 645 | Avg. Number of Pages in Operations & Maintenance Manuals (pages / product)
|  | 43 | Number of Unique Product Types (Types / project) | [6 empty] | 43 | Number of Unique Product Types (Types / project)
|  | 10 | Avg. Number of Pages in Commissioning Report (pages / component) | [6 empty] | 10 | Avg. Number of Pages in Commissioning Report (pages / component)
|  | 20 | Avg. Number of Components & Systems to be Commissioned | [6 empty] | 20 | Avg. Number of Components & Systems to be Commissioned
|  | 50 | Avg. Number of Pages in Record Specifications | [6 empty] | 50 | Avg. Number of Pages in Record Specifications
|  | 90 | Avg. Number of Sheets in Record (As-Built) Drawings | [6 empty] | 90 | Avg. Number of Sheets in Record (As-Built) Drawings
|  | 1 | Avg. Number of Sheets in Final Approved Shop Drawings | [6 empty] | 1 | Avg. Number of Sheets in Final Approved Shop Drawings
|  | 6 | Number of Submittal Sets Reqd. (sets / submittal) | [6 empty] | 0 | Number of Submittal Sets Reqd. (sets / submittal)
|  | 0.15 | Avg. Per Page Copy Cost ($ / page) | [6 empty] | 0 | Avg. Per Page Copy Cost ($ / page)
|  | 3 | Avg. Per Sheet Copy Cost ($ / sheet) | [6 empty] | 0 | Avg. Per Sheet Copy Cost ($ / sheet)
|  | 0.72278 | Avg. In-house Reproduction Time Per Set (hours/set) | [6 empty] | 0 | Avg. In-house Reproduction Time Per Set (hours/set)
|  | 44.19 | Contractor Administrative Rate ($ / hour) |  |  | 191.6373 |  |  |  | 44.19 | Contractor Administrative Rate ($ / hour) | 0
|  |  | Reproduction Costs |  |  | 26824.5 |  |  |  |  | Reproduction Costs | 0
|  |  | SubTotal |  |  |  | 27016.1373 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 250.03 | Send Copies of Turnover Package | [5 empty] | HANDLING/ ELEC.DOC. | 250.03 | Send Copies of Turnover Package
|  | 42.5 | Avg. Mailing Cost per Transmittal ($ / Transmittal) | [6 empty] | 0 | Avg. Mailing Cost per Transmittal ($ / Transmittal)
|  | 0.5 | Avg. Time to Prepare a Transmittal (hours/transmittal) | [6 empty] | 0.2 | Avg. Time to Prepare a Transmittal (hours/transmittal)
|  | 44.19 | Contractor Administrative Rate ($ / hour) |  |  | 22.095 |  |  |  | 44.19 | Contractor Administrative Rate ($ / hour) | 8.838
|  |  | Mailing Cost ($) |  |  | 42.5 |  |  |  |  | Mailing Cost ($) | 0
|  |  | SubTotal |  |  |  | 64.595 |  |  |  | SubTotal |  | 8.838
HANDLING/ ELEC.DOC. | 250.04 | Log Transmittal of the Turnover Package | [5 empty] | HANDLING/ ELEC.DOC. | 250.04 | Log Transmittal of the Turnover Package
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 44.19 | Contractor Administrative Rate ($ / hour) |  |  | 11.0475 |  |  |  | 44.19 | Contractor Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 11.0475 |  |  |  | SubTotal |  | 0
| 250.05 | Receive Copies of the Turnover Package | [6 empty] | 250.05 | Receive Copies of the Turnover Package
HANDLING/ ELEC.DOC. | 250.06 | Log Receipt of the Turnover Package | [5 empty] | HANDLING/ ELEC.DOC. | 250.06 | Log Receipt of the Turnover Package
|  | 0.25 | Time to Log (hours / transmittal) | [6 empty] | 0 | Time to Log (hours / transmittal)
|  | 23.71 | Owner Administrative Rate ($ / hour) |  |  | 5.9275 |  |  |  | 23.71 | Owner Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 5.9275 |  |  |  | SubTotal |  | 0
HANDLING/ ELEC.DOC. | 250.07 | Review Turnover Package | [5 empty] | HANDLING/ ELEC.DOC. | 250.07 | Review Turnover Package
|  | 645 | Avg. Number of Pages in Operations & Maintenance Manuals | [6 empty] | 645 | Avg. Number of Pages in Operations & Maintenance Manuals
|  | 0.0017 | Avg. Time Spent Reviewing Operations & Maintenance Manuals (hours/page) | [6 empty] | 0.0017 | Avg. Time Spent Reviewing Operations & Maintenance Manuals (hours/page)
|  | 10 | Avg. Number of Pages in Commissioning Report | [6 empty] | 10 | Avg. Number of Pages in Commissioning Report
|  | 0.0083 | Avg. Time Spent Reviewing Commissioning Report (hours/page) | [6 empty] | 0.0083 | Avg. Time Spent Reviewing Commissioning Report (hours/page)
|  | 50 | Avg. Number of Pages in Record Specifications | [6 empty] | 50 | Avg. Number of Pages in Record Specifications
|  | 0.0017 | Avg. Time Spent Reviewing Record Specifications (hours / page) | [6 empty] | 0 | Avg. Time Spent Reviewing Record Specifications (hours / page)
|  | 90 | Avg. Number of Sheets in Record (As-Built) Drawings | [6 empty] | 90 | Avg. Number of Sheets in Record (As-Built) Drawings
|  | 0.0083 | Avg. Time Spent Reviewing Record (As-Built) Drawings (hours /sheet) | [6 empty] | 0.0083 | Avg. Time Spent Reviewing Record (As-Built) Drawings (hours /sheet)
|  | 1 | Avg. Number of Sheets in Final Approved Shop Drawings | [6 empty] | 1 | Avg. Number of Sheets in Final Approved Shop Drawings
|  | 0.0083 | Avg. Time Spent Reviewing Final Approved Shop Drawings (hours/sheet) | [6 empty] | 0 | Avg. Time Spent Reviewing Final Approved Shop Drawings (hours/sheet)
|  | 23.71 | Owner Administrative Rate ($ / hour) |  |  | 47.8895 |  |  |  | 23.71 | Owner Administrative Rate ($ / hour) | 45.6773
|  |  | SubTotal |  |  |  | 47.8895 |  |  |  | SubTotal |  | 45.6773
HANDLING/ ELEC.DOC. | 250.08 | File Turnover Package | [5 empty] | HANDLING/ ELEC.DOC. | 250.08 | File Turnover Package
|  | 0.083 | Avg. Time Spent Filing Operations & Maintenance Manuals (hours / document) | [6 empty] | 0 | Avg. Time Spent Filing Operations & Maintenance Manuals (hours / document)
|  | 0.083 | Avg. Time Spent Filing Commissioning Report (hours/document) | [6 empty] | 0 | Avg. Time Spent Filing Commissioning Report (hours/document)
|  | 0.083 | Avg. Time Spent Filing Record Specifications (hours/document) | [6 empty] | 0 | Avg. Time Spent Filing Record Specifications (hours/document)
|  | 90 | Avg. Number of Sheets in Record (As-Built) Drawings | [6 empty] | 90 | Avg. Number of Sheets in Record (As-Built) Drawings
|  | 0.0017 | Avg. Time Spent Filing Record (As-Built) Drawings (hours/sheet) | [6 empty] | 0 | Avg. Time Spent Filing Record (As-Built) Drawings (hours/sheet)
|  | 1 | Avg. Number of Sheets in Final Approved Shop Drawings | [6 empty] | 1 | Avg. Number of Sheets in Final Approved Shop Drawings
|  | 0.0017 | Avg. Time Spent Filing Final Approved Shop Drawings(hours/sheet) | [6 empty] | 0 | Avg. Time Spent Filing Final Approved Shop Drawings(hours/sheet)
|  | 23.71 | Owner Administrative Rate ($ / hour) |  |  | 9.5717 |  |  |  | 23.71 | Owner Administrative Rate ($ / hour) | 0
|  |  | SubTotal |  |  |  | 9.5717 |  |  |  | SubTotal |  | 0
[6 empty] | Current Process Total | 27439.4048 |  |  |  |  | Expected Process Total | 82.939